Microsoft Word Virtual
Event Proposal Template Example

PROPOSAL FOR

GLOBAL INNOVATORS VIRTUAL SUMMIT 20XX

| PREPARED BY |  | DATE |
| --- | --- | --- |
| Denis Vidal, Digital Frontiers Institute |  | MM/DD/YY |

table of contents

1.	INTRODUCTION	3

2.	VIRTUAL EVENT CONCEPT	3

3.	OBJECTIVES AND EXPECTED OUTCOMES	3

4.	TARGET AUDIENCE AND ENGAGEMENT STRATEGY	3

5.	VIRTUAL PLATFORM AND TECHNOLOGY REQUIREMENTS	4

6.	CONTENT AND PROGRAM STRUCTURE	4

7.	INTERACTIVE ELEMENTS AND PARTICPANT ENGAGEMENT	4

8.	MARKETING AND ONLINE PROMOTION STRATEGY	4

9.	SPONSORSHIP AND VIRTUAL EXHIBITOR OPPORTUNITIES	4

10.	BUDGET AND RESOURCE PLAN	5

11.	PROJECT TIMELINE AND MILESTONES	5

12.	RISK MANAGEMENT AND CONTINGENCY PLANS	5

13.	CONCLUSION	5

14.	APPENDICES	5

# INTRODUCTION

The "Global Innovators Virtual Summit 20XX" is designed to connect thought leaders, technology pioneers, and entrepreneurs worldwide, facilitating discussions on the future of innovation in a dynamic virtual setting.

# virtual event concept

This summit will explore the theme "Innovation for a Sustainable Future," featuring sessions on renewable technologies, sustainable business practices, and the role of AI in environmental conservation. The virtual format allows global access, reducing carbon footprint and promoting inclusivity.

# OBJECTIVES and expected outcomes

- Foster global dialogue on sustainability and innovation. - Connect 10,000+ participants from over 100 countries. - Generate actionable insights and collaborative projects.

# TARGET AUDIENCE AND ENGAGEMENT STRATEGY

Targeting professionals in tech, sustainability, and policy sectors, the summit will use targeted social media campaigns, partnerships with eco-conscious organizations, and interactive pre-event webinars to build engagement.

# virtual platform and technology requirements

The summit will be hosted on "Virtu-Con," a platform offering high-quality streaming, interactive features like live Q&A, and virtual networking spaces. Participants will need a stable internet connection and a device capable of running the platform.

# CONTENT AND PROGRAM STRUCTURE

• Day 1: Keynotes on global trends in sustainability. • Day 2: Breakout sessions on sustainable technologies. • Day 3: Workshops on implementing innovation in business. • Networking and virtual expo available daily.

# interactive elements and particpant engagement

Live polls and Q&A will be integrated into sessions for real-time engagement, with gamified challenges encouraging exploration of the virtual expo hall. Virtual "coffee breaks" will facilitate networking.

# MARKETING AND ONLINE PROMOTION STRATEGY

A multichannel digital campaign, leveraging SEO, social media advertising, and influencer collaborations, aims to maximize registrations. Early bird and group discounts will incentivize early sign-ups.

# sponsorship and virtual exhibitor opportunities

Sponsors can host branded sessions and virtual booths and feature in digital swag bags. Tiered sponsorship packages offer varying levels of visibility and interaction opportunities.

# BUDGET AND RESOURCE PLAN

Projected budget of $150,000, covering platform licensing, speaker fees, marketing, and technical support. Anticipated revenue from registrations and sponsorships is estimated at $250,000.

# project timeline and milestones

• Nov 20XX: Finalize platform and begin speaker outreach. • Jan 20XX: Launch marketing campaign. • Mar 20XX: Open registration. • Jun 20XX: Host "Global Innovators Virtual Summit."

# risk management and contingency plans

Plans to address technological failures include backup streaming services and technical support hotlines. Strategies to boost engagement include pre-event content and interactive session reminders.

# CONCLUSION

The "Global Innovators Virtual Summit" presents a unique opportunity to lead the conversation on sustainable innovation, offering unparalleled access to global insights and fostering a community of forward thinkers.

# APPENDICES

• A: Detailed description of the Virtu-Con platform. • B: Preliminary list of speakers and topics. • C: Marketing strategy and promotional materials.

DOCUMENT SIGN-OFF

| PREPARED BY |  |  |
| --- | --- | --- |
| Denis Vidal, Digital Frontiers Institute |  |  |

| REVIEWED BY |
| --- |
| Lori Garcia, Head of Programming |  |

| APPROVAL |
| --- |
| Lori Garcia, Head of Programming |  |

DISCLAIMER Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.