## EXAMPLE - Change Mgmt Roadmap
Change Management Roadmap Template Example
Team / Organization Name | Name
Date | MM/DD/YY
Version | 1
OUTLINE
MILESTONE | CHANGE MANAGER | PRIORITY | AMOUNT OF WORK IN HOURS |  |  | START DATE | DUE DATE | STATUS | RESISTANCE TO CHANGE | DESCRIPTION
|  |  | ESTIMATE | COMPLETED | REMAINING
|  |  | 50 | 50 | 0 |  |  | 100%
Get stakeholder alignment | Alexandra Mattson | High | 40 | 40 | 0 | 2022-03-12 | 2022-03-15 | 100% | Low | Get stakeholder buy-in on project objectives and outcomes.
Perform change impact assessment | Brian Gorman | Medium | 25 | 23 | 2 | 2022-03-15 | 2022-03-16 | 92% | Medium | Complete a comprehensive analysis of the upcoming changes and the potential impact of each on various departments and processes.
Develop communication plan | Hilda Wilson | Low | 100 | 56 | 44 | 2022-03-15 | 2022-03-21 | 56% | High | Develop and approve a communication plan that outlines how and when the change will be communicated to the organization.
Roll-out training program | Makara McLean | High | 60 | 43 | 17 | 2022-03-16 | 2022-03-22 | 71.67% | Low | Design, develop, and deploy training programs to ensure all employees are prepared for the change.
| Guadalupe Garcia | Medium | 40 | 22 | 18 | 2022-03-17 | 2022-03-22 | 55% | Medium
| Petrus Nishimura | Medium | 32 | 22 | 10 | 2022-03-18 | 2022-03-22 | 68.75% | Medium
| Petrus Nishimura | Medium | 12 | 12 | 0 | 2022-03-23 | 2022-03-23 | 100% | Medium
| Makara McLean | Medium | 80 | 22 | 58 | 2022-03-24 | 2022-03-28 | 27.5% | Medium
| Guadalupe Garcia | Medium | 60 | 40 | 20 | 2022-03-29 | 2022-04-02 | 66.67% | Medium
| Petrus Nishimura | Medium | 40 | 0 | 40 |  |  | 0% | Medium
| Petrus Nishimura | Medium | 30 | 0 | 30 |  |  | 0% | Medium
| Hilda Wilson | Medium | 20 | 0 | 20 |  |  | 0% | Medium
| Alexandra Mattson | Medium | 20 | 0 | 20 |  |  | 0% | Medium
| Brian Gorman | Medium | 8 | 0 | 8 |  |  | 0% | Medium
| Brian Gorman | Medium | 12 | 0 | 12 |  |  | 0% | Medium
| Hilda Wilson | Medium | 4 | 0 | 4 |  |  | 0% | Medium
| Petrus Nishimura | Medium | 2 | 0 | 2 |  |  | 0% | Medium
CHANGE MANAGEMENT ROADMAP
Change Statement
This is a comprehensive initiative that will revolutionize our customer experience through strategic innovation, process optimization, and technological advancement, ensuring a seamless transition to a more agile and customer-centric operation.
Milestones | RESPONSIBLE | Cost | PRIORITY | START DATE | END DATE | DURATION in days
Get stakeholder alignment | Krista Ahmed | 12000 | High | 2028-01-16 | 2028-02-02 | 18
Perform change impact assessment | Tamika Marshall | 9500 | Medium | 2028-01-31 | 2028-02-05 | 6
Develop communication plan | Tamika Marshall | 7000 | Low | 2028-02-05 | 2028-02-15 | 11
Roll-out training program | Carmen Robertson | 15000 | High | 2028-01-22 | 2028-01-29 | 8
Milestone 5 | Krista Ahmed | 0 |  | 2028-01-28 | 2028-01-31 | 4
Milestone 6 | Jonathon Wong | 0 |  | 2028-01-29 | 2028-02-25 | 28
Milestone 7 | Carmen Robertson | 0 |  | 2028-02-28 | 2028-03-01 | 3
Milestone 8 | Leigh Gibbs | 0 |  | 2028-02-28 | 2028-03-04 | 6
Milestone 9 | Tamika Marshall | 0 |  | 2028-03-01 | 2028-03-16 | 16
Milestone 10 | Tamika Marshall | 0 |  | 2028-03-16 | 2028-03-17 | 2
Milestone 11 | Tamika Marshall | 0 |  | 2028-03-18 | 2028-03-20 | 3
Milestone 12 | Carmen Robertson | 0 |  | 2028-03-24 | 2028-04-16 | 24
Milestone 13 | Jonathon Wong | 0 |  | 2028-03-24 | 2028-03-26 | 3
Milestone 14 | Jonathon Wong | 0 |  | 2028-03-26 | 2028-04-05 | 11
Milestone 15 | Leigh Gibbs | 0 |  | 2028-04-06 | 2028-04-21 | 16
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Change Mgmt Roadmap
Change Management Roadmap Template
Team / Organization Name | Name
Date | MM/DD/YY
Version | 1
OUTLINE
MILESTONE | CHANGE MANAGER | PRIORITY | AMOUNT OF WORK IN HOURS |  |  | START DATE | DUE DATE | STATUS | RESISTANCE TO CHANGE | DESCRIPTION
|  |  | ESTIMATE | COMPLETED | REMAINING
|  |  | 50 | 50 | 0 |  |  | 100%
Milestone | Name |  | 50 | 25 | 25 |  |  | 50%
Milestone | Name |  | 30 | 10 | 20 |  |  | 33.33%
|  |  | 20 | 10 | 10 |  |  | 50%
0
0
0
0
0
0
0
0
0
0
0
0
0
0
CHANGE MANAGEMENT ROADMAP
Change Statement
[Insert statement here]
Milestones | RESPONSIBLE | Cost | PRIORITY | START DATE | END DATE | DURATION in days
Milestone 1 | Name | 0 | High
Milestone 2 |  | 0 | Medium
Milestone 3 |  | 0 | Low
Milestone 4 |  | 0
Milestone 5 |  | 0
Milestone 6 |  | 0
Milestone 7 |  | 0
Milestone 8 |  | 0
Milestone 9 |  | 0
Milestone 10 |  | 0
Milestone 11 |  | 0
Milestone 12 |  | 0
Milestone 13 |  | 0
Milestone 14 |  | 0
Milestone 15 |  | 0
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
PRIORITY and RESISTANCE TO CHANGE
Low
Medium
High

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.