## EXAMPLE Multi-Project Tracking
SIMPLE MULTIPLE PROJECT TRACKING TEMPLATE for Excel - EXAMPLE
COMPANY NAME |  |  |  |  | START DATE
Valley View Inc. |  |  |  |  | 2027-03-01
Fill in the non-shaded cells only.
TRACKING |  | PROJECT INFORMATION | [5 empty] | DELIVERABLES |  | COST / HOURS |  |  | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk 4 |  |  |  |  | Wk 5 |  |  |  |  | Wk 6 |  |  |  |  | Wk 7 |  |  |  |  | Wk 8 |  |  |  |  | Wk 9 |  |  |  |  | Wk 10 |  |  |  |  | Wk 11 |  |  |  |  | Wk 12 |  |  |  |  | Wk 13 |  |  |  |  | Wk 14 |  |  |  |  | Wk 15 |  |  |  |  | Wk 16 |  |  |  |  | Wk 17 |  |  |  |  | Wk 18 |  |  |  |  | Wk 19 |  |  |  |  | Wk 20
STATUS | PRIORITY | PROJECT NAMES + TASK TITLES | TASK DESCRIPTION | TASK OWNER | START DATE | END DATE | # of Days | DELIVERABLE | % COMPLETE | FIXED COST | EST. HOURS | ACTUAL HOURS | time axis 2027-03-01 to 2027-07-16
On Hold | MED | NEW PRODUCT LAUNCH | Launching New Product to the Public | Lori G. | 2027-03-01 | 2027-04-21 | 38 | Meeting scheduled with stakeholders and leadership team | 74.33% | 22530 | 306 | 298 | bar: 2027-03-01 to 2027-04-21
In Progress | MED | Stakeholder Meeting | Initial meeting with stakeholders to discuss project | Denis V. | 2027-03-01 | 2027-04-03 | 25 | List of goals, objectives, and timelines | 33% | 8500 | 32 | 36 | bar: 2027-03-01 to 2027-04-02
Complete | HIGH | Define Project | Define scope and objectives | Eugene M. | 2027-04-02 | 2027-04-18 | 11 | Market analysis and competitive landscape | 100% | 2500 | 104 | 100 | bar: 2027-04-02 to 2027-04-16
In Progress | LOW | Market Research | Research current market trends and competitors | Hilda C. | 2027-04-13 | 2027-04-18 | 4 | Budget and resource allocation plan | 90% | 3200 | 40 | 40 | bar: 2027-04-13 to 2027-04-16
In Progress | MED | Budget and Resources | Meet with finance officer and research resources | Lori G. | 2027-04-03 | 2027-04-12 | 6 | Product prototype presentation deck | 33% | 750 | 50 | 56 | bar: 2027-04-05 to 2027-04-12
Complete | LOW | Product Prototype | Create a prototype of the product for testing and evaluation | Eugene M. | 2027-04-09 | 2027-04-20 | 8 |  | 100% | 6380 | 64 | 56 | bar: 2027-04-09 to 2027-04-20
On Hold | MED | P1 Task 6 |  |  | 2027-04-18 | 2027-04-21 | 3 |  | 90% | 1200 | 16 | 10 | bar: 2027-04-19 to 2027-04-21
Overdue | HIGH | PROJECT 2 |  |  | 2027-03-03 | 2027-10-01 | 153 |  | 21.67% | 16700 | 792 | 367 | bar: 2027-03-03 to 2027-07-16
Needs Review | MED | P2 Task 1 |  |  | 2027-03-03 | 2027-04-15 | 32 |  | 70% | 2200 | 350 | 356 | bar: 2027-03-03 to 2027-04-15
Needs Update | MED | P2 Task 2 |  |  | 2027-04-30 | 2027-05-02 | 1 |  | 60% | 14500 | 20 | 11 | bar: 2027-04-30
Not Started | MED | P2 Task 3 |  |  | 2027-05-05 | 2027-10-01 | 108 |  | 0% |  | 272 | bar: 2027-05-05 to 2027-07-16
Not Started | MED | P2 Task 4 |  |  | 2027-05-06 | 2027-06-03 | 21 |  | 0% |  | 150 | bar: 2027-05-06 to 2027-06-03
Not Started | MED | P2 Task 5 |  |  |  |  | 0 |  | 0%
Not Started | MED | P2 Task 6 |  |  |  |  | 0 |  | 0%
Not Started | MED | PROJECT 3 |  |  | 2025-04-15 | 2027-04-18 | 524 |  | 74.33% | 8350 | 112 | 99 | bar: 2027-03-02 to 2027-04-16
Not Started | MED | P3 Task 1 |  |  | 2027-03-15 | 2027-04-18 | 25 |  | 33% | 6500 | 40 | 36 | bar: 2027-03-15 to 2027-04-16
Not Started | MED | P3 Task 2 |  |  | 2025-04-15 | 2025-04-16 | 2 |  | 100% |  | 16 | 12
Not Started | MED | P3 Task 3 |  |  | 2025-04-17 | 2025-04-17 | 1 |  | 90% |  | 5 | 5
Not Started | MED | P3 Task 4 |  |  | 2025-04-21 | 2025-04-24 | 4 |  | 33% |  | 32 | 22
Not Started | MED | P3 Task 5 |  |  | 2025-04-22 | 2025-04-23 | 2 |  | 100% | 1850 | 14 | 16
Not Started | MED | P3 Task 6 |  |  | 2025-04-25 | 2025-04-25 | 1 |  | 90% |  | 5 | 8
Not Started | MED | PROJECT 4 |  |  | 2027-03-01 | 2027-04-06 | 27 |  | 0% | 0 | 0 | 0 | bar: 2027-03-01 to 2027-04-06
Not Started | MED | P4 Task 1 |  |  | 2027-03-01 | 2027-03-02 | 2 |  | 0% | bar: 2027-03-01 to 2027-03-02
Not Started | MED | P4 Task 2 |  |  | 2027-04-01 | 2027-04-06 | 4 |  | 0% | bar: 2027-04-01 to 2027-04-06
Not Started | MED | P4 Task 3 |  |  | 2027-03-15 | 2027-03-20 | 5 |  | 0% | bar: 2027-03-15 to 2027-03-19
Not Started | MED | P4 Task 4 |  |  | 2027-03-16 | 2027-03-21 | 4 |  | 0% | bar: 2027-03-16 to 2027-03-19
Not Started | MED | P4 Task 5 |  |  |  |  | 0 |  | 0%
Not Started | MED | P4 Task 6 |  |  |  |  | 0 |  | 0%
Not Started | MED | PROJECT 5 |  |  | 2027-03-03 | 2027-05-12 | 51 |  | 0% | 0 | 0 | 0 | bar: 2027-03-03 to 2027-05-12
Not Started | MED | P5 Task 1 |  |  | 2027-03-03 | 2027-05-01 | 43 |  | 0% | bar: 2027-03-03 to 2027-04-30
Not Started | MED | P5 Task 2 |  |  | 2027-03-07 | 2027-05-12 | 48 |  | 0% | bar: 2027-03-08 to 2027-05-12
Not Started | MED | P5 Task 3 |  |  |  |  | 0 |  | 0%
Not Started | MED | P5 Task 4 |  |  |  |  | 0 |  | 0%
Not Started | MED | P5 Task 5 |  |  |  |  | 0 |  | 0%
Not Started | MED | P5 Task 6 |  |  |  |  | 0 |  | 0%
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Multi-Project Tracking
SIMPLE MULTIPLE PROJECT TRACKING TEMPLATE for Excel
COMPANY NAME |  |  |  |  | START DATE
2027-03-01
Fill in the non-shaded cells only.
TRACKING |  | PROJECT INFORMATION | [5 empty] | DELIVERABLES |  | COST / HOURS |  |  | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk 4 |  |  |  |  | Wk 5 |  |  |  |  | Wk 6 |  |  |  |  | Wk 7 |  |  |  |  | Wk 8 |  |  |  |  | Wk 9 |  |  |  |  | Wk 10 |  |  |  |  | Wk 11 |  |  |  |  | Wk 12 |  |  |  |  | Wk 13 |  |  |  |  | Wk 14 |  |  |  |  | Wk 15 |  |  |  |  | Wk 16 |  |  |  |  | Wk 17 |  |  |  |  | Wk 18 |  |  |  |  | Wk 19 |  |  |  |  | Wk 20
STATUS | PRIORITY | PROJECT NAMES + TASK TITLES | TASK DESCRIPTION | TASK OWNER | START DATE | END DATE | # of Days | DELIVERABLE | % COMPLETE | FIXED COST | EST. HOURS | ACTUAL HOURS | time axis 2027-03-01 to 2027-07-16
On Hold | MED | PROJECT 1 |  |  | 0 | 0 | 0 |  | 74.33% | 0 | 0 | 0
In Progress | MED | P1 Task 1 |  |  |  |  | 0 |  | 33% | 0 | 0 | 0
Complete | HIGH | P1 Task 2 |  |  |  |  | 0 |  | 100% | 0 | 0 | 0
In Progress | LOW | P1 Task 3 |  |  |  |  | 0 |  | 90% | 0 | 0 | 0
In Progress | MED | P1 Task 4 |  |  |  |  | 0 |  | 33% | 0 | 0 | 0
Complete | LOW | P1 Task 5 |  |  |  |  | 0 |  | 100% | 0 | 0 | 0
On Hold | MED | P1 Task 6 |  |  |  |  | 0 |  | 90% | 0 | 0 | 0
Overdue | HIGH | PROJECT 2 |  |  | 0 | 0 | 0 |  | 21.67% | 0 | 0 | 0
Needs Review | MED | P2 Task 1 |  |  |  |  | 0 |  | 70% | 0 | 0 | 0
Needs Update | MED | P2 Task 2 |  |  |  |  | 0 |  | 60% | 0 | 0 | 0
Not Started | MED | P2 Task 3 |  |  |  |  | 0 |  | 0% |  | 0
Not Started | MED | P2 Task 4 |  |  |  |  | 0 |  | 0% |  | 0
Not Started | MED | P2 Task 5 |  |  |  |  | 0 |  | 0%
Not Started | MED | P2 Task 6 |  |  |  |  | 0 |  | 0%
Not Started | MED | PROJECT 3 |  |  | 0 | 0 | 0 |  | 74.33% | 8350 | 112 | 99
Not Started | MED | P3 Task 1 |  |  |  |  | 0 |  | 33% | 6500 | 40 | 36
Not Started | MED | P3 Task 2 |  |  |  |  | 0 |  | 100% |  | 16 | 12
Not Started | MED | P3 Task 3 |  |  |  |  | 0 |  | 90% |  | 5 | 5
Not Started | MED | P3 Task 4 |  |  |  |  | 0 |  | 33% |  | 32 | 22
Not Started | MED | P3 Task 5 |  |  |  |  | 0 |  | 100% | 1850 | 14 | 16
Not Started | MED | P3 Task 6 |  |  |  |  | 0 |  | 90% |  | 5 | 8
Not Started | MED | PROJECT 4 |  |  | 0 | 0 | 0 |  | 0% | 0 | 0 | 0
Not Started | MED | P4 Task 1 |  |  |  |  | 0 |  | 0%
Not Started | MED | P4 Task 2 |  |  |  |  | 0 |  | 0%
Not Started | MED | P4 Task 3 |  |  |  |  | 0 |  | 0%
Not Started | MED | P4 Task 4 |  |  |  |  | 0 |  | 0%
Not Started | MED | P4 Task 5 |  |  |  |  | 0 |  | 0%
Not Started | MED | P4 Task 6 |  |  |  |  | 0 |  | 0%
Not Started | MED | PROJECT 5 |  |  | 0 | 0 | 0 |  | 0% | 0 | 0 | 0
Not Started | MED | P5 Task 1 |  |  |  |  | 0 |  | 0%
Not Started | MED | P5 Task 2 |  |  |  |  | 0 |  | 0%
Not Started | MED | P5 Task 3 |  |  |  |  | 0 |  | 0%
Not Started | MED | P5 Task 4 |  |  |  |  | 0 |  | 0%
Not Started | MED | P5 Task 5 |  |  |  |  | 0 |  | 0%
Not Started | MED | P5 Task 6 |  |  |  |  | 0 |  | 0%

## Dropdown Keys DO NOT DELETE
KEYS
STATUS | PRIORITY
Not Started | LOW
In Progress | MED
Complete | HIGH
On Hold
Overdue
Needs Review
Needs Update

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.