## Project Portfolio Scorecard
PROJECT PORTFOLIO SCORECARD TEMPLATE
PROJECT MANAGEMENT OFFICE | PRIORITY | STATUS | PLANNED | ACTUAL | PLANNED LESS ACTUAL | OWNER | COMMENTARY | OUTCOMES OF RISK ANALYSIS | BUDGET IMPACT | COST BENEFIT ANALYSIS | DATE MODIFIED | PRIORITY KEY | STATUS KEY
PROJECTS COMPLETE # |  |  | 6 | 6 | 0 | Chris K. | We've completed the six projects planned through Q3. |  |  |  |  | HIGH | GREEN
TIME TO MOBILIZE IN DAYS |  |  | 7 | 6 | 1 | Chris K. | Mobilization is occurring one day faster than planned through Q3. |  |  |  |  | MEDIUM | YELLOW
TOTAL PORTFOLIO COST SAVINGS |  |  | 263000 | 181000 | 82000 | Greta L. | The additional benefits gained in Project Alpha more than offset the overruns in Project Beta. |  |  |  |  | LOW | RED
[12 empty] | ON HOLD | GREY
KEY PERFORMANCE INDICATOR (KPI) | PRIORITY | STATUS | PLANNED | ACTUAL | PLANNED LESS ACTUAL | OWNER | COMMENTARY | OUTCOMES OF RISK ANALYSIS | BUDGET IMPACT | COST BENEFIT ANALYSIS | DATE MODIFIED
PROJECT ALPHA | HIGH | YELLOW
Costs/Savings Realized ($) | LOW | YELLOW | 195000 | 100000 | 95000 | Chris K. | The cost savings continue to come in more than planned.
Scheduled Hours (hours) | ON HOLD | RED | 600 | 240 | 360 | Chris K. | The effort is less than budgeted.
Quality Index (1-100) | HIGH | GREY | 97 | 7 | 90 | Greta L. | #1 in sight by EOY on current growth trend
0
PROJECT BETA
Costs/Savings Realized ($) | MEDIUM | RED | 68000 | 81000 | -13000 | Jeffrey L. | Cost overruns are because the work is more complex than anticipated.
Scheduled Hours (hours) | MEDIUM | GREEN | 580 | 180 | 400 | Mark D. | The effort involved in Project Beta continues to be more than planned.
Quality Index (1-100) | LOW | YELLOW | 72 | 18 | 54 | John J. | Our QA processes are currently under review.
(add a key performance measure) |  |  |  |  | 0 | John J.
(Project Name)
(add a key performance measure) |  |  |  |  | 0 | Name
(Project Name)
(add a key performance measure) |  |  |  |  | 0
0
CLICK HERE TO CREATE PROJECT PORTFOLIO SCORECARD TEMPLATES IN SMARTSHEET

## BLANK - Proj Port Scorecard
PROJECT PORTFOLIO SCORECARD TEMPLATE
PROJECT MANAGEMENT OFFICE | PRIORITY | STATUS | PLANNED | ACTUAL | PLANNED LESS ACTUAL | OWNER | COMMENTARY | OUTCOMES OF RISK ANALYSIS | BUDGET IMPACT | COST BENEFIT ANALYSIS | DATE MODIFIED | PRIORITY KEY | STATUS KEY
PROJECTS COMPLETE # |  |  |  |  | 0 | [6 empty] | HIGH | GREEN
TIME TO MOBILIZE IN DAYS |  |  |  |  | 0 | [6 empty] | MEDIUM | YELLOW
TOTAL PORTFOLIO COST SAVINGS (add all projects) |  |  | 0 | 0 | 0 | [6 empty] | LOW | RED
[12 empty] | ON HOLD | GREY
KEY PERFORMANCE INDICATOR (KPI) | PRIORITY | STATUS | PLANNED | ACTUAL | PLANNED LESS ACTUAL | OWNER | COMMENTARY | OUTCOMES OF RISK ANALYSIS | BUDGET IMPACT | COST BENEFIT ANALYSIS | DATE MODIFIED
PROJECT NAME
Costs/Savings Realized ($) |  |  | 0 | 0 | 0
Scheduled Hours (hours) |  |  | 0 | 0 | 0
Quality Index (1-100) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
PROJECT NAME
Costs/Savings Realized ($) |  |  | 0 | 0 | 0
Scheduled Hours (hours) |  |  | 0 | 0 | 0
Quality Index (1-100) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
PROJECT NAME
Costs/Savings Realized ($) |  |  | 0 | 0 | 0
Scheduled Hours (hours) |  |  | 0 | 0 | 0
Quality Index (1-100) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
PROJECT NAME
Costs/Savings Realized ($) |  |  | 0 | 0 | 0
Scheduled Hours (hours) |  |  | 0 | 0 | 0
Quality Index (1-100) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0
(add a key performance measure) |  |  | 0 | 0 | 0