Microsoft Word Conference Event 
Proposal Template Example

PROPOSAL FOR

FUTURE OF FINTECH 20XX

| PREPARED BY |  | DATE |
| --- | --- | --- |
| Paul Finley |  | MM/DD/YY |

table of contents

1.	EXECUTIVE SUMMARY	3

2.	CONFERENCE OVERVIEW	3

3.	OBJECTIVES AND GOALS	4

4.	TARGET AUDIENCE	4

5.	PROPOSED VENUE AND DATE	5

6.	CONFERENCE PROGRAM	5

7.	KEYNOTE SPEAKERS  AND PANELISTS	6

8.	SPONSORSHIP OPPORTUNITIES	6

9.	MARKETING AND PROMOTION STRATEGY	7

10.	BUDGET OVERVIEW	7

11.	LOGISTICS AND OPERATIONS PLAN	8

12.	RISK MANAGEMENT PLAN	8

13.	CONCLUSION	9

14.	APPENDICES	9

| # EXECUTIVE SUMMARY | "Future of FinTech 20XX" aims to be the premier global conference that explores the next wave of innovation in financial technology. This event seeks to bring together industry leaders, startups, investors, and regulators to discuss trends, challenges, and opportunities that are shaping the future of finance. |
| --- | --- |

| # conference overview | Scheduled for October 20-22, 20XX, in New York City, this three-day conference will feature a mix of keynote presentations, panel discussions, interactive workshops, and networking events, all focused on advancing the FinTech industry. |
| --- | --- |

| - objectives and goals | • To showcase the latest innovations and trends in FinTech. • To facilitate networking and collaboration among FinTech professionals. • To provide insights into regulatory challenges and opportunities. |
| --- | --- |

| - target audience | Our target audience includes financial industry professionals, tech entrepreneurs, investors, policymakers, and academics interested in FinTech innovations and trends. |
| --- | --- |

| - PROPOSED VENUE AND DATE | The New York Marriott Marquis, located in the heart of Times Square, offers an ideal setting for our conference, providing ample space for sessions, exhibitions, and networking. The proposed dates are October 20-22, 20XX, to coincide with New York FinTech Week. |
| --- | --- |

| - CONFERENCE PROGRAM | Day 1: Keynote on "The Future of Money," followed by panels on blockchain technology and digital currencies. Day 2: Workshops on AI in financial services, followed by a startup pitch competition. Day 3: Panel discussions on regulatory landscapes, closing with a networking gala. |
| --- | --- |

| - KEYNOTE SPEAKERS AND PANELISTS | Lori Garcia: CEO of Crypto Innovate, speaking on the impact of blockchain. John Smith: Renowned economist, discussing global trends in digital finance. |
| --- | --- |

| - SPONSORSHIP OPPORTUNITIES | Platinum Package: This $50,000 sponsorship level includes main stage naming rights, an exhibition booth, and VIP meeting opportunities. Gold Package: This $30,000 sponsorship level includes session sponsorship, a booth space, and a special mention during the opening. |
| --- | --- |

| - marketing and promotion strategy | We have a comprehensive strategy that leverages social media, partnerships with major financial publications, email campaigns, and targeted outreach to financial institutions and tech companies. |
| --- | --- |

| - budget overview | The estimated total cost is $300,000, with revenue streams from ticket sales, sponsorships, and exhibitor fees that are projected to reach $450,000. |
| --- | --- |

| - LOGISTICS AND OPERATIONS PLAN | Provide details on registration processes, technology setup for virtual attendees, catering arrangements, and accommodations for speakers. |
| --- | --- |

| - RISK MANAGEMENT PLAN | Provide your plans to address potential risks, including technology failures, health and safety protocols, and strategies for virtual integration in case of travel restrictions. |
| --- | --- |

| - CONCLUSION | "Future of FinTech 20XX" will serve as a critical platform for understanding and shaping the future of finance. Your support in bringing this vision to life is invaluable. |
| --- | --- |

| - APPENDICES | A: Floor plans for New York Marriott Marquis. B: Detailed budget breakdown. C: Speaker invitation letters. |
| --- | --- |

DOCUMENT SIGN-OFF

| PREPARED BY |  |  |
| --- | --- | --- |
| Paul Finley, Fin Innovations LLC |  |  |

| REVIEWED BY |
| --- |
| Denis Vidal, Director of Conference Planning |  |

| APPROVAL |
| --- |
| Romy Bailey, VP of Planning |  |

DISCLAIMER Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.