## Simple User Story Map
Simple User Story Map Template
Project Name | Name
Version | 0
Date | MM/DD/YY
Team Members | Name
USER STORY MAP
TASK 1 | TASK 2 | TASK 3 | TASK 4
Subtask / Epic | Subtask / Epic | Subtask / Epic | Subtask / Epic
Subtask / Epic | Subtask / Epic | Subtask / Epic | Subtask / Epic
USER STORY | PRIORITY | STATUS | STORY POINTS | OWNER | RELEASE
Story | LOW | COMPLETE | 1 | Name | 1
| MEDIUM | IN PROCESS | 2 |  | 2
| HIGH | NOT STARTED | 3 |  | 3
OVERDUE
RELEASE PLANNING
RELEASE NO. | STORIES INCLUDED |  | RELEASE DATE
1 |  |  | MM/DD/YY
2 |  |  | MM/DD/YY
3 |  |  | MM/DD/YY
4 |  |  | MM/DD/YY
NOTES AND COMMENTS
Description
CLICK HERE TO CREATE IN SMARTSHEET
Story 1
Story 2
Story 3
Story 4
Story 1
Story 2
Story 3
Story 4
Story 1
Story 2
Story 3
Story 4
Story 1
Story 2
Story 3
Story 4

## EXAMPLE Simple User Story Map
Simple User Story Map Template Example
Project Name | My Product Development
Version | 123
Date | MM/DD/YY
Team Members | John (Project Manager), Lisa (Development), Mark (Quality)
USER STORY MAP
HIGH LEVEL ACTIVITY | SIGN UP | BROWSE PRODUCTS | CHECK OUT
Subtask / Epic | Create Account | View Product Listings | Add to Cart
| Social Media Sign Up | Filter Products | Apply Discount Codes
| Email Verification | View Product Details | Select Payment Method
USER STORY | PRIORITY | STATUS | STORY POINTS | OWNER | RELEASE
As a user, I want to create an account using my email so I can log in securely. | HIGH | NOT STARTED | 3 | Lisa | 1
As a user, I want to sign in using my social media accounts so I can save time. | MEDIUM | IN PROCESS | 5 | Lisa | 1
As a user, I want to filter products by category so I can find what I need quickly. | HIGH | NOT STARTED | 8 | Mark | 2
As a user, I want to view product details so I can make informed purchase decisions. | HIGH | NOT STARTED | 5 | John | 1
As a user, I want to add items to my cart so I can purchase them later. | HIGH | NOT STARTED | 3 | Mark | 1
As a user, I want to apply discount codes so I can save money on my purchases. | MEDIUM | NOT STARTED | 3 | Lisa | 2
As a user, I want to select a payment method so I can complete my purchase. | HIGH | NOT STARTED | 3 | John | 1
RELEASE PLANNING
RELEASE NO. | STORIES INCLUDED |  | RELEASE DATE
1 |  |  | MM/DD/YY
2 |  |  | MM/DD/YY
3 |  |  | MM/DD/YY
4 |  |  | MM/DD/YY
NOTES AND COMMENTS
Note - Ensure that email verification process is robust to prevent spam accounts. Comment - Consider adding more social media sign-in options in future releases.
Account Creation
Social Sign-In
View Product Details
Add to Cart
Filter Products
Apply Discount Codes
Story 1
Story 2
Story 3
Story 4
Story 1
Story 2
Story 3
Story 4
Select Payment Method

## Dropdown Keys - Do Not Delete
Dropdown Keys - Do Not Delete
PRIORITY | STATUS
LOW | COMPLETE
MEDIUM | IN PROCESS
HIGH | NOT STARTED
OVERDUE

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.