## Lessons Learned BLANK
Agile Retrospective Lessons Learned Template
PROJECT NAME |  |  | DATE OF LAST UPDATE | DATE OF FAILURE
|  |  | 07/31/20XX | 07/15/20XX
PARTICIPANTS
PROJECT SUMMARY
DESCRIPTION OF PROJECT FAILURE
POSSIBLE CAUSES OF PROJECT FAILURE
SIGNS OF IMPENDING FAILURE
WHAT WENT WRONG?
KEY POTENTIAL RISKS & ACTION PLAN
IDENTIFIED RISKS | RANK | ACTION ITEM | OWNER | DEADLINE | RESPONSE KEY
| Mitigate |  |  |  | Mitigate
| Transfer |  |  |  | Avoid
| Avoid |  |  |  | Transfer
| Accept |  |  |  | Accept
CLICK HERE TO CREATE IN SMARTSHEET

## Lessons Learned EXAMPLE
Agile Retrospective Lessons Learned Template Example
PROJECT NAME |  |  | DATE OF LAST UPDATE | DATE OF FAILURE
EV Charging App Enhancement |  |  | 07/31/20XX | 07/15/20XX
PARTICIPANTS
Diana Kennedy
Everett Crosse
Fiorella Fitzgerald
Guadalupe Garcia
Hazel Christensen
PROJECT SUMMARY
The project aimed to enhance the EV charging app with new features, improve user experience, and integrate advanced analytics to provide better insights to users.
DESCRIPTION OF PROJECT FAILURE
The project faced multiple delays and did not meet the initial deadline, resulting in missed milestones and unsatisfactory performance of the new features.
POSSIBLE CAUSES OF PROJECT FAILURE
Inadequate documentation and unclear requirements
Overreliance on external vendors for critical components
Insufficient testing and quality assurance processes
SIGNS OF IMPENDING FAILURE
Frequent miscommunications and misunderstandings among team members
Consistent delays in task completion and missed deadlines
Increasing number of unresolved bugs and issues during the sprint
WHAT WENT WRONG?
Poorly defined project scope leading to scope creep
Lack of proper risk management and contingency planning
Inadequate resource allocation and time management
KEY POTENTIAL RISKS & ACTION PLAN
IDENTIFIED RISKS | RANK | ACTION ITEM | OWNER | DEADLINE | RESPONSE KEY
Incomplete Documentation | Mitigate | Develop comprehensive documentation guidelines. | Diana Kennedy | 08/07/20XX | Mitigate
Dependency on External Vendors | Transfer | Establish clear contracts with penalties for delays. | Everett Crosse | 08/14/20XX | Avoid
Insufficient Testing | Mitigate | Implement automated testing tools and processes. | Fiorella Fitzgerald | 08/21/20XX | Transfer
Scope Creep | Avoid | Define and enforce a strict project scope with regular reviews. | Guadalupe Garcia | 08/07/20XX | Accept
Resource Allocation | Accept | Monitor and adjust resource allocation as needed. | Hazel Christensen | Ongoing, with monthly reviews

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.