## Event Project Timeline
Event Project Timeline Spreadsheet Template
Enter the date of the first Monday of each month ----> | PHASE ONE | [8 empty] | PHASE TWO | [9 empty] | PHASE THREE | [9 empty] | PHASE FOUR | [8 empty] | PHASE FIVE | [7 empty] | PHASE SIX
| JANUARY |  |  |  | FEBRUARY |  |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  |  | MAY |  |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUGUST |  |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  |  | DECEMBER
| 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 |  | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 |  | 4 | 11 | 18 | 25 |  | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28
PROJECT WEEK | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
PHASE ONE
Initial Planning and Research
PHASE TWO
Detailed Planning and Budgeting
PHASE THREE
Organizing and Booking
PHASE FOUR
Promotion and Final Preparations
PHASE FIVE
Execution and Follow-Up
CLICK HERE TO CREATE IN SMARTSHEET | bar: 1 to APRIL 27 22
PROJECT END
Define obectives
Set budget
Research venues
Refine plan
Allocate budget
Contract vendors
Draft timeline
Identify risks
Conduct initial marketing
Plan logistics
Arrange speakers
Book vendors
Secure venue
Launch marketing
Finalize program
Confirm details
Send invitations
Execute event
Conduct post-event surveys
Make final payments
TODAY

## Blank Event Project Timeline
Event Project Timeline Spreadsheet Template
Enter the date of the first Monday of each month ----> | PHASE ONE | [8 empty] | PHASE TWO | [9 empty] | PHASE THREE | [9 empty] | PHASE FOUR | [8 empty] | PHASE FIVE
| JANUARY |  |  |  | FEBRUARY |  |  |  |  | MARCH |  |  |  |  | APRIL |  |  |  |  | MAY |  |  |  |  | JUNE |  |  |  |  | JULY |  |  |  | AUGUST |  |  |  |  | SEPTEMBER |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  |  | DECEMBER
| 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 |  | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27 |  | 4 | 11 | 18 | 25 |  | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28
PROJECT WEEK | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
PHASE ONE
Initial Planning and Research
PHASE TWO
Detailed Planning and Budgeting Planning
PHASE THREE
Organizing and Booking
PHASE FOUR
Promotion and Final Preparations
PHASE FIVE
Execution and Follow -Up
PROJECT END
TODAY
Venue Research
Set Budget
Define Objectives
Refine Plan
Allocate Budget
Contact Vendors
Draft Timeline
Identify Risks
Initial Marketing
Secure Venue
Book Vendors
Arrange Speakers
Logistics Planning
Launch Marketing
Finalize Program
Confirm Details
Send Invitations
Final Payments
Event Execution
Post-Event Surveys

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.