## EXAMPLE - Agile Test Estimation
Agile Test Estimation Template – Example
TITLE
Agile Test Estimation for Positive Charge's EV Charging System
PREPARED BY |  | DATE | VERSION | TEST ID
Carmen Robertson |  | 07/15/20XX | 1.0 | – – – – –
ESTIMATION
Enter non-shaded cells only. Shaded formula fields will calculate automatically.
ESTIMATED EFFORT |  | BUFFER % | BUFFER AMOUNT | TOTAL ESTIMATED EFFORT
94 |  | 10% | 9.4 | 103.4
( TASKS TOTAL + PHASES TOTAL ) |  | Enter Percentage | ( EST * BUFFER % ) | ( EFFORT + BUFFER )
TEST TASKS
TASK ID | TASK DESCRIPTION | ESTIMATED EFFORT in Hours | RESOURCE ASSIGNED | START DATE | END DATE
T001 | Test user login functionality | 5 | Jamal King | 07/16/20XX | 07/16/20XX
T002 | Test initiation of charging session | 8 | Petrus Nishimura | 07/17/20XX | 07/17/20XX
T003 | Test charging status updates | 6 | Tamika Marshall | 07/18/20XX | 07/18/20XX
TOTAL TEST TASKS ESTIMATED EFFORT |  | 19
TEST PHASES
TEST PHASE |  | ESTIMATED EFFORT in Hours
Test Planning |  | 10
Test Design |  | 12
Test Execution |  | 40
Defect Management |  | 8
Test Reporting |  | 5
TOTAL TEST PHASES ESTIMATED EFFORT |  | 75
ASSUMPTIONS
1 | Stable internet connection is available for all tests
2 | Test data is prepared and validated before the test execution phase
RISKS
1 | Potential delays due to unforeseen defects
2 | Resource availability issues
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Agile Test Estimation
Agile Test Estimation Template
TITLE
PREPARED BY |  | DATE | VERSION | TEST ID
ESTIMATION
Enter non-shaded cells only. Shaded formula fields will calculate automatically.
ESTIMATED EFFORT |  | BUFFER % | BUFFER AMOUNT | TOTAL ESTIMATED EFFORT
0 |  | 0% | 0 | 0
( TASKS TOTAL + PHASES TOTAL ) |  | Enter Percentage | ( EST * BUFFER % ) | ( EFFORT + BUFFER )
TEST TASKS
TASK ID | TASK DESCRIPTION | ESTIMATED EFFORT in Hours | RESOURCE ASSIGNED | START DATE | END DATE
TOTAL TEST TASKS ESTIMATED EFFORT |  | 0
TEST PHASES
TEST PHASE |  | ESTIMATED EFFORT in Hours
Test Planning
Test Design
Test Execution
Defect Management
Test Reporting
TOTAL TEST PHASES ESTIMATED EFFORT |  | 0
ASSUMPTIONS
1
2
RISKS
1
2

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.