## EXAMPLE – Agile Test Strategy
Agile Test Strategy Template – Example
TITLE
Agile Test Strategy for Positive Charge Software Project
Agile Test Strategy for Project Name
VERSION | DATE |  | PREPARED BY
1.0 | Thursday, July 17, 20XX |  | Alexandra Mattson
Introduction
Overview | Brief description of the project
This document outlines the Agile test strategy for Positive Charge's software project, which aims to enhance our EV-charging and logistics platform. The project focuses on improving user experience, optimizing charging station allocation, and enhancing route planning for electric vehicles.
Purpose | Purpose of the test strategy document
The purpose of this test strategy document is to define the testing approach, deliverables, and schedule to ensure the quality and reliability of the new software features.
Scope
In-Scope Items | Components and features to be tested
- EV-charging station locator - Real-time charging station availability updates - Enhanced route planning with charging stops - User account management features - Payment gateway integration
Out-of-Scope Items | Items not covered by this strategy
- Legacy systems integration - Third-party API enhancements
Testing Approach
Types of Testing | Functional, non-functional, regression, etc.
- Functional testing - Non-functional testing (performance, security) - Regression testing - User Acceptance Testing (UAT)
Agile Methodology | Specific Agile practices like sprints, stand-ups
- Sprints: Bi-weekly sprint cycles - Daily stand-up meetings: 15-minute meetings every morning - Sprint reviews and retrospectives: At the end of each sprint
Test Levels | Unit, integration, system, acceptance
- Unit testing - Integration testing - System testing - Acceptance testing
Test Deliverables
List of documents and reports to be delivered
- Test plan document - Test cases and test scripts - Test summary reports - Defect reports - UAT sign-off document
Test Environment
Setup | Description of the test environment
A dedicated test environment that replicates the production setup, including staging servers, databases, and network configurations.
Requirements | Hardware and software specifications
- Hardware: Standard servers, load balancers - Software: Latest versions of web servers, database systems, and necessary middleware
Tools and Automation
Testing Tools | Tools to be used, e.g., Selenium, JIRA
- Selenium for automation testing - JIRA for issue tracking and test management - Postman for API testing
Automation Strategy | Approach to test automation
- Automate regression test cases - Continuous Integration (CI) setup with Jenkins for automated test execution
Test Data Management
Data Approach | Management of test data
Use anonymized production data for realistic test scenarios. Create synthetic data where necessary.
Privacy and Security | Considerations for data privacy
Ensure test data complies with data privacy regulations and is securely managed.
Defect Management
Reporting Process | Defect reporting and tracking process
Defects are logged in JIRA and prioritized based on severity and impact. Regular triage meetings to review and assign defects.
Tools | Tools used for defect management
JIRA for defect tracking
Roles and Responsibilities
List of roles in the testing team and responsibilities of each role
ROLE | RESPONSIBILITIES
Test Manager | Oversee the testing process. Ensure testing coverage and timelines.
Test Engineers | Design and execute test cases. Write and execute test cases, log defects.
Automation Engineers | Develop and maintain automated tests. Implement automation scripts.
Product Owner | Provide requirements and accept deliverables. Validate the functionality meets requirements.
Schedule
Timeline | Timeline for testing activities
ACTIVITIES |  |  | DATE
Sprint 1 |  |  | July 15 - July 28
Sprint 2 |  |  | July 29 - August 11
Sprint 3 |  |  | August 12 - August 25
Milestones | Key milestones and deadlines
KEY MILESTONE |  |  |  | DATE
Sprint planning |  |  |  | July 14
First sprint review |  |  |  | July 28
Final UAT |  |  |  | August 25
Risks and Mitigation
POTENTIAL RISKS |  | MITIGATION STRATEGIES
Delays in test environment setup |  | Set up and validate the test environment
Unavailability of test data |  | Ensure data availability before testing begins
High defect rate in critical features |  | Prioritize and address critical defects promptly
Communication Plan
Channels
Slack for daily communication, email for formal updates, Confluence for documentation
Frequency
Daily stand-ups, weekly status reports
Stakeholders
Product Owner, Development team, QA team, project manager
Exit Criteria
Criteria for concluding the testing phase and metrics for success
CRITERIA |  | SUCCESS METRICS
All test cases executed with a pass rate of 95% |  | Defect density
No critical defects open |  | Test coverage
UAT sign-off obtained |  | User satisfaction
Conclusion
Summary and next steps
This Agile test strategy provides a structured approach to ensure the quality of Positive Charge's software enhancements. Next steps include executing the defined test cases, monitoring progress, and addressing any issues that arise during the testing phases.
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK – Agile Test Strategy
Agile Test Strategy Template
TITLE
Agile Test Strategy for Project Name
VERSION | DATE |  | PREPARED BY
Introduction
Overview | Brief description of the project
Purpose | Purpose of the test strategy document
Scope
In-Scope Items | Components and features to be tested
Out-of-Scope Items | Items not covered by this strategy
Testing Approach
Types of Testing | Functional, non-functional, regression, etc.
Agile Methodology | Specific Agile practices like sprints, stand-ups
Test Levels | Unit, integration, system, acceptance
Test Deliverables
List of documents and reports to be delivered
Test Environment
Setup | Description of the test environment
Requirements | Hardware and software specifications
Tools and Automation
Testing Tools | Tools to be used, e.g., Selenium, JIRA
Automation Strategy | Approach to test automation
Test Data Management
Data Approach | Management of test data
Privacy and Security | Considerations for data privacy
Defect Management
Reporting Process | Defect reporting and tracking process
Tools | Tools used for defect management
Roles and Responsibilities
List of roles in the testing team and responsibilities of each role
ROLE | RESPONSIBILITIES
Schedule
Timeline | Timeline for testing activities
ACTIVITIES |  |  | DATE
Milestones | Key milestones and deadlines
KEY MILESTONE |  |  |  | DATE
Risks and Mitigation
POTENTIAL RISKS |  | MITIGATION STRATEGIES
Communication Plan
Channels
Frequency
Stakeholders
Exit Criteria
Criteria for concluding the testing phase and metrics for success
CRITERIA |  | SUCCESS METRICS
Conclusion
Summary and next steps

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.