## EXAMPLE - Agile Test Report
Agile Test Summary Report Template – Example
User to enter Defect Tracking and Text Execution information in the data tables below. Dashboard data, charts, and graphs will populate automatically.
TITLE |  |  |  | TOTAL DEFECTS
EV Charging System Testing Report |  |  |  | 25
PROJECT NAME |  |  |  | TOTAL TESTS
Positive Charge EV Charging System |  |  |  | 150
–––––––– TESTING PERIOD ––––––––
REPORT PREPARED BY |  | REPORT DATE | START DATE | END DATE
Mateus Tobin |  | 07/15/20XX | 06/01/20XX | 07/14/20XX
TEST OBJECTIVES Brief description of the testing goals
Ensure the EV charging system operates reliably and efficiently, verify user interface functionality, initiate charging session, and ensure backend data processing.
KEY FINDINGS Summary of major issues and observations
– There are some issues with charging session initiation. – Some users experience login failures.
RECOMMENDATIONS Suggestions for improvement
– Investigate and resolve the charging session initiation issue. – Enhance the user authentication process.
CONCLUSION Overall assessment and next steps
Overall, the system performs well, and critical issues have been identified for resolution. Next steps include addressing the defects and re–testing.
Dashboard Data
DEFECT SUMMARY |  |  | TEST EXECUTION SUMMARY
TOTAL No. of DEFECTS | 25 |  | TOTAL No. of TESTS | 150
Open | 3 |  | PASSED | 109
In Progress | 5 |  | FAILED | 21
Closed | 17 |  | Blocked | 15
Minor | 14 |  | Not Executed | 5
Major | 7
Critical | 4
Defect Tracking Data
Defect ID | DATE DETECTED | DESCRIPTION | DATA POINT 2 | DATA POINT 3 | DEFECT STATUS | DEFECT SEVERITY | OWNER | REMARKS
DEF001 | 00/00/0000 |  |  |  | Closed | Minor
DEF002 | 00/00/0000 |  |  |  | In Progress | Major
DEF003 | 00/00/0000 |  |  |  | Open | Critical
DEF004 | 00/00/0000 |  |  |  | In Progress | Critical
DEF005 | 00/00/0000 |  |  |  | Closed | Critical
DEF006 | 00/00/0000 |  |  |  | Closed | Critical
DEF007 | 00/00/0000 |  |  |  | Closed | Minor
DEF008 | 00/00/0000 |  |  |  | Closed | Minor
DEF009 | 00/00/0000 |  |  |  | Closed | Minor
DEF010 | 00/00/0000 |  |  |  | Closed | Minor
DEF011 | 00/00/0000 |  |  |  | In Progress | Minor
DEF012 | 00/00/0000 |  |  |  | In Progress | Minor
DEF013 | 00/00/0000 |  |  |  | In Progress | Minor
DEF014 | 00/00/0000 |  |  |  | Open | Minor
DEF015 | 00/00/0000 |  |  |  | Open | Minor
DEF016 | 00/00/0000 |  |  |  | Closed | Minor
DEF017 | 00/00/0000 |  |  |  | Closed | Minor
DEF018 | 00/00/0000 |  |  |  | Closed | Minor
DEF019 | 00/00/0000 |  |  |  | Closed | Minor
DEF020 | 00/00/0000 |  |  |  | Closed | Major
DEF021 | 00/00/0000 |  |  |  | Closed | Major
DEF022 | 00/00/0000 |  |  |  | Closed | Major
DEF023 | 00/00/0000 |  |  |  | Closed | Major
DEF024 | 00/00/0000 |  |  |  | Closed | Major
DEF025 | 00/00/0000 |  |  |  | Closed | Major
Test Execution Data
Test Case ID | DATE | DESCRIPTION | TEST STEPS | EXPECTED RESULT | ACTUAL RESULT | EXECUTION STATUS | TESTED BY | REMARKS
TC001 | 00/00/0000 | Verify user login functionality. |  |  |  | PASSED |  | None
TC002 | 00/00/0000 | Verify initiation of charging session. |  |  |  | FAILED |  | Charging session does not start for some users.
TC003 | 00/00/0000 |  |  |  |  | Blocked
TC004 | 00/00/0000 |  |  |  |  | Not Executed
TC005 | 00/00/0000 |  |  |  |  | PASSED
TC006 | 00/00/0000 |  |  |  |  | PASSED
TC007 | 00/00/0000 |  |  |  |  | PASSED
TC008 | 00/00/0000 |  |  |  |  | PASSED
TC009 | 00/00/0000 |  |  |  |  | PASSED
TC010 | 00/00/0000 |  |  |  |  | PASSED
TC011 | 00/00/0000 |  |  |  |  | PASSED
TC012 | 00/00/0000 |  |  |  |  | FAILED
TC013 | 00/00/0000 |  |  |  |  | FAILED
TC014 | 00/00/0000 |  |  |  |  | FAILED
TC015 | 00/00/0000 |  |  |  |  | FAILED
TC016 | 00/00/0000 |  |  |  |  | FAILED
TC017 | 00/00/0000 |  |  |  |  | FAILED
TC018 | 00/00/0000 |  |  |  |  | FAILED
TC019 | 00/00/0000 |  |  |  |  | FAILED
TC020 | 00/00/0000 |  |  |  |  | FAILED
TC021 | 00/00/0000 |  |  |  |  | FAILED
TC022 | 00/00/0000 |  |  |  |  | FAILED
TC023 | 00/00/0000 |  |  |  |  | FAILED
TC024 | 00/00/0000 |  |  |  |  | Blocked
TC025 | 00/00/0000 |  |  |  |  | Blocked
TC026 | 00/00/0000 |  |  |  |  | Blocked
TC027 | 00/00/0000 |  |  |  |  | Blocked
TC028 | 00/00/0000 |  |  |  |  | Blocked
TC029 | 00/00/0000 |  |  |  |  | Blocked
TC030 | 00/00/0000 |  |  |  |  | Blocked
TC031 | 00/00/0000 |  |  |  |  | Blocked
TC032 | 00/00/0000 |  |  |  |  | Blocked
TC033 | 00/00/0000 |  |  |  |  | Blocked
TC034 | 00/00/0000 |  |  |  |  | Blocked
TC035 | 00/00/0000 |  |  |  |  | Blocked
TC036 | 00/00/0000 |  |  |  |  | Blocked
TC037 | 00/00/0000 |  |  |  |  | Blocked
TC038 | 00/00/0000 |  |  |  |  | Not Executed
TC039 | 00/00/0000 |  |  |  |  | Not Executed
TC040 | 00/00/0000 |  |  |  |  | Not Executed
TC041 | 00/00/0000 |  |  |  |  | Not Executed
TC042 | 00/00/0000 |  |  |  |  | FAILED
TC043 | 00/00/0000 |  |  |  |  | FAILED
TC044 | 00/00/0000 |  |  |  |  | FAILED
TC045 | 00/00/0000 |  |  |  |  | FAILED
TC046 | 00/00/0000 |  |  |  |  | FAILED
TC047 | 00/00/0000 |  |  |  |  | FAILED
TC048 | 00/00/0000 |  |  |  |  | FAILED
TC049 | 00/00/0000 |  |  |  |  | FAILED
TC050 | 00/00/0000 |  |  |  |  | PASSED
TC051 | 00/00/0000 |  |  |  |  | PASSED
TC052 | 00/00/0000 |  |  |  |  | PASSED
TC053 | 00/00/0000 |  |  |  |  | PASSED
TC054 | 00/00/0000 |  |  |  |  | PASSED
TC055 | 00/00/0000 |  |  |  |  | PASSED
TC056 | 00/00/0000 |  |  |  |  | PASSED
TC057 | 00/00/0000 |  |  |  |  | PASSED
TC058 | 00/00/0000 |  |  |  |  | PASSED
TC059 | 00/00/0000 |  |  |  |  | PASSED
TC060 | 00/00/0000 |  |  |  |  | PASSED
TC061 | 00/00/0000 |  |  |  |  | PASSED
TC062 | 00/00/0000 |  |  |  |  | PASSED
TC063 | 00/00/0000 |  |  |  |  | PASSED
TC064 | 00/00/0000 |  |  |  |  | PASSED
TC065 | 00/00/0000 |  |  |  |  | PASSED
TC066 | 00/00/0000 |  |  |  |  | PASSED
TC067 | 00/00/0000 |  |  |  |  | PASSED
TC068 | 00/00/0000 |  |  |  |  | PASSED
TC069 | 00/00/0000 |  |  |  |  | PASSED
TC070 | 00/00/0000 |  |  |  |  | PASSED
TC071 | 00/00/0000 |  |  |  |  | PASSED
TC072 | 00/00/0000 |  |  |  |  | PASSED
TC073 | 00/00/0000 |  |  |  |  | PASSED
TC074 | 00/00/0000 |  |  |  |  | PASSED
TC075 | 00/00/0000 |  |  |  |  | PASSED
TC076 | 00/00/0000 |  |  |  |  | PASSED
TC077 | 00/00/0000 |  |  |  |  | PASSED
TC078 | 00/00/0000 |  |  |  |  | PASSED
TC079 | 00/00/0000 |  |  |  |  | PASSED
TC080 | 00/00/0000 |  |  |  |  | PASSED
TC081 | 00/00/0000 |  |  |  |  | PASSED
TC082 | 00/00/0000 |  |  |  |  | PASSED
TC083 | 00/00/0000 |  |  |  |  | PASSED
TC084 | 00/00/0000 |  |  |  |  | PASSED
TC085 | 00/00/0000 |  |  |  |  | PASSED
TC086 | 00/00/0000 |  |  |  |  | PASSED
TC087 | 00/00/0000 |  |  |  |  | PASSED
TC088 | 00/00/0000 |  |  |  |  | PASSED
TC089 | 00/00/0000 |  |  |  |  | PASSED
TC090 | 00/00/0000 |  |  |  |  | PASSED
TC091 | 00/00/0000 |  |  |  |  | PASSED
TC092 | 00/00/0000 |  |  |  |  | PASSED
TC093 | 00/00/0000 |  |  |  |  | PASSED
TC094 | 00/00/0000 |  |  |  |  | PASSED
TC095 | 00/00/0000 |  |  |  |  | PASSED
TC096 | 00/00/0000 |  |  |  |  | PASSED
TC097 | 00/00/0000 |  |  |  |  | PASSED
TC098 | 00/00/0000 |  |  |  |  | PASSED
TC099 | 00/00/0000 |  |  |  |  | PASSED
TC100 | 00/00/0000 |  |  |  |  | PASSED
TC101 | 00/00/0000 |  |  |  |  | PASSED
TC102 | 00/00/0000 |  |  |  |  | PASSED
TC103 | 00/00/0000 |  |  |  |  | PASSED
TC104 | 00/00/0000 |  |  |  |  | PASSED
TC105 | 00/00/0000 |  |  |  |  | PASSED
TC106 | 00/00/0000 |  |  |  |  | PASSED
TC107 | 00/00/0000 |  |  |  |  | PASSED
TC108 | 00/00/0000 |  |  |  |  | PASSED
TC109 | 00/00/0000 |  |  |  |  | PASSED
TC110 | 00/00/0000 |  |  |  |  | PASSED
TC111 | 00/00/0000 |  |  |  |  | PASSED
TC112 | 00/00/0000 |  |  |  |  | PASSED
TC113 | 00/00/0000 |  |  |  |  | PASSED
TC114 | 00/00/0000 |  |  |  |  | PASSED
TC115 | 00/00/0000 |  |  |  |  | PASSED
TC116 | 00/00/0000 |  |  |  |  | PASSED
TC117 | 00/00/0000 |  |  |  |  | PASSED
TC118 | 00/00/0000 |  |  |  |  | PASSED
TC119 | 00/00/0000 |  |  |  |  | PASSED
TC120 | 00/00/0000 |  |  |  |  | PASSED
TC121 | 00/00/0000 |  |  |  |  | PASSED
TC122 | 00/00/0000 |  |  |  |  | PASSED
TC123 | 00/00/0000 |  |  |  |  | PASSED
TC124 | 00/00/0000 |  |  |  |  | PASSED
TC125 | 00/00/0000 |  |  |  |  | PASSED
TC126 | 00/00/0000 |  |  |  |  | PASSED
TC127 | 00/00/0000 |  |  |  |  | PASSED
TC128 | 00/00/0000 |  |  |  |  | PASSED
TC129 | 00/00/0000 |  |  |  |  | PASSED
TC130 | 00/00/0000 |  |  |  |  | PASSED
TC131 | 00/00/0000 |  |  |  |  | PASSED
TC132 | 00/00/0000 |  |  |  |  | PASSED
TC133 | 00/00/0000 |  |  |  |  | PASSED
TC134 | 00/00/0000 |  |  |  |  | PASSED
TC135 | 00/00/0000 |  |  |  |  | PASSED
TC136 | 00/00/0000 |  |  |  |  | PASSED
TC137 | 00/00/0000 |  |  |  |  | PASSED
TC138 | 00/00/0000 |  |  |  |  | PASSED
TC139 | 00/00/0000 |  |  |  |  | PASSED
TC140 | 00/00/0000 |  |  |  |  | PASSED
TC141 | 00/00/0000 |  |  |  |  | PASSED
TC142 | 00/00/0000 |  |  |  |  | PASSED
TC143 | 00/00/0000 |  |  |  |  | PASSED
TC144 | 00/00/0000 |  |  |  |  | PASSED
TC145 | 00/00/0000 |  |  |  |  | PASSED
TC146 | 00/00/0000 |  |  |  |  | PASSED
TC147 | 00/00/0000 |  |  |  |  | PASSED
TC148 | 00/00/0000 |  |  |  |  | PASSED
TC149 | 00/00/0000 |  |  |  |  | PASSED
TC150 | 00/00/0000 |  |  |  |  | PASSED
CLICK HERE TO CREATE IN SMARTSHEET
Defect Density
Defect Distribution
Test Execution Status

## BLANK - Agile Test Report
Agile Test Summary Report Template
User to enter Defect Tracking and Text Execution information in the data tables below. Dashboard data, charts, and graphs will populate automatically.
TITLE |  |  |  | TOTAL DEFECTS
0
PROJECT NAME |  |  |  | TOTAL TESTS
0
–––––––– TESTING PERIOD ––––––––
REPORT PREPARED BY |  | REPORT DATE | START DATE | END DATE
TEST OBJECTIVES Brief description of the testing goals
KEY FINDINGS Summary of major issues and observations
RECOMMENDATIONS Suggestions for improvement
CONCLUSION Overall assessment and next steps
Dashboard Data
DEFECT SUMMARY |  |  | TEST EXECUTION SUMMARY
TOTAL No. of DEFECTS | 0 |  | TOTAL No. of TESTS | 0
Open | 0 |  | PASSED | 0
In Progress | 0 |  | FAILED | 0
Closed | 0 |  | Blocked | 0
Minor | 0 |  | Not Executed | 0
Major | 0
Critical | 0
Defect Tracking Data
Defect ID | DATE DETECTED | DESCRIPTION | DATA POINT 2 | DATA POINT 3 | DEFECT STATUS | DEFECT SEVERITY | OWNER | REMARKS
Test Execution Data
Test Case ID | DATE | DESCRIPTION | TEST STEPS | EXPECTED RESULT | ACTUAL RESULT | EXECUTION STATUS | TESTED BY | REMARKS
Defect Density
Defect Distribution
Test Execution Status

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
EXECUTION STATUS | IMPACT SEVERITY | DEFECT SEVERITY | DEFECT STATUS | IMPLEMENTATION STATUS | TEST CASE STATUS
PASSED | N/A | Minor | Open | Planned | Not Started
FAILED | Low | Major | In Progress | Implemented | In Progress
Blocked | Medium | Critical | Closed | Attempted | Complete
Not Executed | High |  |  |  | Needs Review
| Critical |  |  |  | Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.