## EXAMPLE – Agile UAT
Agile User Acceptance Testing (UAT) Test Plan – Example
1. Introduction
Purpose | Describe the purpose of the UAT.
The purpose of this User Acceptance Testing (UAT) plan is to validate that the Positive Charge EV-charging logistics software meets the business requirements and is ready for production deployment.
Scope | Define the scope of the UAT, including features and functionalities to be tested.
This UAT will focus on the end-to-end functionalities of the EV-charging station management, user account management, and real-time logistics tracking features.
Objectives | Outline the objectives of the UAT, such as validating end-to-end business processes.
– Validate the seamless integration of the charging stations with the software. – Ensure that user accounts can be created, managed, and accessed correctly. – Confirm that real-time logistics tracking is accurate and reliable.
2. Background
Project Overview | Provide a brief overview of the project.
Positive Charge is developing a software solution to manage EV-charging stations and streamline logistics operations for electric vehicles. This UAT will ensure the solution is ready for our pilot launch.
Key Stakeholders | List key stakeholders involved in the UAT process.
TITLE |  | NAME | CONTACT
Project Manager |  | Brooklyn Jansen
Product Owner |  | Hazel Christensen
Development Team Lead |  | Makara McLean
UAT Lead |  | Romy Bailey
3. UAT Approach
Test Strategy | Explain the overall testing strategy, including the types of testing to be performed.
We will use a combination of manual and automated testing. The UAT will focus on functional testing, usability testing, and performance testing.
Test Levels | Detail the levels of testing (e.g., system testing, integration testing).
– System testing: Validate the entire system's functionality. – Integration testing: Ensure all components integrate seamlessly.
Entry and Exit Criteria |  | Define the criteria for starting and ending the UAT.
Entry Criteria | All unit and integration tests must be passed. UAT environment must be set up.
Exit Criteria | All critical defects must be resolved. Stakeholders must sign off.
4. UAT Scope
In-Scope Items | List the functionalities and features included in the UAT.
– User account creation, login, and management – EV-charging station status monitoring and management – Real-time logistics tracking and reporting
Out-of-Scope Items |  | Mention any functionalities and features that are excluded from the UAT.
– Future enhancements and additional features planned for post-launch
5. UAT Environment
Test Environment | Describe the test environment, including hardware, software, and network configurations.
– Servers configured with the latest build – Charging stations connected and operational – Network settings to simulate real-world usage
Data Requirements |  | Specify the test data needed for UAT.
– Test user accounts with different roles (admin, user) – Simulated charging station data – Real-time logistics data samples
6. UAT Schedule
Timeline | Provide a detailed timeline for UAT activities, including start and end dates.
ACTIVITIES |  |  |  | START DATE | END DATE
User Acceptance Testing (UAT) |  |  |  | 08/01/20XX | 08/14/20XX
Milestones | Highlight key milestones in the UAT process.
KEY MILESTONE |  |  |  |  | END DATE
Test plan review |  |  |  |  | 07/25/20XX
Initial testing completion |  |  |  |  | 08/07/20XX
Defect resolution |  |  |  |  | 08/10/20XX
Final review and sign-off |  |  |  |  | 08/14/20XX
7. UAT Roles and Responsibilities
List the UAT team members and their roles. Define the responsibilities of each team member.
ROLE | TEAM MEMBER | RESPONSIBILITIES
UAT Lead | Romy Bailey | Coordinate UAT activities and report progress.
Testers | Brian Gorman Diana Kennedy | Execute test cases and report defects.
Business Analysts | Henry McNeal Jamal King | Validate requirements and assist in test case creation.
8. UAT Test Scenarios and Test Cases
Test Scenario ID | Unique identifier for each test scenario | UAT_TS_001
Title | Brief title of the test scenario | User Account Creation
Description | Detailed description of the test scenario | Verify that new user accounts can be created successfully.
Test Steps | Step-by-step instructions to execute the test | 1. Navigate to the registration page. 2. Enter valid user information. 3. Click Submit.
Expected Results | Expected outcome for each step | – User receives a confirmation email. – Account is created and user can log in.
Test Data | Specific data required for the test scenario | – Username: testuser@example.com – Password: TestPassword123
9. UAT Defect Management
Defect Reporting | Note the process for reporting defects.
Defects will be reported using Jira.
Defect Tracking | Define the method for tracking and managing defects.
All defects will be tracked in Jira with regular updates.
Defect Resolution | List the steps for defect resolution and retesting.
Development team will address defects based on priority.
10. UAT Tools
Testing Tools | List the tools used for UAT (e.g., test management, defect tracking).
– Jira for defect tracking – Selenium for automated testing – Postman for API testing
Tool Configuration | List the configuration details for the tools.
Ensure all tools are configured and accessible to the UAT team.
11. UAT Acceptance Criteria
Success Criteria | List the criteria for accepting the UAT results.
– All test cases executed with no critical defects remaining – Stakeholders approve the UAT results
Failure Criteria | List the criteria for rejecting the UAT results.
– Critical defects remain unresolved – Key functionalities fail to meet business requirements
12. UAT Sign-off
Approval Process | Note the process for obtaining UAT sign-off from stakeholders.
UAT results will be reviewed in a meeting with stakeholders. Final approval will be documented.
Sign-off Sheet | Document how stakeholders will sign off on UAT completion.
A sign-off sheet will be circulated to stakeholders for signatures upon completion.
13. UAT Risks and Mitigations
POTENTIAL RISKS |  |  | MITIGATION STRATEGIES
Delays in defect resolution |  |  | Regular status meetings to track progress
Incomplete test data |  |  | Backup plans for data preparation
14. Appendices
Glossary | Define any terms used in the UAT Test Plan.
– UAT: User Acceptance Testing – Jira: A tool used for issue tracking and project management.
References | List the documents and resources referenced in the UAT Test Plan.
– UAT Test Plan Template Document v1.0 – Project Requirement Specifications
Additional Information |  | Note any other relevant information.
– Contact Information for UAT Support: support@positivecharge.com
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK – Agile UAT
Agile User Acceptance Testing (UAT) Test Plan Template
1. Introduction
Purpose | Describe the purpose of the UAT.
Scope | Define the scope of the UAT, including features and functionalities to be tested.
Objectives | Outline the objectives of the UAT, such as validating end-to-end business processes.
2. Background
Project Overview | Provide a brief overview of the project.
Key Stakeholders | List key stakeholders involved in the UAT process.
TITLE |  | NAME | CONTACT
3. UAT Approach
Test Strategy | Explain the overall testing strategy, including the types of testing to be performed.
Test Levels | Detail the levels of testing (e.g., system testing, integration testing).
Entry and Exit Criteria |  | Define the criteria for starting and ending the UAT.
Entry Criteria
Exit Criteria
4. UAT Scope
In-Scope Items | List the functionalities and features included in the UAT.
Out-of-Scope Items |  | Mention any functionalities and features that are excluded from the UAT.
5. UAT Environment
Test Environment | Describe the test environment, including hardware, software, and network configurations.
Data Requirements |  | Specify the test data needed for UAT.
6. UAT Schedule
Timeline | Provide a detailed timeline for UAT activities, including start and end dates.
ACTIVITIES |  |  |  | START DATE | END DATE
Milestones | Highlight key milestones in the UAT process.
KEY MILESTONE |  |  |  |  | END DATE
7. UAT Roles and Responsibilities
List the UAT team members and their roles. Define the responsibilities of each team member.
ROLE | TEAM MEMBER | RESPONSIBILITIES
8. UAT Test Scenarios and Test Cases
Test Scenario ID | Unique identifier for each test scenario
Title | Brief title of the test scenario
Description | Detailed description of the test scenario
Test Steps | Step-by-step instructions to execute the test
Expected Results | Expected outcome for each step
Test Data | Specific data required for the test scenario
9. UAT Defect Management
Defect Reporting | Note the process for reporting defects.
Defect Tracking | Define the method for tracking and managing defects.
Defect Resolution | List the steps for defect resolution and retesting.
10. UAT Tools
Testing Tools | List the tools used for UAT (e.g., test management, defect tracking).
Tool Configuration | List the configuration details for the tools.
11. UAT Acceptance Criteria
Success Criteria | List the criteria for accepting the UAT results.
Failure Criteria | List the criteria for rejecting the UAT results.
12. UAT Sign-off
Approval Process | Note the process for obtaining UAT sign-off from stakeholders.
Sign-off Sheet | Document how stakeholders will sign off on UAT completion.
13. UAT Risks and Mitigations
POTENTIAL RISKS |  |  | MITIGATION STRATEGIES
14. Appendices
Glossary | Define any terms used in the UAT Test Plan.
References | List the documents and resources referenced in the UAT Test Plan.
Additional Information |  | Note any other relevant information.

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.