## Agile Production Scheduling
Agile Production Scheduling Template
Sprint Planning and Backlog Management
Sprint Iteration Goals | Sprint 1 | Goals | [6 empty] | Sprints | Sprint 1
| Sprint 2 | Goals | [7 empty] | Sprint 2
| Sprint 3 | Goals | [7 empty] | Sprint 3
| Sprint 4 | Goals | [7 empty] | Sprint 4
| Sprint 5 | Goals | [7 empty] | Sprint 5
Work Breakdown Structure | Tasks | Owner | Work in Hours |  |  | Sprint | Start Date | Due Date | Duration | Percent Complete | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | Estimate | Completed | Remaining | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation |  | 309 | 309 | 0 |  |  |  |  | 100%
1.1 | Project Charter | Jenna P | 40 | 40 | 0 |  | 2030-03-12 | 2030-03-15 | 4 | 100% | bar: WEEK 1 F to WEEK 2 F
1.1.1 | Project Charter Revisions | Kylie R | 25 | 25 | 0 |  | 2030-03-15 | 2030-03-16 | 2 | 100%
1.2 | Research | Pete S | 100 | 100 | 0 |  | 2030-03-15 | 2030-03-21 | 7 | 100% | bar: WEEK 2 M to WEEK 3 R
1.3 | Projections | Steve L | 60 | 60 | 0 |  | 2030-03-16 | 2030-03-22 | 7 | 100% | bar: WEEK 2 M to WEEK 3 R
1.4 | Stakeholders | Allen W | 40 | 40 | 0 |  | 2030-03-17 | 2030-03-22 | 6 | 100% | bar: WEEK 2 M to WEEK 3 R
1.5 | Guidelines | Malik M | 32 | 32 | 0 |  | 2030-03-18 | 2030-03-22 | 5 | 100% | bar: WEEK 2 M to WEEK 3 R
1.6 | Project Initiation | Malik M | 12 | 12 | 0 |  | 2030-03-23 | 2030-03-23 | 1 | 100% | bar: WEEK 3 F
2 | Project Definition and Planning |  | 210 | 110 | 100 |  |  |  |  | 52.38%
2.1 | Scope & Goal Setting | Steve L | 80 | 70 | 10 |  | 2030-03-24 | 2030-03-28 | 5 | 87.5% | bar: WEEK 4 M to WEEK 5 F
2.2 | Budget | Allen W | 60 | 40 | 20 |  | 2030-03-29 | 2030-04-02 | 5 | 66.67%
2.3 | Communication Plan | Malik M | 40 | 0 | 40 |  |  |  | 1 | 0%
2.4 | Risk Management | Malik M | 30 | 0 | 30 |  |  |  | 1 | 0%
3 | Project Launch and Execution |  | 66 | 0 | 66 |  |  |  |  | 0%
3.1 | Status & Tracking | Pete S | 20 | 0 | 20 |  |  |  | 1 | 0%
3.2 | KPIs | Jenna P | 20 | 0 | 20 |  |  |  | 1 | 0%
3.2.1 | Monitoring | Kylie R | 8 | 0 | 8 |  |  |  | 1 | 0%
3.2.2 | Forecasts | Kylie R | 12 | 0 | 12 |  |  |  | 1 | 0%
3.3 | Project Updates | Pete S | 4 | 0 | 4 |  |  |  | 1 | 0%
3.3.1 | Chart Updates | Malik M | 2 | 0 | 2 |  |  |  | 1 | 0%
4 | Project Performance / Monitoring |  | 32 | 0 | 32 |  |  |  |  | 0%
4.1 | Project Objectives | Steve L | 8 | 0 | 8 |  |  |  | 1 | 0%
4.2 | Quality Deliverables | Allen W | 12 | 0 | 12 |  |  |  | 1 | 0%
4.3 | Effort and Cost Tracking | Malik M | 8 | 0 | 8 |  |  |  | 1 | 0%
4.4 | Project Performance | Malik M | 4 | 0 | 4 |  |  |  | 1 | 0%
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/ DAYS
| BURNDOWN DATA | TOTAL HOURS | 617 | 419 | 198 | 60 | 10.2833 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | TOTAL
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 617 | 606.7167 | 596.4333 | 586.15 | 575.8667 | 565.5833 | 555.3 | 545.0167 | 534.7333 | 524.45 | 514.1667 | 503.8833 | 493.6 | 483.3167 | 473.0333 | 462.75 | 452.4667 | 442.1833 | 431.9 | 421.6167 | 411.3333 | 401.05 | 390.7667 | 380.4833 | 370.2 | 359.9167 | 349.6333 | 339.35 | 329.0667 | 318.7833 | 308.5 | 298.2167 | 287.9333 | 277.65 | 267.3667 | 257.0833 | 246.8 | 236.5167 | 226.2333 | 215.95 | 205.6667 | 195.3833 | 185.1 | 174.8167 | 164.5333 | 154.25 | 143.9667 | 133.6833 | 123.4 | 113.1167 | 102.8333 | 92.55 | 82.2667 | 71.9833 | 61.7 | 51.4167 | 41.1333 | 30.85 | 20.5667 | 10.2833 | HOURS
[10 empty] | ESTIMATE | 617 | 609 | 589 | 559 | 519 | 499 | 488 | 472 | 430 | 385 | 365 | 355 | 339 | 315 | 267 | 247 | 243 | 238 | 234 | 226 | 218 | 213 | 208 | 203 | 200 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 15968
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | WEEK 1 M: 8; WEEK 1 T: 20; WEEK 1 W: 30; WEEK 1 R: 40; WEEK 1 F: 20; WEEK 2 M: 11; WEEK 2 T: 16; WEEK 2 W: 42; WEEK 2 R: 45; WEEK 2 F: 20; WEEK 3 M: 10; WEEK 3 T: 16; WEEK 3 W: 24; WEEK 3 R: 48; WEEK 3 F: 20; WEEK 4 M: 4; WEEK 4 T: 5; WEEK 4 W: 4; WEEK 4 R: 8; WEEK 4 F: 8; WEEK 5 M: 5; WEEK 5 T: 5; WEEK 5 W: 5; WEEK 5 R: 3; WEEK 5 F: 2 | 419
[10 empty] | HRS REMAINING | 609 | 589 | 559 | 519 | 499 | 488 | 472 | 430 | 385 | 365 | 355 | 339 | 315 | 267 | 247 | 243 | 238 | 234 | 226 | 218 | 213 | 208 | 203 | 200 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 198 | 15549
BURNDOWN CHART
Retrospective Notes and Feedback Loop
CLICK HERE TO CREATE IN SMARTSHEET

## Backlog
Backlog
Priority | Sprint | Functionality | Task | Description | Owner | Work Estimate in Hours | Status | Notes
High | [5 empty] | 1 | TO DO
Medium | [5 empty] | 2 | IN PROGRESS
Low | [5 empty] | 4 | DONE
[6 empty] | 8 | BLOCKED
[6 empty] | 16 | REVIEW
8
24
40
40
80
8
8
8
8
8
8
8
8
8
8
8
8
8
8
8
8
8
8
8
8
8
8
8
8
8
8
8

## Kanban and Stand-Up Notes
Kanban Board | Copy and paste Kanban cards to the Kanban Board below. |  |  |  | Stand-Up Notes
To Do | In Progress | Done | Blocked | Review | Notes
Details of Task to Be Completed
Status: Note Status Here
POINTS: 0
OWNER: Name
Details of Task to Be Completed
Status: Note Status Here
POINTS: 0
OWNER: Name
Details of Task to Be Completed
Status: Note Status Here
POINTS: 0
OWNER: Name
Details of Task to Be Completed
Status: Note Status Here
POINTS: 0
OWNER: Name
Details of Task to Be Completed
Status: Note Status Here
POINTS: 0
OWNER: Name
Details of Task to Be Completed
Status: Note Status Here
POINTS: 0
OWNER: Name
Details of Task to Be Completed
Status: Note Status Here
POINTS: 0
OWNER: Name
Details of Task to Be Completed
Status: Note Status Here
POINTS: 0
OWNER: Name
Details of Task to Be Completed
Status: Note Status Here
POINTS: 0
OWNER: Name
Details of Task to Be Completed
Status: Note Status Here
POINTS: 0
OWNER: Name
Date: MM/DD/YY
Team Member Name: Name
Current Work: Description
Future Work: Description
Blockers: Description
Date: MM/DD/YY
Team Member Name: Name
Current Work: Description
Future Work: Description
Blockers: Description
Date: MM/DD/YY
Team Member Name: Name
Current Work: Description
Future Work: Description
Blockers: Description
Date: MM/DD/YY
Team Member Name: Name
Current Work: Description
Future Work: Description
Blockers: Description

## Capacity Planning
Capacity Planning
Resource Availability | Requirements | Notes

## Dropdown Keys - DO NOT DELETE
KEY DROPDOWNS - DO NOT DELETE
PRIORITY | STATUS | Work Estimate in Hours
High | IN PROGRESS | 1
Medium | TO DO | 2
Low | DONE | 4
| BLOCKED | 8
| REVIEW | 16
24
40
80

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.