## EXAMPLE - Budget Contingency
Percentage-Based Budget Contingency Template with Construction Example Data
[6 empty] | CONTINGENCY PERCENTAGE |  | TOTAL BUDGET |  | CONTINGENCY BUDGET |  | TOTAL BUDGET with CONTINGENCY
[6 empty] | 10% |  | 42590 |  | 4259 |  | 46849
User to complete non-shaded cells only. | [5 empty] | LABOR |  |  | MATERIALS |  |  | FIXED
TASK | DESCRIPTION | STATUS | PLANNED START DATE | ACTUAL START DATE | END DATE | HR | $/HR | TOTAL LABOR | UNITS | $/UNITS | TOTAL MATERIALS | TRAVEL | EQUIPMENT / SPACE | MISC. | TOTAL
Task | Planning | Complete | 2035-08-01 |  | 2035-08-19 | 90 | 60 | 5400 |  |  | 0 |  |  |  | 5400
Task | Build (off-site) | In Progress | 2035-08-21 |  | 2035-09-04 | 320 | 40 | 12800 | 1 | 8000 | 8000 |  | 1200 |  | 22000
Task | Installation (on-site) | Not Started | 2035-09-09 |  | 2035-09-12 | 96 | 40 | 3840 | 1 | 1500 | 1500 | 2500 | 500 |  | 8340
Task | Breakdown and disposal (on-site) | Not Started | 2035-09-17 |  | 2035-09-19 | 32 | 40 | 1280 | 1 | 500 | 500 | 2500 |  | 650 | 4930
Task | Project close | Not Started | 2035-09-23 |  | 2035-09-26 | 32 | 60 | 1920 |  |  | 0 |  |  |  | 1920
Task | [7 empty] | 0 |  |  | 0 |  |  |  | 0
SUBTOTAL | [7 empty] | 25240 |  |  | 10000 | 5000 | 1700 | 650 | 42590
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Budget Contingency
Percentage-Based Budget Contingency Template
[6 empty] | CONTINGENCY PERCENTAGE |  | TOTAL BUDGET |  | CONTINGENCY BUDGET |  | TOTAL BUDGET with CONTINGENCY
[6 empty] | 5% |  | 0 |  | 0 |  | 0
User to complete non-shaded cells only. | [5 empty] | LABOR |  |  | MATERIALS |  |  | FIXED
TASK | DESCRIPTION | STATUS | PLANNED START DATE | ACTUAL START DATE | END DATE | HR | $/HR | TOTAL LABOR | UNITS | $/UNITS | TOTAL MATERIALS | TRAVEL | EQUIPMENT / SPACE | MISC. | TOTAL
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
[8 empty] | 0 |  |  | 0 |  |  |  | 0
SUBTOTAL | [7 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.