## EXAMPLE Risk Budget Contingency
Risk Assessment Budget Contingency Plan Template with Government Example Data
PROJECT NAME | [5 empty] | LOW-END CONTINGENCY
Repave and New Bike Lane on Grand St | [5 empty] | 133400 |  |  | Total Estimated Costs Priority Levels 10 and higher
PROJECT MANAGER |  |  | DATE |  |  | HIGH-END CONTINGENCY
Fiorella Fitzgerald |  |  | MM/DD/YY |  |  | 153400 |  |  | Total Estimated Costs All Priority Levels
|  | Enter Risk Class titles on the Dropdown Key tab to populate the Risk Register Dropdown Menu. | [5 empty] | DO NOT ALTER SCORE CELLS Outcomes populate automatically.
REF ID | DATE RAISED | RISK CLASS | RISK DESCRIPTION | IMPACT DESCRIPTION | ESTIMATED COST | PROBABILITY 1 – 5 | IMPACT 1 – 16 | PRIORITY LEVEL Prob x Impact | CONTINGENCY PLAN STRATEGY | TRIGGER POINTS | END PLAN TRIGGER | ACTION | OWNER | NOTES
10001 | MM/DD/YY | Category One | Must obtain permits to shut down 6 blocks of the street to traffic during work hours on relatively short notice. | If we cannot shut the street down for the required hours and amount of time, the project schedule will be affected. | 8400 | 3 | 4 | 12 | If we have not obtained permits before the 4 week deadline, spend the money to rush order them. | 4 weeks before project start | When permits are obtained | Rush order permits | Tamika Marshall
10002 | MM/DD/YY | Category Two | Must acquire bike lane signage and concrete barriers before we can paint road lines. | If we do not receive the concrete barriers from the supplier before the paint date, painting and street re-opening will be delayed. | 20000 | 1 | 8 | 8 | If we have not received the concrete barriers for bike lanes, spend contingency on temporary lane markers and printed signage for roadways. | Non-receipt of concrete barriers before new road material is laid | On-time receipt of concrete barriers | Acquire temporary lane markers and signage | Marta Hicks
10003 | MM/DD/YY | Category Five | This road is a main shipping and bus route so if the closed roads are not well marked, there could be damage to the new road material before it cures. | If there is damage to the newly paved road and vehicles, we will have to redo the work and potentially pay for vehicle damage. | 80000 | 3 | 16 | 48 | If there is damage to the new road material, prioritize rescheduling heavy equipment rental to repair the damage as close to schedule as possible. | Damage to new road materials or vehicles | No damage to road or vehicles | Prioritize repair of road ASAP | Tamika Marshall
10004 | MM/DD/YY | Category Seven | Road material requires weather cooperation for proper curing. If the weather is bad, we may have to delay the project. | If the project is delayed due to weather, we will have to put the crews on standby and extend the project schedule. | 45000 | 4 | 4 | 16 | If the weather is bad, retain crews on call or extend their contracts as necessary. | Weather in excess of 100F or rain of more than 1" per day | Weather suitable for road work and road material curing | Retain crews and extend contracts as necessary | Olivia Carter
0
0
0
0
0
0
0
0
0
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Risk Budget Contingency
Risk Assessment Budget Contingency Plan Template
PROJECT NAME | [5 empty] | LOW-END CONTINGENCY
[6 empty] | 0 |  |  | Total Estimated Costs Priority Levels 10 and higher
PROJECT MANAGER |  |  | DATE |  |  | HIGH-END CONTINGENCY
[6 empty] | 0 |  |  | Total Estimated Costs All Priority Levels
|  | Enter Risk Class titles on the Dropdown Key tab to populate the Risk Register Dropdown Menu. | [5 empty] | DO NOT ALTER SCORE CELLS Outcomes populate automatically.
REF ID | DATE RAISED | RISK CLASS | RISK DESCRIPTION | IMPACT DESCRIPTION | ESTIMATED COST | PROBABILITY 1 – 5 | IMPACT 1 – 16 | PRIORITY LEVEL Prob x Impact | CONTINGENCY PLAN STRATEGY | TRIGGER POINTS | END PLAN TRIGGER | ACTION | OWNER | NOTES
0
0
0
0
0
0
0
0
0
0
0
0
0

## Dropdown Keys – DO NOT DELETE –
PROJECT RISK REGISTER – MATRIX
PROBABILITY ¦ 1 – 5 | IMPACT ¦ 1 – 16 | PI SCORES ¦ 1 – 80 |  | 1 | 2 | 3 | 4 | 5
1 - RARE | 1 - INSIGNIFICANT | 1 – 2 • NEGLIGIBLE | 1 | 1 | 2 | 3 | 4 | 5
2 - UNLIKELY | 2 - MINOR | 3 – 8 • LOW | 2 | 2 | 4 | 6 | 8 | 10
3 - POSSIBLE | 4 - MODERATE | 10 – 16 • MEDIUM | 4 | 4 | 8 | 12 | 16 | 20
4 - LIKELY | 8 - MAJOR | 20 – 32 • HIGH | 8 | 8 | 16 | 24 | 32 | 40
5 - ALMOST CERTAIN | 16 - SEVERE | 40 – 80 • EXTREME | 16 | 16 | 32 | 48 | 64 | 80
PROBABILITY KEY | IMPACT KEY
1 | 1
2 | 2
3 | 4
4 | 8
5 | 16
Enter Risk Class titles below to populate the Risk Register Dropdown Menu.
RISK CLASS
Category One
Category Two
Category Three
Category Four
Category Five
Category Six
Category Seven
Category Eight
Category Nine
Category Ten
PROBABILITY
IMPACT

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.