## EXAMPLE Risk Budget Contingency
Risk Assessment Budget Contingency Plan Template with Nonprofit Example Data
PROJECT NAME | [5 empty] | LOW-END CONTINGENCY
Opening a New Permanent Supportive Housing Shelter | [5 empty] | 100000 |  |  | Total Estimated Costs Priority Levels 10 and higher
PROJECT MANAGER |  |  | DATE |  |  | HIGH-END CONTINGENCY
Fiorella Fitzgerald |  |  | MM/DD/YY |  |  | 145000 |  |  | Total Estimated Costs All Priority Levels
|  | Enter Risk Class titles on the Dropdown Key tab to populate the Risk Register Dropdown Menu. | [5 empty] | DO NOT ALTER SCORE CELLS Outcomes populate automatically.
REF ID | DATE RAISED | RISK CLASS | RISK DESCRIPTION | IMPACT DESCRIPTION | ESTIMATED COST | PROBABILITY 1 – 5 | IMPACT 1 – 16 | PRIORITY LEVEL Prob x Impact | CONTINGENCY PLAN STRATEGY | TRIGGER POINTS | END PLAN TRIGGER | ACTION | OWNER | NOTES
10001 | MM/DD/YY | Category One | Renovating the old hotel space may take more budget than initially planned. | If there is mold or asbestos found in the space, renovation costs will increase. | 100000 | 3 | 8 | 24 | If mold or asbestos is found during inspection, prioritize cleaning and drywall repair to make the space livable. | If mold or asbestos is found | No mold or asbestos is detected | Prioritize making the space habitable | Tamika Marshall
10002 | MM/DD/YY | Category Two | We may not be able to work with previously contracted furnishing suppliers due to funding changes since the last project. | If we cannot work with the previous suppliers, we may end up spending more to furnish the rooms. | 30000 | 2 | 4 | 8 | Attempt to negotiate with existing contacts, but pivot to other available furnishers if necessary. | We are unable to strike a deal with our existing supplier | We are able to make a deal with the existing supplier | Find a furnishing supplier that can work with our budget | Marta Hicks
10003 | MM/DD/YY | Category Five | We need to hire support staff for the building before we can open to residents. | If we cannot hire the required support staff in time, we may need to delay resident move-in dates, which will delay rental income. | 15000 | 1 | 2 | 2 | Start the hiring process two months in advance of resident move in and prioritize high-need positions first. | We are unable to hire the required support staff before resident move-in | We have all required support staff by the date of move-in | Use contingency funds to pay upkeep costs until rental income starts to come in | Olivia Carter
0
0
0
0
0
0
0
0
0
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Risk Budget Contingency
Risk Assessment Budget Contingency Plan Template
PROJECT NAME | [5 empty] | LOW-END CONTINGENCY
[6 empty] | 0 |  |  | Total Estimated Costs Priority Levels 10 and higher
PROJECT MANAGER |  |  | DATE |  |  | HIGH-END CONTINGENCY
[6 empty] | 0 |  |  | Total Estimated Costs All Priority Levels
|  | Enter Risk Class titles on the Dropdown Key tab to populate the Risk Register Dropdown Menu. | [5 empty] | DO NOT ALTER SCORE CELLS Outcomes populate automatically.
REF ID | DATE RAISED | RISK CLASS | RISK DESCRIPTION | IMPACT DESCRIPTION | ESTIMATED COST | PROBABILITY 1 – 5 | IMPACT 1 – 16 | PRIORITY LEVEL Prob x Impact | CONTINGENCY PLAN STRATEGY | TRIGGER POINTS | END PLAN TRIGGER | ACTION | OWNER | NOTES
0
0
0
0
0
0
0
0
0
0
0
0
0

## Dropdown Keys – DO NOT DELETE –
PROJECT RISK REGISTER – MATRIX
PROBABILITY ¦ 1 – 5 | IMPACT ¦ 1 – 16 | PI SCORES ¦ 1 – 80 |  | 1 | 2 | 3 | 4 | 5
1 - RARE | 1 - INSIGNIFICANT | 1 – 2 • NEGLIGIBLE | 1 | 1 | 2 | 3 | 4 | 5
2 - UNLIKELY | 2 - MINOR | 3 – 8 • LOW | 2 | 2 | 4 | 6 | 8 | 10
3 - POSSIBLE | 4 - MODERATE | 10 – 16 • MEDIUM | 4 | 4 | 8 | 12 | 16 | 20
4 - LIKELY | 8 - MAJOR | 20 – 32 • HIGH | 8 | 8 | 16 | 24 | 32 | 40
5 - ALMOST CERTAIN | 16 - SEVERE | 40 – 80 • EXTREME | 16 | 16 | 32 | 48 | 64 | 80
PROBABILITY KEY | IMPACT KEY
1 | 1
2 | 2
3 | 4
4 | 8
5 | 16
Enter Risk Class titles below to populate the Risk Register Dropdown Menu.
RISK CLASS
Category One
Category Two
Category Three
Category Four
Category Five
Category Six
Category Seven
Category Eight
Category Nine
Category Ten
PROBABILITY
IMPACT

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.