## EX - Agile Portfolio Dashboard
Agile Project Portfolio Dashboard Template
Enter project data below; charts, graphs, and summary info will populate automatically.
This tab contains example data. To begin building your dashboard, use the BLANK tab. If necessary, enter alternate dropdown menu data in the tables below.
Department | [5 empty] | Department Lead |  | Date of Last Update
Marketing | [5 empty] | Marta Hicks |  | 10/21/20XX
Portfolio Progress | [6 empty] | Portfolio Financial Health
Deliverables |  | 75 |  | Bugs | 26 |  | Total Planned Budget |  |  | 5961000
% Finished |  | 30.67% |  | Stories | 27 |  | Total Actual Spend |  |  | 5865500
% Ongoing |  | 21.33% |  | Tasks | 22 |  | Budget Utilization Rate |  |  | 98.4%
Deliverables by Priority |  |  |  | Deliverables by Status | [5 empty] | Priority Level |  |  |  | Risk Radar
Project Data
Deliverable Type | ID | Description | Priority | Status | Assigned To | Budget Planned | Budget Actual | Budget Remaining | Expected Start Date | Expected Date of Completion | Duration in Days | Number of Days Remaining | Percent of Project Complete | Risk Level | Associated Risks | Comments | Attachments / Links
Bug |  |  | High | Finished |  | 525000 | 500000 | 25000 | 2024-03-05 | 2024-12-30 | 301 | 53 | 100% | Highly Unlikely
Story |  |  | Medium | Overdue |  | 285000 | 312000 | -27000 | 2024-04-16 | 2024-09-14 | 152 | -54 | 90% | Unlikely
Task |  |  | High | Overdue |  | 430000 | 384000 | 46000 | 2024-08-25 | 2024-09-30 | 37 | -38 | 50% | Possible
Bug |  |  | Low | Overdue |  | 85000 | 132000 | -47000 | 2024-09-10 | 2024-11-25 | 77 | 18 | 85% | Likely
Story |  |  | Medium | Paused |  | 250000 | 288500 | -38500 |  |  |  | – | 15% | Highly Likely
Bug |  |  | Low | Finished |  | 45000 | 62000 | -17000 |  |  |  | – | 100% | Highly Likely
Bug |  |  | High | Proposed |  | 580000 | 450000 | 130000 |  |  |  | – | 50% | Unlikely
Bug |  |  | High | Unscheduled |  | 785000 | 625000 | 160000 |  |  |  | – | 10% | Highly Unlikely
Task |  |  | Extreme | Review |  |  |  | – |  |  |  | – | 5% | Unlikely
Task |  |  | Extreme | Approved |  |  |  | – |  |  |  | – | 30% | Unlikely
Task |  |  | Extreme | Ongoing |  |  |  | – |  |  |  | – | 45% | Highly Unlikely
Task |  |  | Low | Finished |  |  |  | – |  |  |  | – | 100% | Unlikely
Story |  |  | Low | Paused |  |  |  | – |  |  |  | – | 85% | Unlikely
Bug |  |  | Low | Overdue |  |  |  | – |  |  |  | – | 30% | Unlikely
Story |  |  | Low | Terminated |  |  |  | – |  |  |  | – | 0% | Highly Unlikely
Bug |  |  | Low | Finished |  |  |  | – |  |  |  | – | 100% | Highly Unlikely
Story |  |  | Low | Finished |  |  |  | – |  |  |  | – | 100% | Unlikely
Bug |  |  | Low | Finished |  |  |  | – |  |  |  | – | 100% | Unlikely
Story |  |  | Low | Finished |  |  |  | – |  |  |  | – | 100% | Highly Unlikely
Story |  |  | Medium | Finished |  |  |  | – |  |  |  | – | 100% | Highly Likely
Task |  |  | Medium | Finished |  |  |  | – |  |  |  | – | 100% | Unlikely
Task |  |  | Medium | Finished |  |  |  | – |  |  |  | – | 100% | Highly Unlikely
Story |  |  | Medium | Finished |  |  |  | – |  |  |  | – | 100% | Highly Likely
Bug |  |  | Medium | Finished |  |  |  | – |  |  |  | – | 100% | Likely
Bug |  |  | Extreme | Finished |  |  |  | – |  |  |  | – | 100% | Likely
Story |  |  | High | Finished |  |  |  | – |  |  |  | – | 100% | Likely
Task |  |  | High | Finished |  | 500 |  | 500 |  |  |  | – | 100% | Likely
Task |  |  | Medium | Ongoing |  |  |  | – |  |  |  | – | 35% | Likely
Bug |  |  | High | Finished |  |  |  | – |  |  |  | – | 100% | Likely
Bug |  |  | Medium | Finished |  | 65000 | 58000 | 7000 |  |  |  | – | 100% | Highly Unlikely
Bug |  |  | Low | Ongoing |  | 98500 | 125000 | -26500 |  |  |  | – | 50% | Unlikely
Story |  |  | Extreme | Ongoing |  | 280000 | 312000 | -32000 |  |  |  | – | 25% | Likely
Story |  |  | Low | Ongoing |  | 325000 | 343000 | -18000 |  |  |  | – | 25% | Unlikely
Task |  |  | Low | Approved |  | 125000 | 123500 | 1500 |  |  |  | – | 13% | Likely
Story |  |  | Low | Approved |  | 250000 | 239500 | 10500 |  |  |  | – | 28% | Likely
Bug |  |  | Low | Overdue |  |  |  | – |  |  |  | – | 25% | Highly Unlikely
Story |  |  | Low | Paused |  |  |  | – |  |  |  | – | 25% | Unlikely
Bug |  |  | Low | Paused |  |  |  | – |  |  |  | – | 30% | Unlikely
Story |  |  | Low | Paused |  |  |  | – |  |  |  | – | 10% | Highly Unlikely
Story |  |  | High | Not Started |  |  |  | – |  |  |  | – | 5% | Unlikely
Task |  |  | Extreme | Review |  |  |  | – |  |  |  | – | 18% | Unlikely
Task |  |  | Extreme | Approved |  |  |  | – |  |  |  | – | 30% | Unlikely
Task |  |  | Extreme | Ongoing |  |  |  | – |  |  |  | – | 25% | Highly Unlikely
Task |  |  | Low | Finished |  |  |  | – |  |  |  | – | 100% | Unlikely
Story |  |  | Low | Paused |  |  |  | – |  |  |  | – | 20% | Unlikely
Bug |  |  | Low | Overdue |  |  |  | – |  |  |  | – | 20% | Unlikely
Story |  |  | Low | Terminated |  |  |  | – |  |  |  | – | 20% | Highly Unlikely
Bug |  |  | Low | Review |  |  |  | – |  |  |  | – | 20% | Highly Unlikely
Story |  |  | Low | Review |  |  |  | – |  |  |  | – | 30% | Unlikely
Bug |  |  | Low | Approved |  |  |  | – |  |  |  | – | 40% | Unlikely
Story |  |  | Low | Approved |  |  |  | – |  |  |  | – | 50% | Highly Unlikely
Story |  |  | Medium | Approved |  |  |  | – |  |  |  | – | 60% | Highly Likely
Task |  |  | Medium | Finished |  |  |  | – |  |  |  | – | 100% | Unlikely
Task |  |  | Medium | Finished |  |  |  | – |  |  |  | – | 100% | Highly Unlikely
Story |  |  | Medium | Ongoing |  |  |  | – |  |  |  | – | 25% | Highly Likely
Bug |  |  | Medium | Ongoing |  |  |  | – |  |  |  | – | 30% | Likely
Bug |  |  | Extreme | Ongoing |  |  |  | – |  |  |  | – | 40% | Likely
Story |  |  | High | Ongoing |  |  |  | – |  |  |  | – | 50% | Likely
Task |  |  | High | Ongoing |  | 500 |  | 500 |  |  |  | – | 60% | Likely
Task |  |  | Medium | Ongoing |  |  |  | – |  |  |  | – | 70% | Likely
Bug |  |  | High | Ongoing |  |  |  | – |  |  |  | – | 80% | Likely
Bug |  |  | Medium | Finished |  | 65000 | 58000 | 7000 |  |  |  | – | 100% | Highly Unlikely
Bug |  |  | Low | Ongoing |  | 98500 | 125000 | -26500 |  |  |  | – | 50% | Unlikely
Story |  |  | Extreme | Ongoing |  | 280000 | 312000 | -32000 |  |  |  | – | 25% | Likely
Story |  |  | Low | Ongoing |  | 325000 | 343000 | -18000 |  |  |  | – | 25% | Unlikely
Task |  |  | Low | Approved |  | 125000 | 123500 | 1500 |  |  |  | – | 13% | Likely
Story |  |  | Low | Approved |  | 250000 | 239500 | 10500 |  |  |  | – | 28% | Likely
Task |  |  | Medium | Finished |  | 84000 | 75000 | 9000 |  |  |  | – | 100% | Possible
Bug |  |  | Medium | Not Started |  | 28000 | 27000 | 1000 |  |  |  | – | 0% | Likely
Bug |  |  | Low | Terminated |  | 45000 | 45000 | 0 |  |  |  | – | 0% | Highly Unlikely
Story |  |  | High | Not Started |  | 58000 | 58000 | 0 |  |  |  | – | 0% | Highly Unlikely
Task |  |  | Extreme | Unscheduled |  | 128000 | 133000 | -5000 |  |  |  | – | 5% | Highly Unlikely
Story |  |  | High | Unscheduled |  | 175000 | 184000 | -9000 |  |  |  | – | 5% | Highly Unlikely
Task |  |  | High | Finished |  | 58000 | 58000 | 0 |  |  |  | – | 100% | Highly Unlikely
Bug |  |  | Extreme | Not Started |  | 112000 | 130000 | -18000 |  |  |  | – | 0% | Highly Unlikely
Dropdown Menu and Chart Data
If necessary, enter alternate dropdown menu data in the tables below.
Quantity columns calculate automatically to populate Dashboard charts; do not alter.
Deliverable Type | Deliverable Quantity | Project Status | Status Quantity | Priority Level | Priority Quantity | [8 empty] | Risk Level | Risk Quantity
Bug | 26 | Proposed | 1 | Low | 31 | [8 empty] | Highly Unlikely | 22
Story | 27 | Unscheduled | 3 | Medium | 18 | [8 empty] | Unlikely | 25
Task | 22 | Not Started | 4 | High | 14 | [8 empty] | Possible | 2
|  | Review | 4 | Extreme | 12 | [8 empty] | Likely | 20
|  | Approved | 9 | [10 empty] | Highly Likely | 6
|  | Ongoing | 16
|  | Finished | 23
|  | Paused | 6
|  | Overdue | 6
|  | Terminated | 3
Dashboard Data
Quantity columns calculate automatically to populate Dashboard charts; do not alter.
Deliverable Type | Low | Medium | High | Extreme | Total Deliverables by Type
Bug | 13 | 5 | 5 | 3 | 26
Story | 14 | 6 | 5 | 2 | 27
Task | 4 | 7 | 4 | 7 | 22
CLICK HERE TO CREATE IN SMARTSHEET
Formulas:
Number of Days Remaining = IF(PROJECTS[[#This Row],[Expected Date of Completion]]="","–",(PROJECTS[[#This Row],[Expected Date of Completion]]-TODAY()))

## BLANK - Portfolio Dashboard
Agile Project Portfolio Dashboard Template
Enter project data below; charts, graphs, and summary info will populate automatically.
Department | [5 empty] | Department Lead |  | Date of Last Update
Portfolio Progress | [6 empty] | Portfolio Financial Health
Deliverables |  | 0 |  | Bugs | 0 |  | Total Planned Budget |  |  | 0
% Finished |  |  |  | Stories | 0 |  | Total Actual Spend |  |  | 0
% Ongoing |  |  |  | Tasks | 0 |  | Budget Utilization Rate |  |  | –
Deliverables by Priority |  |  |  | Deliverables by Status | [5 empty] | Priority Level |  |  |  | Risk Radar
Project Data
Deliverable Type | ID | Description | Priority | Status | Assigned To | Budget Planned | Budget Actual | Budget Remaining | Expected Start Date | Expected Date of Completion | Duration in Days | Number of Days Remaining | Percent of Project Complete | Risk Level | Associated Risks | Comments | Attachments / Links
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | –
[8 empty] | – |  |  |  | – | 100%
[8 empty] | – |  |  |  | – | 0%
Dropdown Menu and Chart Data
If necessary, enter alternate dropdown menu data in the tables below.
Quantity columns calculate automatically to populate Dashboard charts; do not alter.
Deliverable Type | Deliverable Quantity | Project Status | Status Quantity | Priority Level | Priority Quantity | [8 empty] | Risk Level | Risk Quantity
Bug | 0 | Proposed | 0 | Low | 0 | [8 empty] | Highly Unlikely | 0
Story | 0 | Unscheduled | 0 | Medium | 0 | [8 empty] | Unlikely | 0
Task | 0 | Not Started | 0 | High | 0 | [8 empty] | Possible | 0
|  | Review | 0 | Extreme | 0 | [8 empty] | Likely | 0
|  | Approved | 0 | [10 empty] | Highly Likely | 0
|  | Ongoing | 0
|  | Finished | 0
|  | Paused | 0
|  | Overdue | 0
|  | Terminated | 0
Dashboard Data
Quantity columns calculate automatically to populate Dashboard charts; do not alter.
Deliverable Type | Low | Medium | High | Extreme | Total Deliverables by Type
Bug | 0 | 0 | 0 | 0 | 0
Story | 0 | 0 | 0 | 0 | 0
Task | 0 | 0 | 0 | 0 | 0
Formulas:
Number of Days Remaining = IF(PROJECTS2[[#This Row],[Expected Date of Completion]]="","–",(PROJECTS2[[#This Row],[Expected Date of Completion]]-TODAY()))

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.