## EXAMPLE - IT Project Port Dash
IT Project Portfolio Dashboard Template
Enter dashboard data in the tables below; charts, graphs, and summary info will populate automatically.
This tab contains example data. To begin building your dashboard, use the BLANK tab.
DELIVERY TIMELINE & RESOURCES
PROJECT FINANCIALS
RISK ANALYSIS
OPEN & PENDING ACTIONS
DASHBOARD DATA
PROJECT NAME | TIMELINE |  |  |  | NUMBER OF TEAM MEMBERS | BUDGET |  |  | RISKS |  |  | OPEN |  | PENDING ACTIONS
| CALENDAR | BEGIN | FINISH | # of DAYS |  | PROJECTED | ACTUAL | REMAINDER | HIGH | MEDIUM | LOW | ISSUES | REVISIONS
Existing Project Enhancements | 2025-05-01 | 2025-05-05 | 2025-07-01 | 57 | 50 | 5000000 | 4500000 | 500000 | 0 | 3 | 5 | 6 | 2 | 4
Infrastructure | 2025-06-01 | 2025-05-10 | 2025-08-10 | 92 | 30 | 3000000 | 3100000 | -100000 | 1 | 2 | 3 | 3 | 1 | 3
New Ventures | 2025-07-01 | 2025-06-10 | 2026-03-01 | 264 | 20 | 2000000 | 2300000 | -300000 | 3 | 1 | 1 | 2 | 1 | 2
[6 empty] | 10000000 | 9900000 | 100000 | 4 | 6 | 9 | 11 | 4 | 9
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - IT Project Port Dash
IT Project Portfolio Dashboard Template
**Enter data in the table beginning on Row 20. Dashboard charts will populate automatically.
DELIVERY TIMELINE & RESOURCES
PROJECT FINANCIALS
RISK ANALYSIS
OPEN & PENDING ACTIONS
DASHBOARD DATA
**Delete unused rows to correctly populate charts and graphs, above.
**User to complete non-shaded cells only.
PROJECT NAME | TIMELINE |  |  |  | NUMBER OF TEAM MEMBERS | BUDGET |  |  | RISKS |  |  | OPEN |  | PENDING ACTIONS
| CALENDAR | BEGIN | FINISH | # of DAYS |  | PROJECTED | ACTUAL | REMAINDER | HIGH | MEDIUM | LOW | ISSUES | REVISIONS
Project A |  |  |  | 0 |  |  |  | 0
Project B |  |  |  | 0 |  |  |  | 0
Project C |  |  |  | 0 |  |  |  | 0
Project D |  |  |  | 0 |  |  |  | 0
Project E |  |  |  | 0 |  |  |  | 0
Project F |  |  |  | 0 |  |  |  | 0
Project G |  |  |  | 0 |  |  |  | 0
Project H |  |  |  | 0 |  |  |  | 0
Project J |  |  |  | 0 |  |  |  | 0
Project K |  |  |  | 0 |  |  |  | 0
Project L |  |  |  | 0 |  |  |  | 0
Project M |  |  |  | 0 |  |  |  | 0
Project N |  |  |  | 0 |  |  |  | 0
Project P |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PROJECT REPORT
PROJECT NAME | SCHEDULE | BUDGET | RESOURCES | RISKS | ISSUES | COMMENTS
Project A
Project B
Project C
Project D
Project E
Project F
Project G
Project H
Project J
Project K
Project L
Project M
Project N
Project P
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your data table.*

## – Disclaimer –
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.