## EX - Portfolio Budget Dash
Project Portfolio Dashboard with Budget Tracking Template
Enter project data below; charts, graphs, and summary info will populate automatically.
This tab contains example data. To begin building your dashboard, use the BLANK tab. If necessary, enter alternate dropdown menu data on the Dropdown Keys tab.
Department | [5 empty] | Department Lead |  |  |  | Total Projects |  | Date of Last Update
Marketing | [5 empty] | Jason Desjardins |  |  |  | 4 |  | 10/21/20XX
Portfolio Planned vs. Actual Budget
| Budget | 196700
| Actual | 170215
| Balance | 26485
[6 empty] | LABOR |  |  | MATERIALS |  |  | OTHER |  |  |  |  | BUDGET vs. ACTUAL |  | BALANCE
TASK ID | DESCRIPTION | STATUS | START DATE – PLANNED – | START DATE – ACTUAL – | END DATE | HOURS | $ / HR | LABOR TOTAL | UNITS | $ / UNITS | MATERIALS TOTAL | TRAVEL | EQUIP. / SPACE | FIXED | MISC. | OTHER TOTAL | BUDGET | ACTUAL | UNDER / OVER
1.0 | PROJECT 1
1.1 | Task | In Progress |  |  |  | 5 | 50 | 250 | 5000 | 0.03 | 150 |  |  |  |  | 0 | 800 | 400 | 400
1.2 | Task | In Progress |  |  |  | 25 | 35 | 875 |  |  | 0 |  |  |  |  | 0 | 1000 | 875 | 125
1.3 | Task | Complete |  |  |  | 40 | 75 | 3000 | 1 | 2600 | 2600 |  |  |  |  | 0 | 6000 | 5600 | 400
1.3a | Subtask | On Hold | [5 empty] | 0 |  |  | 0 |  | 5200 |  |  | 5200 | 5000 | 5200 | -200
1.3b | Subtask | Overdue | [5 empty] | 0 |  |  | 0 |  |  | 4000 |  | 4000 | 4000 | 4000 | 0
1.3c | Subtask | Needs Review | [5 empty] | 0 |  |  | 0 |  |  |  | 1600 | 1600 | 500 | 1600 | -1100
1.3d | Subtask | Approved | [5 empty] | 0 |  |  | 0 |  | 3200 |  |  | 3200 | 2500 | 3200 | -700
1.4 | Task | In Progress | [5 empty] | 0 | 5 | 350 | 1750 |  |  |  |  | 0 | 1500 | 1750 | -250
1.5 | Task | Not Started |  |  |  | 17 | 85 | 1445 |  |  | 0 |  |  |  |  | 0 | 2000 | 1445 | 555
[8 empty] | 5570 |  |  | 4500 | 0 | 8400 | 4000 | 1600 | 14000 | 23300 | 24070 | -770
[6 empty] | LABOR |  |  | MATERIALS |  |  | OTHER |  |  |  |  | BUDGET vs. ACTUAL |  | BALANCE
TASK ID | DESCRIPTION | STATUS | START DATE – PLANNED – | START DATE – ACTUAL – | END DATE | HOURS | $ / HR | LABOR TOTAL | UNITS | $ / UNITS | MATERIALS TOTAL | TRAVEL | EQUIP. / SPACE | FIXED | MISC. | OTHER TOTAL | BUDGET | ACTUAL | UNDER / OVER
2.0 | PROJECT 2
2.1 | Task | Complete | [5 empty] | 0 | 15 | 480 | 7200 |  |  |  |  | 0 | 8500 | 7200 | 1300
2.2 | Task | On Hold | [5 empty] | 0 |  |  | 0 | 1800 |  |  |  | 1800 | 2200 | 1800 | 400
2.3 | Task | Overdue |  |  |  | 72 | 150 | 10800 |  |  | 0 |  |  |  |  | 0 | 14000 | 10800 | 3200
2.4 | Task | In Progress | [5 empty] | 0 |  |  | 0 |  |  |  | 1650 | 1650 | 2000 | 1650 | 350
2.5 | Task | Not Started | [5 empty] | 0 | 2 | 8000 | 16000 |  |  |  |  | 0 | 10000 | 16000 | -6000
2.6 | Task | Not Started | [5 empty] | 0 |  |  | 0 |  |  | 8600 |  | 8600 | 8600 | 8600 | 0
2.7 | Task | Not Started |  |  |  | 40 | 50 | 2000 |  |  | 0 |  |  |  |  | 0 | 3000 | 2000 | 1000
2.8 | Task | Not Started |  |  |  | 160 | 40 | 6400 |  |  | 0 |  |  |  |  | 0 | 7500 | 6400 | 1100
2.9 | Task | Not Started | [5 empty] | 0 |  |  | 0 |  | 14000 |  |  | 14000 | 18000 | 14000 | 4000
[8 empty] | 19200 |  |  | 23200 | 1800 | 14000 | 8600 | 1650 | 26050 | 73800 | 68450 | 5350
[6 empty] | LABOR |  |  | MATERIALS |  |  | OTHER |  |  |  |  | BUDGET vs. ACTUAL |  | BALANCE
TASK ID | DESCRIPTION | STATUS | START DATE – PLANNED – | START DATE – ACTUAL – | END DATE | HOURS | $ / HR | LABOR TOTAL | UNITS | $ / UNITS | MATERIALS TOTAL | TRAVEL | EQUIP. / SPACE | FIXED | MISC. | OTHER TOTAL | BUDGET | ACTUAL | UNDER / OVER
3.0 | PROJECT 3
3.1 | Task | Not Started |  |  |  | 5 | 50 | 250 | 5000 | 0.03 | 150 |  |  |  |  | 0 | 800 | 400 | 400
3.2 | Task | In Progress |  |  |  | 25 | 35 | 875 |  |  | 0 |  |  |  |  | 0 | 1000 | 875 | 125
3.3 | Task | Complete |  |  |  | 40 | 75 | 3000 | 1 | 2600 | 2600 |  |  |  |  | 0 | 6000 | 5600 | 400
3.4 | Task | On Hold | [5 empty] | 0 |  |  | 0 |  | 5200 |  |  | 5200 | 5000 | 5200 | -200
3.5 | Task | Overdue | [5 empty] | 0 |  |  | 0 |  |  | 4000 |  | 4000 | 4000 | 4000 | 0
3.6 | Task | In Progress | [5 empty] | 0 |  |  | 0 |  |  |  | 1600 | 1600 | 500 | 1600 | -1100
3.7 | Task | In Progress | [5 empty] | 0 |  |  | 0 |  | 3200 |  |  | 3200 | 2500 | 3200 | -700
3.8 | Task | In Progress | [5 empty] | 0 | 5 | 350 | 1750 |  |  |  |  | 0 | 1500 | 1750 | -250
3.9 | Task | Not Started |  |  |  | 17 | 85 | 1445 |  |  | 0 |  |  |  |  | 0 | 2000 | 1445 | 555
[8 empty] | 5570 |  |  | 4500 | 0 | 8400 | 4000 | 1600 | 14000 | 23300 | 24070 | -770
[6 empty] | LABOR |  |  | MATERIALS |  |  | OTHER |  |  |  |  | BUDGET vs. ACTUAL |  | BALANCE
TASK ID | DESCRIPTION | STATUS | START DATE – PLANNED – | START DATE – ACTUAL – | END DATE | HOURS | $ / HR | LABOR TOTAL | UNITS | $ / UNITS | MATERIALS TOTAL | TRAVEL | EQUIP. / SPACE | FIXED | MISC. | OTHER TOTAL | BUDGET | ACTUAL | UNDER / OVER
4.0 | PROJECT 4
4.1 | Task | Complete |  |  |  | 100 | 80 | 8000 | 15 | 25 | 375 |  |  |  |  | 0 | 11000 | 8375 | 2625
4.2 | Task | On Hold | [5 empty] | 0 |  |  | 0 | 1800 |  |  |  | 1800 | 2200 | 1800 | 400
4.3 | Task | Overdue |  |  |  | 72 | 150 | 10800 |  |  | 0 |  |  |  |  | 0 | 14000 | 10800 | 3200
4.4 | Task | In Progress | [5 empty] | 0 |  |  | 0 |  |  |  | 1650 | 1650 | 2000 | 1650 | 350
4.5 | Task | Not Started | [5 empty] | 0 |  |  | 0 |  |  |  |  | 0 | 10000 | 0 | 10000
4.6 | Task | Not Started | [5 empty] | 0 |  |  | 0 |  |  | 8600 |  | 8600 | 8600 | 8600 | 0
4.7 | Task | Not Started |  |  |  | 40 | 50 | 2000 |  |  | 0 |  |  |  |  | 0 | 3000 | 2000 | 1000
4.8 | Task | Not Started |  |  |  | 160 | 40 | 6400 |  |  | 0 |  |  |  |  | 0 | 7500 | 6400 | 1100
4.9 | Task | Not Started | [5 empty] | 0 |  |  | 0 |  | 14000 |  |  | 14000 | 18000 | 14000 | 4000
[8 empty] | 27200 |  |  | 375 | 1800 | 14000 | 8600 | 1650 | 26050 | 76300 | 53625 | 22675
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Portfolio Budget Dash
Project Portfolio Dashboard with Budget Tracking Template
Enter project data below; charts, graphs, and summary info will populate automatically.
If necessary, enter alternate dropdown menu data on the Dropdown Keys tab.
Department | [5 empty] | Department Lead |  |  |  | Total Projects |  | Date of Last Update
Portfolio Planned vs. Actual Budget
| Budget | 0
| Actual | 0
| Balance | 0
[6 empty] | LABOR |  |  | MATERIALS |  |  | OTHER |  |  |  |  | BUDGET vs. ACTUAL |  | BALANCE
TASK ID | DESCRIPTION | STATUS | START DATE – PLANNED – | START DATE – ACTUAL – | END DATE | HOURS | $ / HR | LABOR TOTAL | UNITS | $ / UNITS | MATERIALS TOTAL | TRAVEL | EQUIP. / SPACE | FIXED | MISC. | OTHER TOTAL | BUDGET | ACTUAL | UNDER / OVER
1.0 | PROJECT 1
1.1 | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
1.2 | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
1.3 | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
1.4 | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
1.5 | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
1.6 | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
1.7 | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
1.8 | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
1.9 | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | LABOR |  |  | MATERIALS |  |  | OTHER |  |  |  |  | BUDGET vs. ACTUAL |  | BALANCE
TASK ID | DESCRIPTION | STATUS | START DATE – PLANNED – | START DATE – ACTUAL – | END DATE | HOURS | $ / HR | LABOR TOTAL | UNITS | $ / UNITS | MATERIALS TOTAL | TRAVEL | EQUIP. / SPACE | FIXED | MISC. | OTHER TOTAL | BUDGET | ACTUAL | UNDER / OVER
2.0 | PROJECT 2
2.1 | Task | [6 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
2.2 | Task | [6 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
2.3 | Task | [6 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
2.4 | Task | [6 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
2.5 | Task | [6 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
2.6 | Task | [6 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
2.7 | Task | [6 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
2.8 | Task | [6 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
2.9 | Task | [6 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | LABOR |  |  | MATERIALS |  |  | OTHER |  |  |  |  | BUDGET vs. ACTUAL |  | BALANCE
TASK ID | DESCRIPTION | STATUS | START DATE – PLANNED – | START DATE – ACTUAL – | END DATE | HOURS | $ / HR | LABOR TOTAL | UNITS | $ / UNITS | MATERIALS TOTAL | TRAVEL | EQUIP. / SPACE | FIXED | MISC. | OTHER TOTAL | BUDGET | ACTUAL | UNDER / OVER
3.0 | PROJECT 3
3.1 | Task | [6 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
3.2 | Task | [6 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
3.3 | Task | [6 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
3.4 | Task | [6 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
3.5 | Task | [6 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
3.6 | Task | [6 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
3.7 | Task | [6 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
3.8 | Task | [6 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
3.9 | Task | [6 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | LABOR |  |  | MATERIALS |  |  | OTHER |  |  |  |  | BUDGET vs. ACTUAL |  | BALANCE
TASK ID | DESCRIPTION | STATUS | START DATE – PLANNED – | START DATE – ACTUAL – | END DATE | HOURS | $ / HR | LABOR TOTAL | UNITS | $ / UNITS | MATERIALS TOTAL | TRAVEL | EQUIP. / SPACE | FIXED | MISC. | OTHER TOTAL | BUDGET | ACTUAL | UNDER / OVER
4.0 | PROJECT 4
4.1 | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
4.2 | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
4.3 | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
4.4 | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
4.5 | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
4.6 | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
4.7 | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
4.8 | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
4.9 | [7 empty] | 0 |  |  | 0 |  |  |  |  | 0 |  | 0 | 0
[8 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.