## EX - Project Task Dashboard
Project Portfolio Task Management Dashboard Template
Enter project data below; charts, graphs, and summary info will populate automatically.
This tab contains example data. To begin building your dashboard, use the BLANK tab. If necessary, enter alternate dropdown menu data in the tables below.
Department |  |  |  | Department Lead |  | Date of Last Update
Marketing |  |  |  | Marta Hicks |  | 10/21/20XX
Overall Project Count |  |  | 8 |  | Portfolio Financial Health
Overall Task Count |  |  | 55 |  | Budget |  | 6655000
% of Finished Tasks |  |  | 3.636% |  | Actual |  | 5636000
% of Ongoing Tasks |  |  | 12.73% |  | Balance |  | 1019000
Active Projects and Project Tasks | [8 empty] | Tasks by Status |  |  |  |  | Risk Radar
Priority Level
Project Data
Project ID | Project Name | Task ID | Description | Priority | Status | Assigned To | Budget | Actual | Budget Less Actual | Expected Start Date | Expected Date of Completion | Duration in Days | Number of Days Remaining | Percent of Project Complete | Risk Level | Associated Risks | Comments | Attachments / Links
PID-001 | Project 1 | [5 empty] | 800000 | 500000 | 300000 | 2024-03-05 | 2024-12-30 | 301 | 53 |  | Highly Unlikely
PID-001 | Project 1 | TSK-1001 |  | Medium | Overdue |  | 285000 | 312000 | -27000 | 2024-04-16 | 2024-09-14 | 152 | -54 | 90% | Unlikely
PID-001 | Project 1 | TSK-1002 |  | High | Overdue |  | 430000 | 384000 | 46000 | 2024-08-25 | 2024-09-30 | 37 | -38 | 50% | Possible
PID-001 | Project 1 | TSK-1003 |  | Low | Overdue |  |  |  | – | 2024-09-10 | 2024-11-25 | 77 | 18 | 85% | Likely
PID-001 | Project 1 | TSK-1004 |  | Medium | Paused |  |  |  | – |  |  |  | – | 15% | Highly Likely
PID-001 | Project 1 | TSK-1005 |  | Low | Finished |  |  |  | – |  |  |  | – | 100% | Highly Likely
PID-001 | Project 1 | TSK-1006 |  | Medium | Finished |  |  |  | – |  |  |  | – | 100% | Highly Unlikely
PID-001 | Project 1 | TSK-1007 |  | Low | Ongoing |  |  |  | – |  |  |  | – | 50% | Unlikely
PID-001 | Project 1 | TSK-1008 |  | Extreme | Review |  |  |  | – |  |  |  | – | 25% | Likely
PID-001 | Project 1 | TSK-1009 |  | Low | Review |  |  |  | – |  |  |  | – | 25% | Unlikely
PID-001 | Project 1 | TSK-1010 |  | Low | Approved |  |  |  | – |  |  |  | – | 13% | Likely
PID-001 | Project 1 | TSK-1011 |  | Low | Approved |  |  |  | – |  |  |  | – | 28% | Likely
PID-002 | Project 2 | [7 empty] | – |  |  |  | – | 0% | Possible
PID-002 | Project 2 | TSK-2001 |  | Medium | Not Started |  |  |  | – |  |  |  | – | 0% | Likely
PID-002 | Project 2 | TSK-2002 |  | Low | Terminated |  |  |  | – |  |  |  | – | 0% | Highly Unlikely
PID-002 | Project 2 | TSK-2003 |  | High | Not Started |  |  |  | – |  |  |  | – | 0% | Highly Unlikely
PID-002 | Project 2 | TSK-2004 |  | Extreme | Unscheduled |  |  |  | – |  |  |  | – | 5% | Highly Unlikely
PID-002 | Project 2 | TSK-2005 |  | High | Unscheduled |  |  |  | – |  |  |  | – | 5% | Highly Unlikely
PID-003 | Project 3 | [7 empty] | – |  |  |  | – | 0% | Highly Unlikely
PID-003 | Project 3 | TSK-3001 |  | Extreme | Not Started |  |  |  | – |  |  |  | – | 0% | Highly Unlikely
PID-003 | Project 3 | TSK-3002 |  | Low | Proposed |  |  |  | – |  |  |  | – | 0% | Highly Unlikely
PID-003 | Project 3 | TSK-3003 |  | Low | Not Started |  |  |  | – |  |  |  | – | 0% | Highly Unlikely
PID-003 | Project 3 | TSK-3004 |  | High | Review |  |  |  | – |  |  |  | – | 30% | Likely
PID-003 | Project 3 | TSK-3005 |  | Extreme | Approved |  |  |  | – |  |  |  | – | 40% | Unlikely
PID-003 | Project 3 | TSK-3006 |  | High | Approved |  |  |  | – |  |  |  | – | 25% | Unlikely
PID-003 | Project 3 | TSK-3007 |  | Extreme | Ongoing |  |  |  | – |  |  |  | – | 80% | Unlikely
PID-004 | Project 4 | [7 empty] | – |  |  |  | – | 50% | Unlikely
PID-004 | Project 4 | TSK-4001 |  | Medium | Terminated |  |  |  | – |  |  |  | – | 0% | Unlikely
PID-004 | Project 4 | TSK-4002 |  | Extreme | Review |  |  |  | – |  |  |  | – | 0% | Unlikely
PID-004 | Project 4 | TSK-4003 |  | Medium | Ongoing |  |  |  | – |  |  |  | – | 25% | Unlikely
PID-004 | Project 4 | TSK-4004 |  | Extreme | Proposed |  | 1624000 | 1500000 | 124000 | 2024-06-01 | 2024-10-27 | 149 | -11 | 8% | Likely
PID-004 | Project 4 | TSK-4005 |  | Extreme | Approved |  | 946000 | 720000 | 226000 |  |  |  | – | 11% | Likely
PID-004 | Project 4 | TSK-4006 |  | Low | Approved |  | 0 | 0 | 0 |  |  |  | – | 17% | Highly Likely
PID-004 | Project 4 | TSK-4007 |  | Low | Not Started |  |  |  | – |  |  |  | – | 0% | Possible
PID-005 | Project 5 |  |  | Low | Terminated |  |  |  | – |  |  |  | – | 0% | Possible
PID-005 | Project 5 | TSK-5001 |  | Medium | Not Started |  |  |  | – |  |  |  | – | 0% | Likely
PID-005 | Project 5 | TSK-5002 | [6 empty] | – |  |  |  | – | 0% | Highly Unlikely
PID-005 | Project 5 | TSK-5003 |  | High | Not Started |  |  |  | – |  |  |  | – | 0% | Highly Unlikely
PID-005 | Project 5 | TSK-5004 |  | Extreme | Unscheduled |  |  |  | – |  |  |  | – | 5% | Highly Unlikely
PID-005 | Project 5 | TSK-5005 |  | High | Unscheduled |  |  |  | – |  |  |  | – | 5% | Highly Unlikely
PID-005 | Project 5 | TSK-5006 |  | High | Proposed |  |  |  | – |  |  |  | – | 0% | Highly Unlikely
PID-006 | Project 6 | [7 empty] | – |  |  |  | – | 0% | Highly Unlikely
PID-006 | Project 6 | TSK-6001 |  | Low | Proposed |  |  |  | – |  |  |  | – | 0% | Highly Unlikely
PID-006 | Project 6 | TSK-6002 |  | Low | Not Started |  |  |  | – |  |  |  | – | 0% | Highly Unlikely
PID-006 | Project 6 | TSK-6003 |  | High | Review |  |  |  | – |  |  |  | – | 30% | Likely
PID-006 | Project 6 | TSK-6004 |  | Extreme | Approved |  |  |  | – |  |  |  | – | 40% | Unlikely
PID-007 | Project 7 | [7 empty] | – |  |  |  | – | 25% | Unlikely
PID-007 | Project 7 | TSK-7001 |  | Extreme | Ongoing |  |  |  | – |  |  |  | – | 80% | Unlikely
PID-007 | Project 7 | TSK-7002 |  | Medium | Paused |  |  |  | – |  |  |  | – | 50% | Unlikely
PID-007 | Project 7 | TSK-7003 |  | Medium | Terminated |  |  |  | – |  |  |  | – | 0% | Unlikely
PID-007 | Project 7 | TSK-7004 |  | Extreme | Review |  |  |  | – |  |  |  | – | 0% | Unlikely
PID-007 | Project 7 | TSK-7005 |  | Medium | Ongoing |  |  |  | – |  |  |  | – | 25% | Unlikely
PID-007 | Project 7 | TSK-7006 |  | Extreme | Proposed |  | 1624000 | 1500000 | 124000 | 2024-06-01 | 2024-10-27 | 149 | -11 | 8% | Likely
PID-007 | Project 7 | TSK-7007 |  | Extreme | Approved |  | 946000 | 720000 | 226000 |  |  |  | – | 11% | Likely
PID-007 | Project 7 | TSK-7008 |  | Low | Approved |  | 0 | 0 | 0 |  |  |  | – | 17% | Highly Likely
PID-007 | Project 7 | TSK-7009 |  | Low | Proposed |  | 0 | 0 | 0 |  |  |  | – | 20% | Likely
PID-007 | Project 7 | TSK-7010 |  | Medium | Not Started |  | 0 | 0 | 0 |  |  |  | – | 30% | Highly Likely
PID-007 | Project 7 | TSK-7011 |  | Medium | Ongoing |  | 0 | 0 | 0 |  |  |  | – | 45% | Highly Likely
PID-007 | Project 7 | TSK-7012 |  | High | Review |  | 0 | 0 | 0 |  |  |  | – | 30% | Unlikely
PID-008 | Project 8 | [7 empty] | – |  |  |  | – | 40% | Highly Unlikely
PID-008 | Project 8 | TSK-8001 |  | High | Not Started |  |  |  | – |  |  |  | – | 15% | Unlikely
PID-008 | Project 8 | TSK-8002 |  | Extreme | Unscheduled |  |  |  | – |  |  |  | – | 20% | Unlikely
PID-008 | Project 8 | TSK-8003 |  | High | Ongoing |  |  |  | – |  |  |  | – | 75% | Unlikely
Dropdown Menu and Chart Data
If necessary, enter alternate dropdown menu data in the tables below.
Quantity columns calculate automatically to populate dashboard charts; do not alter.
Priority Level | Priority Quantity |  | Project Status | Status Quantity |  | Risk Level | Risk Quantity
Low | 16 |  | Proposed | 6 |  | Highly Unlikely | 19
Medium | 12 |  | Unscheduled | 5 |  | Unlikely | 21
High | 12 |  | Not Started | 10 |  | Possible | 4
Extreme | 15 |  | Review | 7 |  | Likely | 13
|  |  | Approved | 9 |  | Highly Likely | 6
|  |  | Ongoing | 7
|  |  | Finished | 2
|  |  | Paused | 2
|  |  | Overdue | 3
|  |  | Terminated | 4
Dashboard Data | [10 empty] | Overall Total Tasks
Quantity columns calculate automatically to populate dashboard charts; do not alter. | [10 empty] | 55
Unique Project ID | Proposed | Unscheduled | Not Started | Review | Approved | Ongoing | Finished | Paused | Overdue | Terminated | Total Tasks per Project
PID-001 | 0 | 0 | 0 | 2 | 2 | 1 | 2 | 1 | 3 | 0 | 11
PID-002 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5
PID-003 | 1 | 0 | 2 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 7
PID-004 | 1 | 0 | 1 | 1 | 2 | 1 | 0 | 0 | 0 | 1 | 7
PID-005 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6
PID-006 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 4
PID-007 | 2 | 0 | 1 | 2 | 2 | 3 | 0 | 1 | 0 | 1 | 12
PID-008 | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CLICK HERE TO CREATE IN SMARTSHEET
Formulas:
Number of Days Remaining = IF(PROJECTS[[#This Row],[Expected Date of Completion]]="","–",(PROJECTS[[#This Row],[Expected Date of Completion]]-TODAY()))

## BLANK - Project Task Dashboard
Project Portfolio Task Management Dashboard Template
Enter project data below; charts, graphs, and summary info will populate automatically.
If necessary, enter alternate dropdown menu data in the tables below.
Department |  |  |  | Department Lead |  | Date of Last Update
Overall Project Count |  |  | 0 |  | Portfolio Financial Health
Overall Task Count |  |  | 0 |  | Budget |  | 0
% of Finished Tasks |  |  |  |  | Actual |  | 0
% of Ongoing Tasks |  |  |  |  | Balance |  | 0
Active Projects and Project Tasks | [8 empty] | Tasks by Status |  |  |  |  | Risk Radar
Priority Level
Project Data
Project ID | Project Name | Task ID | Description | Priority | Status | Assigned To | Budget | Actual | Budget Less Actual | Expected Start Date | Expected Date of Completion | Duration in Days | Number of Days Remaining | Percent of Project Complete | Risk Level | Associated Risks | Comments | Attachments / Links
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | –
[9 empty] | – |  |  |  | – | 0%
[9 empty] | – |  |  |  | – | 100%
Dropdown Menu and Chart Data
If necessary, enter alternate dropdown menu data in the tables below.
Quantity columns calculate automatically to populate dashboard charts; do not alter.
Priority Level | Priority Quantity |  | Project Status | Status Quantity |  | Risk Level | Risk Quantity
Low | 0 |  | Proposed | 0 |  | Highly Unlikely | 0
Medium | 0 |  | Unscheduled | 0 |  | Unlikely | 0
High | 0 |  | Not Started | 0 |  | Possible | 0
Extreme | 0 |  | Review | 0 |  | Likely | 0
|  |  | Approved | 0 |  | Highly Likely | 0
|  |  | Ongoing | 0
|  |  | Finished | 0
|  |  | Paused | 0
|  |  | Overdue | 0
|  |  | Terminated | 0
Dashboard Data | [10 empty] | Overall Total Tasks
Quantity columns calculate automatically to populate dashboard charts; do not alter. | [10 empty] | 0
Unique Project ID | Proposed | Unscheduled | Not Started | Review | Approved | Ongoing | Finished | Paused | Overdue | Terminated | Total Tasks per Project
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
Number of Days Remaining = IF(PROJECTS2[[#This Row],[Expected Date of Completion]]="","–",(PROJECTS2[[#This Row],[Expected Date of Completion]]-TODAY()))

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.