## EXAMPLE - Selection Process
Vendor and Supplier Selection Process Timeline Gantt Template
PROJECT TITLE
PROJECT MANAGER |  | COMPANY NAME |  |  |  | DATE
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FIVE
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | PREPARE
1.1 | Assign Responsibility | Leon W | 2055-03-12 | 2055-03-15 | 4 | 100%
1.1.1 | Define Requirements and KPIs | Kylie R | 2055-03-15 | 2055-03-16 | 2 | 100%
1.2 | Draft RFP | Pete S | 2055-03-15 | 2055-03-21 | 7 | 90%
1.3 | Review RFP | Steve L | 2055-03-16 | 2055-03-22 | 7 | 40%
1.4 | Approve RFP | Allen W | 2055-03-17 | 2055-03-22 | 6 | 70%
2 | DISCOVER
2.1 | Research Potential Vendors and Suppliers | Steve L | 2055-03-24 | 2055-03-28 | 5 | 5%
2.2 | Distribute to Potential Vendors and Suppliers | Allen W | 2055-03-29 | 2055-04-02 | 5 | 30%
3 | EVALUATE
3.1 | Compare Potential Vendors or Suppliers | Pete S |  |  |  | 0%
3.2 | Select Top Vendors or Suppliers | Leon W |  |  |  | 0%
3.2.1 | Compare Qualifications | Kylie R |  |  |  | 0%
3.2.2 | Stakeholder Review | Kylie R |  |  |  | 0%
3.3 | Legal Review | Pete S |  |  |  | 0%
3.3.1 | Business Analysis and Review | Malik M |  |  |  | 0%
4 | SELECT
4.1 | Select Top 2-3 Vendors or Suppliers | Steve L |  |  |  | 0%
4.2 | Meet with Top 2-3 Vendors or Suppliers | Allen W |  |  |  | 0%
4.3 | Final Vendor Selection | Malik M |  |  |  | 0%
4.4 | Onboard | Malik M |  |  |  | 0%
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Selection Process
Vendor and Supplier Selection Process Timeline Gantt Template
PROJECT TITLE
PROJECT MANAGER |  | COMPANY NAME |  |  |  | DATE
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FIVE
TASK | TASK | TASK | START | DUE | DURATION | PCT OF TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
ID | TITLE | OWNER | DATE | DATE | IN DAYS | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1
1.1 | [5 empty] | 100%
1.2 | [5 empty] | 0%
1.3 | [5 empty] | 0%
1.4 | [5 empty] | 0%
1.5 | [5 empty] | 0%
1.6 | [5 empty] | 0%
1.7 | [5 empty] | 0%
2
2.1 | [5 empty] | 0%
2.2 | [5 empty] | 0%
2.3 | [5 empty] | 0%
2.4 | [5 empty] | 0%
2.5 | [5 empty] | 0%
2.6 | [5 empty] | 0%
2.7 | [5 empty] | 0%
2.8 | [5 empty] | 0%
3
3.1 | [5 empty] | 0%
3.2 | [5 empty] | 0%
3.3 | [5 empty] | 0%
3.4 | [5 empty] | 0%
3.5 | [5 empty] | 0%
3.6 | [5 empty] | 0%
4
4.1 | [5 empty] | 0%
4.2 | [5 empty] | 0%
4.3 | [5 empty] | 0%
4.4 | [5 empty] | 0%
4.5 | [5 empty] | 0%
4.6 | [5 empty] | 0%
5
5.1 | [5 empty] | 0%
5.2 | [5 empty] | 0%
5.3 | [5 empty] | 0%
5.4 | [5 empty] | 0%
5.5 | [5 empty] | 0%
5.6 | [5 empty] | 0%
5.7 | [5 empty] | 0%
MILESTONE 1
Description
MILESTONE 2
Description
MILESTONE 3
Description
MILESTONE 4
Description
MILESTONE 5
Description

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.