## EXAMPLE Scrum Board Sprint
Scrum Board Sprint Template Example
Current Date | Sprint Timeline | Total Estimated Hours |  | Total Hours Used |  | Total Hours Remaining
MM/DD/YY | MM/DD/YY - MM/DD/YY | 1163 |  | 666 |  | 497
Scrum Board | Enter the date of the first Monday and the subsequent dates will populate. >>> |  |  |  | 2035-01-01 | 2035-01-02 | 2035-01-03 | 2035-01-04 | 2035-01-05 | 2035-01-08 | 2035-01-09 | 2035-01-10 | 2035-01-11 | 2035-01-12 | 2035-01-15 | 2035-01-16 | 2035-01-17 | 2035-01-18 | 2035-01-19 | 2035-01-22 | 2035-01-23 | 2035-01-24 | 2035-01-25 | 2035-01-26 | 2035-01-29 | 2035-01-30 | 2035-01-31 | 2035-02-01 | 2035-02-02
Sprint Backlog | Assigned To | Estimated Hours | Hours Used (auto-populate) | Hours Remaining (auto-populate) | MON | TUES | WED | THUR | FRI | MON | TUES | WED | THUR | FRI | MON | TUES | WED | THUR | FRI | MON | TUES | WED | THUR | FRI | MON | TUES | WED | THUR | FRI
Story #1
Task | John K | 60 | 32 | 28 | 5 | 3 | 0 | 0 | 0 | 0 | 5 | 3 | 0 | 0 | 0 | 0 | 5 | 3 | 0 | 0 | 0 | 0 | 5 | 3 | 0 | 0 | 0 | 0 | 0
Task | Matthew M | 60 | 32 | 28 | 1 | 1 | 5 | 0 | 1 | 0 | 1 | 1 | 5 | 0 | 1 | 0 | 1 | 1 | 5 | 0 | 1 | 0 | 1 | 1 | 5 | 0 | 1 | 0 | 0
Task | Virginia W | 50 | 14 | 36 | 0.5 | 0 | 3 | 0 | 0 | 0 | 0.5 | 0 | 3 | 0 | 0 | 0 | 0.5 | 0 | 3 | 0 | 0 | 0 | 0.5 | 0 | 3 | 0 | 0 | 0 | 0
Task | Jeff P | 42 | 28 | 14 | 1 | 2 | 3 | 1 | 0 | 0 | 1 | 2 | 3 | 1 | 0 | 0 | 1 | 2 | 3 | 1 | 0 | 0 | 1 | 2 | 3 | 1 | 0 | 0 | 0
Story #2
Task |  | 34 | 26 | 8 | 3 | 0.5 | 0.5 | 0 | 0 | 2 | 3 | 0.5 | 0.5 | 0 | 0 | 2 | 3 | 0.5 | 0.5 | 0 | 0 | 2 | 3 | 0.5 | 0.5 | 0 | 0 | 2 | 2
Task |  | 70 | 52 | 18 | 5 | 5 | 1 | 1 | 1 | 0 | 5 | 5 | 1 | 1 | 1 | 0 | 5 | 5 | 1 | 1 | 1 | 0 | 5 | 5 | 1 | 1 | 1 | 0 | 0
Task |  | 50 | 37 | 13 | 2 | 5 | 0 | 1 | 0 | 1 | 2 | 5 | 0 | 1 | 0 | 1 | 2 | 5 | 0 | 1 | 0 | 1 | 2 | 5 | 0 | 1 | 0 | 1 | 1
Task |  | 80 | 53 | 27 | 5 | 0 | 5 | 1 | 0 | 1 | 5 | 0 | 0 | 1 | 0 | 1 | 5 | 0 | 5 | 1 | 0 | 1 | 5 | 9 | 5 | 1 | 0 | 1 | 1
Story #3
Task |  | 80 | 24 | 56 | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0
Task |  | 60 | 40 | 20 | 1 | 3 | 3 | 3 | 0 | 0 | 1 | 3 | 3 | 3 | 0 | 0 | 1 | 3 | 3 | 3 | 0 | 0 | 1 | 3 | 3 | 3 | 0 | 0 | 0
Task |  | 20 | 16 | 4 | 1 | 0.5 | 0.5 | 1 | 1 | 0 | 1 | 0.5 | 0.5 | 1 | 1 | 0 | 1 | 0.5 | 0.5 | 1 | 1 | 0 | 1 | 0.5 | 0.5 | 1 | 1 | 0 | 0
Task |  | 20 | 17 | 3 | 0.5 | 0 | 0 | 0 | 0 | 3 | 0.5 | 0 | 0 | 0 | 0 | 3 | 0.5 | 0 | 0 | 0 | 0 | 3 | 0.5 | 0 | 0 | 0 | 0 | 3 | 3
Story #4
Task |  | 80 | 40 | 40 | 4 | 2 | 2 | 1 | 1 | 0 | 4 | 2 | 2 | 1 | 1 | 0 | 4 | 2 | 2 | 1 | 1 | 0 | 4 | 2 | 2 | 1 | 1 | 0 | 0
Task |  | 80 | 57 | 23 | 6 | 3 | 3 | 0 | 1 | 1 | 0 | 3 | 0 | 3 | 1 | 1 | 6 | 3 | 3 | 3 | 1 | 1 | 6 | 3 | 3 | 3 | 1 | 1 | 1
Task |  | 80 | 49 | 31 | 2 | 8 | 8 | 1 | 0 | 1 | 2 | 8 | 8 | 1 | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 1 | 2 | 0 | 0 | 1 | 0 | 1 | 1
Task |  | 15 | 6 | 9 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0
Story #5
Task |  | 32 | 23 | 9 | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 1 | 1 | 0.5 | 1 | 1 | 1
Task |  | 80 | 44 | 36 | 6 | 6 | 0.5 | 3 | 0 | 0 | 0 | 0 | 0.5 | 3 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 6 | 6 | 0.5 | 3 | 9 | 0 | 0
Task |  | 120 | 61 | 59 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 2 | 2 | 2 | 3 | 3 | 3 | 2 | 2 | 4 | 3 | 3 | 3 | 3
Task |  | 50 | 15 | 35 | 0.5 | 0.5 | 1 | 0.5 | 0 | 1 | 0.5 | 0.5 | 1 | 0.5 | 0 | 1 | 0.5 | 0.5 | 1 | 0.5 | 0 | 1 | 0.5 | 0.5 | 1 | 0.5 | 0 | 1 | 1
Totals |  | 1163 | 666 | 497
Totals - Breakdown |  | Estimated Hours | Hours Used (auto-populate) | Hours Remaining (auto-populate)
| Story 1 Totals | 212 | 106 | 106
| Story 2 Totals | 234 | 168 | 66
| Story 3 Totals | 180 | 97 | 83
| Story 4 Totals | 255 | 152 | 103
| Story 5 Totals | 282 | 143 | 139
CLICK HERE TO CREATE IN SMARTSHEET | bar: 2035-01-01 to 2035-01-23

## Scrum Board Sprint
Scrum Board Sprint Template
Current Date | Sprint Timeline | Total Estimated Hours |  | Total Hours Used |  | Total Hours Remaining
MM/DD/YY | MM/DD/YY - MM/DD/YY | 0 |  | 0 |  | 0
Scrum Board | Enter the date of the first Monday and the subsequent dates will populate. >>> |  |  |  | 2035-01-01 | 2035-01-02 | 2035-01-03 | 2035-01-04 | 2035-01-05 | 2035-01-08 | 2035-01-09 | 2035-01-10 | 2035-01-11 | 2035-01-12 | 2035-01-15 | 2035-01-16 | 2035-01-17 | 2035-01-18 | 2035-01-19 | 2035-01-22 | 2035-01-23 | 2035-01-24 | 2035-01-25 | 2035-01-26 | 2035-01-29 | 2035-01-30 | 2035-01-31 | 2035-02-01 | 2035-02-02
Sprint Backlog | Assigned To | Estimated Hours | Hours Used (auto-populate) | Hours Remaining (auto-populate) | MON | TUES | WED | THUR | FRI | MON | TUES | WED | THUR | FRI | MON | TUES | WED | THUR | FRI | MON | TUES | WED | THUR | FRI | MON | TUES | WED | THUR | FRI
Story #1
Task |  | 0 | 0 | 0 | 2035-01-01: 0; 2035-01-02: 0; 2035-01-03: 0; 2035-01-04: 0; 2035-01-05: 0
Task |  | 0 | 0 | 0 | 2035-01-01: 0; 2035-01-02: 0; 2035-01-03: 0; 2035-01-04: 0; 2035-01-05: 0
Task |  | 0 | 0 | 0
Task |  | 0 | 0 | 0
Story #2
Task |  |  | 0 | 0
Task |  |  | 0 | 0
Task |  |  | 0 | 0
Task |  |  | 0 | 0
Story #3
Task |  |  | 0 | 0
Task |  |  | 0 | 0
Task |  |  | 0 | 0
Task |  |  | 0 | 0
Story #4
Task |  |  | 0 | 0
Task |  |  | 0 | 0
Task |  |  | 0 | 0
Task |  |  | 0 | 0
Story #5
Task |  |  | 0 | 0
Task |  |  | 0 | 0
Task |  |  | 0 | 0
Task |  |  | 0 | 0
Totals |  | 0 | 0 | 0
Totals - Breakdown |  | Estimated Hours | Hours Used (auto-populate) | Hours Remaining (auto-populate)
| Story 1 Totals | 0 | 0 | 0
| Story 2 Totals | 0 | 0 | 0
| Story 3 Totals | 0 | 0 | 0
| Story 4 Totals | 0 | 0 | 0
| Story 5 Totals | 0 | 0 | 0

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.