## Scrum Board with Burndown Chart
Scrum Board Template with Burndown Chart
Project Name | Name |  |  | Date | MM/DD/YY |  |  | Sprint Timeline |  | MM/DD/YY - MM/DD/YY
User Story | Story Points | Assigned To | Priority | Status | Day 1 |  | Day 2 |  | Day 3 |  | Day 4 |  | Day 5
[5 empty] | Estimated Hours | Actual Hours | Estimated Hours | Actual Hours | Estimated Hours | Actual Hours | Estimated Hours | Actual Hours | Estimated Hours | Actual Hours
User Story #1 | 8
Task |  | Name | Needs Attention | Complete | 5 | 6 | 4 | 2 | 3 | 0.5 | 2 | 0 | 1 | 0
Task |  | Name | Delayed or Blocked | In Progress | 7 | 4 | 6 | 1 | 5 | 3 | 4 | 0 | 3 | 1
Task |  | Name |  | Not Started | 0.5 | 5 | 0 | 1 | 3 | 2 | 0 | 0 | 1 | 0
Task |  |  |  | Needs Review | 1 | 2 | 2 | 1 | 3 | 3 | 1 | 1 | 1 | 0
User Story #2 | 1
Task |  |  |  | Approved | 3 | 2 | 0.5 | 1 | 0.5 | 0 | 0 | 0.5 | 3 | 0
Task |  |  |  | Overdue | 5 | 1 | 5 | 3 | 1 | 0 | 1 | 0.5 | 0 | 1
Task |  |  |  | On Hold | 2 | 2 | 5 | 3 | 0 | 2 | 1 | 0.5 | 0 | 0
Task |  |  |  |  | 5 | 2 | 9 | 5 | 5 | 3 | 1 | 0 | 0 | 0
User Story #3 | 5
Task |  |  |  |  | 6 | 4 | 0 | 0 | 0 | 0.5 | 0 | 0 | 2 | 0
Task |  |  |  |  | 1 | 1 | 3 | 1 | 3 | 1.5 | 3 | 4 | 0 | 0
Task |  |  |  |  | 1 | 1 | 0.5 | 0 | 0.5 | 0.5 | 1 | 0.5 | 0 | 1
Task |  |  |  |  | 0.5 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0.5 | 0
User Story #4 | 8
Task |  |  |  |  | 4 | 3 | 2 | 1 | 2 | 2 | 1 | 0 | 1 | 1
Task |  |  |  |  | 6 | 2 | 3 | 2 | 3 | 1 | 3 | 1 | 1 | 1
Task |  |  |  |  | 2 | 1 | 8 | 6 | 8 | 7 | 1 | 1 | 0 | 0
Task |  |  |  |  | 0.5 | 0 | 0.5 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | 0
User Story #5 | 3
Task |  |  |  |  | 1 | 0 | 1 | 4 | 1 | 0.5 | 0.5 | 0 | 1 | 1
Task |  |  |  |  | 6 | 5 | 6 | 3 | 0.5 | 0.5 | 3 | 2 | 6 | 9
Task |  |  |  |  | 9 | 6 | 9 | 7 | 4 | 3 | 3 | 1 | 5 | 3
Task |  |  |  |  | 0.5 | 0 | 0.5 | 1 | 1 | 0.5 | 0.5 | 0 | 0 | 0
TOTAL |  |  |  |  | 66 | 47 | 65 | 44 | 44 | 31 | 26 | 12 | 25.5 | 18
CLICK HERE TO CREATE IN SMARTSHEET

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
Priority | Status
Moving Smoothly | Not Started
Needs Attention | In Progress
Delayed or Blocked | Complete
Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.