## EX - Project Collaboration Plan
Project Collaboration Plan
This tab contains example content. Use the BLANK tab to begin building your project collaboration plan.
Project Title |  | Project Manager |  | Start Date | End Date | Duration
Project Alpha |  | Vada M. |  | 2025-01-02 | 2025-03-26 | 84
WBS No. | Task Name | Status | Assigned To | Start Date | End Date | Duration in Days | Comments
1 | Project Conception and Initiation | Complete |  | 2025-01-02 | 2025-01-08 | 7
1.1 | Project Kickoff Meeting | Complete |  | 2025-01-02 | 2025-01-02 | 1
1.2 | Scope and Goal Setting | Complete |  | 2025-01-03 | 2025-01-08 | 6
1.3 | Communication Plan | In Progress |  | 2025-01-04 | 2025-01-08 | 5
2 | Project Definition and Planning | In Progress |  | 2025-01-08 | 2025-01-26 | 19
2.1 | Project Charter | Complete |  | 2025-01-08 | 2025-01-16 | 9
2.1.1 | – Project Charter Revisions | Complete |  | 2025-01-18 | 2025-01-24 | 7
2.2 | Work Breakdown Structure (WBS) | In Progress |  | 2025-01-10 | 2025-01-11 | 2
2.3 | Role and Responsibilities + RACI Matrix | In Progress |  | 2025-01-12 | 2025-01-18 | 7
2.3.1 | – Research | In Progress |  | 2025-01-12 | 2025-01-15 | 4
2.3.2 | – Projections | Approved |  | 2025-01-16 | 2025-01-18 | 3
2.3.3 | – Stakeholders | Needs Review |  | 2025-01-18 | 2025-01-18 | 1
2.3.4 | – Budget | Overdue |  | 2025-01-18 | 2025-01-24 | 7
2.3.5 | – Risk Management | On Hold |  | 2025-01-20 | 2025-01-26 | 7
3 | Project Launch and Execution | In Progress |  | 2025-01-29 | 2025-02-26 | 29
3.1 | Collaborative Work Sessions | In Progress |  | 2025-01-29 | 2025-02-18 | 21
3.2 | Halftime Review | Not Started |  | 2025-02-18 | 2025-02-20 | 3
3.3 | Standup Meetings | In Progress |  | 2025-02-18 | 2025-02-20 | 3
3.4 | Feedback | Approved |  | 2025-02-18 | 2025-02-20 | 3
3.4.1 | – Status and Tracking | Not Started |  | 2025-02-18 | 2025-02-20 | 3
3.4.2 | – KPIs | Needs Review |  | 2025-02-18 | 2025-02-23 | 6
3.4.2.1 | –– Monitoring | Not Started |  | 2025-02-18 | 2025-02-26 | 9
3.4.2.2 | –– Forecasts | Needs Review |  | 2025-02-21 | 2025-02-23 | 3
3.4.3 | – Project Updates | Not Started |  | 2025-02-22 | 2025-02-25 | 4
3.4.3.1 | –– Chart Updates | Not Started |  | 2025-02-25 | 2025-02-26 | 2
4 | Project Performance and Monitoring | In Progress |  | 2025-02-25 | 2025-03-26 | 30
4.1 | Project Objectives | In Progress |  | 2025-02-25 | 2025-02-28 | 4
4.2 | Quality Deliverables | On Hold |  | 2025-02-26 | 2025-03-03 | 6
4.3 | Project Review | Not Started |  | 2025-02-26 | 2025-03-03 | 6
4.3.1 | – Effort and Cost Tracking | Not Started |  | 2025-02-25 | 2025-03-06 | 10
4.3.2 | – Project Performance | Not Started |  | 2025-03-03 | 2025-03-26 | 24
5 | Project Review | Not Started |  | 2025-03-26 | 2025-04-01 | 7
5.1 | Final Deliverables Check | Not Started |  | 2025-03-26 | 2025-03-27 | 2
5.2 | Update Best Practices | Not Started |  | 2025-03-27 | 2025-03-30 | 4
5.3 | Conduct Lessons-Learned Session | Not Started |  | 2025-04-01 | 2025-04-01 | 1
CLICK HERE TO CREATE IN SMARTSHEET
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## BLANK - Project Collab Plan
Project Collaboration Plan
Project Title |  | Project Manager |  | Start Date | End Date | Duration
1
WBS No. | Task Name | Status | Assigned To | Start Date | End Date | Duration in Days | Comments
1 | Project Conception and Initiation |  |  |  |  | 1
1.1 | Project Kickoff Meeting |  |  |  |  | 1
1.2 | Scope and Goal Setting |  |  |  |  | 1
1.3 | Communication Plan |  |  |  |  | 1
2 | Project Definition and Planning |  |  |  |  | 1
2.1 | Project Charter |  |  |  |  | 1
2.1.1 | – Project Charter Revisions |  |  |  |  | 1
2.2 | Work Breakdown Structure (WBS) |  |  |  |  | 1
2.3 | Role and Responsibilities + RACI Matrix |  |  |  |  | 1
2.3.1 | – Research |  |  |  |  | 1
2.3.2 | – Projections |  |  |  |  | 1
2.3.3 | – Stakeholders |  |  |  |  | 1
2.3.4 | – Budget |  |  |  |  | 1
2.3.5 | – Risk Management |  |  |  |  | 1
3 | Project Launch and Execution |  |  |  |  | 1
3.1 | Collaborative Work Sessions |  |  |  |  | 1
3.2 | Halftime Review |  |  |  |  | 1
3.3 | Standup Meetings |  |  |  |  | 1
3.4 | Feedback |  |  |  |  | 1
3.4.1 | – Status and Tracking |  |  |  |  | 1
3.4.2 | – KPIs |  |  |  |  | 1
3.4.2.1 | –– Monitoring |  |  |  |  | 1
3.4.2.2 | –– Forecasts |  |  |  |  | 1
3.4.3 | – Project Updates |  |  |  |  | 1
3.4.3.1 | –– Chart Updates |  |  |  |  | 1
4 | Project Performance and Monitoring |  |  |  |  | 1
4.1 | Project Objectives |  |  |  |  | 1
4.2 | Quality Deliverables |  |  |  |  | 1
4.3 | Project Review |  |  |  |  | 1
4.3.1 | – Effort and Cost Tracking |  |  |  |  | 1
4.3.2 | – Project Performance |  |  |  |  | 1
5 | Project Review |  |  |  |  | 1
5.1 | Final Deliverables Check |  |  |  |  | 1
5.2 | Update Best Practices |  |  |  |  | 1
5.3 | Conduct Lessons-Learned Session |  |  |  |  | 1
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.