## EXAMPLE - Project Dashboard
Project Dashboard Template
Campaign Name |  |  |  | Date | Project Status | % Complete
Project Alpha |  |  |  | 00/00/00 | ON TRACK | 50%
Task Timeline
DASHBOARD DATA
TASK TABLE
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS
Set Kick-Off Meeting | Alex B. | 2025-01-02 | 2025-01-08 | 7 | Complete | High
Agree on Objectives | Frank C. | 2025-01-04 | 2025-01-11 | 8 | Complete | High
Detailed Requests | Jacob S. | 2025-01-07 | 2025-01-11 | 5 | Complete | High
Hardware Requests | Jacob S. | 2025-01-10 | 2025-01-15 | 6 | In Progress | Low
Final Resource Plan | Jacob S. | 2025-01-13 | 2025-01-20 | 8 | On Hold | Low
Staffing | Alex B. | 2025-01-16 | 2025-01-29 | 14 | Overdue | High
Technical Requests | Frank C. | 2025-01-19 | 2025-02-01 | 14 | In Progress | Medium
Testing | Kennedy K. | 2025-01-22 | 2025-02-09 | 19 | In Progress | High
Dev. Complete | Jacob S. | 2025-01-25 | 2025-02-05 | 12 | In Progress | Medium
Hardware Configuration | Alex B. | 2025-01-28 | 2025-02-06 | 10 | On Hold | High
System Testing | Kennedy K. | 2025-01-31 | 2025-02-02 | 3 | Not Started | Medium
LAUNCH |  | 2025-02-03 | 2025-02-04 | 2 | Not Started | Medium
Task Status % |  |  |  | Budget
STATUS | COUNT | % |  | PLANNED | 120000
Not Started | 2 | 16.67% |  | ACTUAL | 111000
In Progress | 4 | 33.33%
Complete | 3 | 25%
Needs Review | 0 | 0%
Approved | 0 | 0%
Overdue | 1 | 8.333%
On Hold | 2 | 16.67%
TOTAL | 12 | 100%
Task Priority % |  |  |  | Pending Items
PRIORITY | COUNT | % |  | Decisions | 5
Low | 2 | 16.67% |  | Actions | 2
Medium | 4 | 33.33% |  | Change Requests | 4
High | 6 | 50%
TOTAL | 12 | 100%
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Project Dashboard
Project Dashboard Template
Campaign Name |  |  |  | Date | Project Status | % Complete
|  |  |  | 00/00/00 | ON TRACK | 0% | Enter DASHBOARD DATA in the tables beginning at row 8. Dashboard graphics will automatically populate.
Task Timeline
DASHBOARD DATA
Task Table
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS
Set Kick-Off Meeting |  |  |  | 0
Agree on Objectives |  |  |  | 0
Detailed Requests |  |  |  | 0
Hardware Requests |  |  |  | 0
Final Resource Plan |  |  |  | 0
Staffing |  |  |  | 0
Technical Requests |  |  |  | 0
Testing |  |  |  | 0
Dev. Complete |  |  |  | 0
Hardware Configuration |  |  |  | 0
System Testing |  |  |  | 0
Task 12 |  |  |  | 0
Task 13 |  |  |  | 0
Task 14 |  |  |  | 0
Task 15 |  |  |  | 0
Task 16 |  |  |  | 0
Task 17 |  |  |  | 0
Task 18 |  |  |  | 0
Task 19 |  |  |  | 0
Task 20 |  |  |  | 0
LAUNCH |  |  |  | 0
Task Status % |  |  |  | Budget
STATUS | COUNT | % |  | PLANNED | 0
Not Started | 0 |  |  | ACTUAL | 0
In Progress | 0
Complete | 0
Needs Review | 0
Approved | 0
Overdue | 0
On Hold | 0
TOTAL | 0 | 0%
Task Priority % |  |  |  | Pending Items
PRIORITY | COUNT | % |  | Decisions | 0
Low | 0 |  |  | Actions | 0
Medium | 0 |  |  | Change Requests | 0
High | 0
TOTAL | 0 | 0%
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.