## EXAMPLE - Contractor Estimate
Contractor Estimate Template
This tab contains example data. To begin building your contractor estimate, use the BLANK tab.
––––––––––– Projected –––––––––––
Job Title |  |  |  |  | Project Manager |  | Start Date | End Date
Project Alpha |  |  |  |  | Carmen Robertson |  | 03/02/20XX | 11/14/20XX
Location
| PROJECTED TOTAL | ACTUAL TOTAL | VARIANCE |  |  |  | CURRENT PAID | AMOUNT DUE
| 21300 | 18975 | -2325 |  |  |  | 12300 | 6675
CATEGORY & ITEMS | PROJECTED SUBTOTAL | ACTUAL SUBTOTAL | VARIANCE | PARTY RESPONSIBLE Vendor, Contractor, etc. | STATUS | % OF TASK COMPLETE | CURRENT PAID | AMOUNT DUE | COMMENTS
PLANNING | 15200 | 13800 | -1400 |  |  | 50% | 12300 | 1500
Admin Fees | 1850 | 1500 | -350 |  | Not Started | 0% | 0 | 1500
Engineering | 3500 | 3200 | -300 |  | In Progress | 50% | 3200 | 0
Financing Costs | 3800 | 3000 | -800 |  | Complete | 100% | 3000 | 0
Legal | 1800 | 2600 | 800 |  | Needs Review | 85% | 2600 | 0
Permit - Building | 300 | 300 | 0 |  | Approved | 65% | 300 | 0
Permit - Environmental | 300 | 300 | 0 |  | Overdue | 45% | 300 | 0
Permit - Zoning | 300 | 300 | 0 |  | On Hold | 25% | 300 | 0
Plans + Specs | 2300 | 1800 | -500 |  |  | 0% | 1800 | 0
Review | 600 | 500 | -100 |  |  | 0% | 500 | 0
Survey | 450 | 300 | -150 |  |  | 0% | 300 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
SITE PREP | 6100 | 5175 | -925 |  |  | 0% | 0 | 5175
Dumpster / Waste Removal | 1400 | 1200 | -200 |  |  | 0% | 0 | 1200
Equipment Rental | 3500 | 2875 | -625 |  |  | 0% | 0 | 2875
Lot Clearing | 1200 | 1100 | -100 |  |  | 0% | 0 | 1100
Portable Restroom Facilities |  |  | 0 |  |  | 0% | 0 | 0
Remodel - Demo |  |  | 0 |  |  | 0% | 0 | 0
Remodel - Dust Control |  |  | 0 |  |  | 0% | 0 | 0
Remodel - Jacking + Shoring |  |  | 0 |  |  | 0% | 0 | 0
Remodel - Surface Protection |  |  | 0 |  |  | 0% | 0 | 0
Scaffolding Rental |  |  | 0 |  |  | 0% | 0 | 0
Site Access |  |  | 0 |  |  | 0% | 0 | 0
Site Security |  |  | 0 |  |  | 0% | 0 | 0
Site Storage |  |  | 0 |  |  | 0% | 0 | 0
Temporary Heat |  |  | 0 |  |  | 0% | 0 | 0
Temporary Power |  |  | 0 |  |  | 0% | 0 | 0
Tool Rental |  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
EARTHWORK / EXCAVATION | 0 | 0 | 0 |  |  | 0% | 0 | 0
Backfill |  |  | 0 |  |  | 0% | 0 | 0
Blasting |  |  | 0 |  |  | 0% | 0 | 0
Compaction |  |  | 0 |  |  | 0% | 0 | 0
Culverts |  |  | 0 |  |  | 0% | 0 | 0
Curtain Drains |  |  | 0 |  |  | 0% | 0 | 0
Cut + Fill |  |  | 0 |  |  | 0% | 0 | 0
Dirt + Stone Removal |  |  | 0 |  |  | 0% | 0 | 0
Finish Grading |  |  | 0 |  |  | 0% | 0 | 0
Foundation - Excavation |  |  | 0 |  |  | 0% | 0 | 0
Foundation - Footing Drains |  |  | 0 |  |  | 0% | 0 | 0
Ponds |  |  | 0 |  |  | 0% | 0 | 0
Retaining Walls |  |  | 0 |  |  | 0% | 0 | 0
Rough Grading |  |  | 0 |  |  | 0% | 0 | 0
Seeding / Sodding |  |  | 0 |  |  | 0% | 0 | 0
Site Drainage - Additional |  |  | 0 |  |  | 0% | 0 | 0
Swales |  |  | 0 |  |  | 0% | 0 | 0
Top Soil |  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
UTILITIES | 0 | 0 | 0 |  |  | 0% | 0 | 0
Electrical - Connection |  |  | 0 |  |  | 0% | 0 | 0
Electrical - Install |  |  | 0 |  |  | 0% | 0 | 0
Electrical - Permit |  |  | 0 |  |  | 0% | 0 | 0
Gas - Connection |  |  | 0 |  |  | 0% | 0 | 0
Gas - Hookup |  |  | 0 |  |  | 0% | 0 | 0
Gas - Permit |  |  | 0 |  |  | 0% | 0 | 0
Oil Tank Install |  |  | 0 |  |  | 0% | 0 | 0
Sewer - Tap Fees & Hookup |  |  | 0 |  |  | 0% | 0 | 0
Telecom - Hookup |  |  | 0 |  |  | 0% | 0 | 0
Telecom - Install |  |  | 0 |  |  | 0% | 0 | 0
Water - Tap Fees & Hookup |  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
WATER + SEWER | 0 | 0 | 0 |  |  | 0% | 0 | 0
High Water Table Dewatering |  |  | 0 |  |  | 0% | 0 | 0
Perc Test |  |  | 0 |  |  | 0% | 0 | 0
Plumbing to House |  |  | 0 |  |  | 0% | 0 | 0
Pressure Tank |  |  | 0 |  |  | 0% | 0 | 0
Pump |  |  | 0 |  |  | 0% | 0 | 0
Septic - Design |  |  | 0 |  |  | 0% | 0 | 0
Septic - Fees |  |  | 0 |  |  | 0% | 0 | 0
Septic - Inspection |  |  | 0 |  |  | 0% | 0 | 0
Septic - Permits |  |  | 0 |  |  | 0% | 0 | 0
Septic - Tie to House |  |  | 0 |  |  | 0% | 0 | 0
Soil Test |  |  | 0 |  |  | 0% | 0 | 0
Trenching |  |  | 0 |  |  | 0% | 0 | 0
Well |  |  | 0 |  |  | 0% | 0 | 0
Well - Fees |  |  | 0 |  |  | 0% | 0 | 0
Well - Permits |  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
FOUNDATION | 0 | 0 | 0 |  |  | 0% | 0 | 0
Anchor Bolts |  |  | 0 |  |  | 0% | 0 | 0
Bulkheads |  |  | 0 |  |  | 0% | 0 | 0
Crawlspace Vapor Barrier |  |  | 0 |  |  | 0% | 0 | 0
Crawlspace Vents |  |  | 0 |  |  | 0% | 0 | 0
Dam Proofing |  |  | 0 |  |  | 0% | 0 | 0
Exterior Foundation Insulation |  |  | 0 |  |  | 0% | 0 | 0
Exterior Insulation Coating |  |  | 0 |  |  | 0% | 0 | 0
Footings |  |  | 0 |  |  | 0% | 0 | 0
Foundation - Drain Board |  |  | 0 |  |  | 0% | 0 | 0
Foundation - Walls |  |  | 0 |  |  | 0% | 0 | 0
Foundation - Windows |  |  | 0 |  |  | 0% | 0 | 0
Grade Beams |  |  | 0 |  |  | 0% | 0 | 0
Hold Downs |  |  | 0 |  |  | 0% | 0 | 0
Pads |  |  | 0 |  |  | 0% | 0 | 0
Piers |  |  | 0 |  |  | 0% | 0 | 0
Slab - Basement |  |  | 0 |  |  | 0% | 0 | 0
Slab - Foundation |  |  | 0 |  |  | 0% | 0 | 0
Slab - Garage |  |  | 0 |  |  | 0% | 0 | 0
Slab Insulation |  |  | 0 |  |  | 0% | 0 | 0
Steel Reinforcing |  |  | 0 |  |  | 0% | 0 | 0
Stem Walls |  |  | 0 |  |  | 0% | 0 | 0
Sub-Slab Vapor Barrier |  |  | 0 |  |  | 0% | 0 | 0
Sump Pump |  |  | 0 |  |  | 0% | 0 | 0
Waterproofing |  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
ROUGH FRAMING | 0 | 0 | 0 |  |  | 0% | 0 | 0
Exterior Walls |  |  | 0 |  |  | 0% | 0 | 0
Fasteners / Nails / Screws |  |  | 0 |  |  | 0% | 0 | 0
Floor Framing |  |  | 0 |  |  | 0% | 0 | 0
Interior Walls |  |  | 0 |  |  | 0% | 0 | 0
Lally Columns |  |  | 0 |  |  | 0% | 0 | 0
Plaster / Drywall Prep |  |  | 0 |  |  | 0% | 0 | 0
Roof Framing / Trusses |  |  | 0 |  |  | 0% | 0 | 0
Rough Stairs |  |  | 0 |  |  | 0% | 0 | 0
Sheathing |  |  | 0 |  |  | 0% | 0 | 0
Sill + Seal |  |  | 0 |  |  | 0% | 0 | 0
Steel / Wood Carrying Beam |  |  | 0 |  |  | 0% | 0 | 0
Steel Framing Connectors |  |  | 0 |  |  | 0% | 0 | 0
Sub-Fascia |  |  | 0 |  |  | 0% | 0 | 0
Subflooring |  |  | 0 |  |  | 0% | 0 | 0
Labor Costs |  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
WINDOWS + DOORS (Exterior) | 0 | 0 | 0 |  |  | 0% | 0 | 0
Exterior Door - Frames + Sills |  |  | 0 |  |  | 0% | 0 | 0
Exterior Door - Hardware |  |  | 0 |  |  | 0% | 0 | 0
Exterior Door - Prehung |  |  | 0 |  |  | 0% | 0 | 0
Exterior Door - Slabs |  |  | 0 |  |  | 0% | 0 | 0
Garage Doors |  |  | 0 |  |  | 0% | 0 | 0
Membrane + Flashing |  |  | 0 |  |  | 0% | 0 | 0
Sidelights |  |  | 0 |  |  | 0% | 0 | 0
Sliding / Hinged Doors |  |  | 0 |  |  | 0% | 0 | 0
Transoms |  |  | 0 |  |  | 0% | 0 | 0
Windows |  |  | 0 |  |  | 0% | 0 | 0
Labor Costs |  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
FINISH - EXTERIOR | 0 | 0 | 0 |  |  | 0% | 0 | 0
Foam Sheathing |  |  | 0 |  |  | 0% | 0 | 0
Weather Barrier |  |  | 0 |  |  | 0% | 0 | 0
Membrane + Flashing |  |  | 0 |  |  | 0% | 0 | 0
Siding |  |  | 0 |  |  | 0% | 0 | 0
Veneer |  |  | 0 |  |  | 0% | 0 | 0
Stucco |  |  | 0 |  |  | 0% | 0 | 0
Fascia |  |  | 0 |  |  | 0% | 0 | 0
Soffit |  |  | 0 |  |  | 0% | 0 | 0
Frieze |  |  | 0 |  |  | 0% | 0 | 0
Corner Boards |  |  | 0 |  |  | 0% | 0 | 0
Water Table |  |  | 0 |  |  | 0% | 0 | 0
Soffit / Gable Vents |  |  | 0 |  |  | 0% | 0 | 0
Trim - Windows |  |  | 0 |  |  | 0% | 0 | 0
Trim - Doors |  |  | 0 |  |  | 0% | 0 | 0
Trim - Finishing |  |  | 0 |  |  | 0% | 0 | 0
Stairs |  |  | 0 |  |  | 0% | 0 | 0
Landing |  |  | 0 |  |  | 0% | 0 | 0
Paint |  |  | 0 |  |  | 0% | 0 | 0
Stain |  |  | 0 |  |  | 0% | 0 | 0
Caulk |  |  | 0 |  |  | 0% | 0 | 0
Labor Costs |  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
ROOFING | 0 | 0 | 0 |  |  | 0% | 0 | 0
Drip Edge |  |  | 0 |  |  | 0% | 0 | 0
Gutters + Downspouts |  |  | 0 |  |  | 0% | 0 | 0
Installation / Labor |  |  | 0 |  |  | 0% | 0 | 0
Membrane + Flashing |  |  | 0 |  |  | 0% | 0 | 0
Ridge & Roof Vents |  |  | 0 |  |  | 0% | 0 | 0
Skylights |  |  | 0 |  |  | 0% | 0 | 0
Underlayment |  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
MASONRY / PAVING | 0 | 0 | 0 |  |  | 0% | 0 | 0
Driveway |  |  | 0 |  |  | 0% | 0 | 0
Walkways |  |  | 0 |  |  | 0% | 0 | 0
Chimneys |  |  | 0 |  |  | 0% | 0 | 0
Stairs - Exterior |  |  | 0 |  |  | 0% | 0 | 0
Patios |  |  | 0 |  |  | 0% | 0 | 0
Fireplaces + Hearths |  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
PORCHES + DECKS | 0 | 0 | 0 |  |  | 0% | 0 | 0
Porch - Open |  |  | 0 |  |  | 0% | 0 | 0
Porch - Screened |  |  | 0 |  |  | 0% | 0 | 0
Deck - Composite |  |  | 0 |  |  | 0% | 0 | 0
Deck - Wood |  |  | 0 |  |  | 0% | 0 | 0
Fencing |  |  | 0 |  |  | 0% | 0 | 0
Railings |  |  | 0 |  |  | 0% | 0 | 0
Outdoor Built-Ins |  |  | 0 |  |  | 0% | 0 | 0
Additional Structures |  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
INSULATION + AIR SEALING | 0 | 0 | 0 |  |  | 0% | 0 | 0
Air Sealing |  |  | 0 |  |  | 0% | 0 | 0
Blower Door |  |  | 0 |  |  | 0% | 0 | 0
Infrared |  |  | 0 |  |  | 0% | 0 | 0
Insulation - Basement Interior |  |  | 0 |  |  | 0% | 0 | 0
Insulation - Crawlspace |  |  | 0 |  |  | 0% | 0 | 0
Insulation - Foam Board |  |  | 0 |  |  | 0% | 0 | 0
Insulation - Roof / Attic |  |  | 0 |  |  | 0% | 0 | 0
Insulation - Spray Foam |  |  | 0 |  |  | 0% | 0 | 0
Insulation - Wall Cavity |  |  | 0 |  |  | 0% | 0 | 0
Roof / Eave Baffles |  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
PLUMBING | 0 | 0 | 0 |  |  | 0% | 0 | 0
Drain |  |  | 0 |  |  | 0% | 0 | 0
Waste |  |  | 0 |  |  | 0% | 0 | 0
Vent |  |  | 0 |  |  | 0% | 0 | 0
Piping - Water Supply |  |  | 0 |  |  | 0% | 0 | 0
Piping - Gas |  |  | 0 |  |  | 0% | 0 | 0
Water Heater |  |  | 0 |  |  | 0% | 0 | 0
Water Treatment |  |  | 0 |  |  | 0% | 0 | 0
Toilets |  |  | 0 |  |  | 0% | 0 | 0
Tubs |  |  | 0 |  |  | 0% | 0 | 0
Sinks |  |  | 0 |  |  | 0% | 0 | 0
Showers |  |  | 0 |  |  | 0% | 0 | 0
Faucets |  |  | 0 |  |  | 0% | 0 | 0
Mixing Valves |  |  | 0 |  |  | 0% | 0 | 0
Shower Heads |  |  | 0 |  |  | 0% | 0 | 0
Disposal |  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
ELECTRICAL | 0 | 0 | 0 |  |  | 0% | 0 | 0
Service Panels |  |  | 0 |  |  | 0% | 0 | 0
Sub-Panels |  |  | 0 |  |  | 0% | 0 | 0
Rough Wiring |  |  | 0 |  |  | 0% | 0 | 0
Phone / Cable / Internet Wiring |  |  | 0 |  |  | 0% | 0 | 0
Lighting Fixtures |  |  | 0 |  |  | 0% | 0 | 0
Low-Voltage Fixtures |  |  | 0 |  |  | 0% | 0 | 0
Low-Voltage Transformers |  |  | 0 |  |  | 0% | 0 | 0
Outlets |  |  | 0 |  |  | 0% | 0 | 0
Switches |  |  | 0 |  |  | 0% | 0 | 0
Dimmers |  |  | 0 |  |  | 0% | 0 | 0
Lighting Control System |  |  | 0 |  |  | 0% | 0 | 0
Doorbell |  |  | 0 |  |  | 0% | 0 | 0
Smoke + CO2 Alarms |  |  | 0 |  |  | 0% | 0 | 0
Intercom System |  |  | 0 |  |  | 0% | 0 | 0
Security System |  |  | 0 |  |  | 0% | 0 | 0
Home Theater |  |  | 0 |  |  | 0% | 0 | 0
Home Entertainment System |  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
HVAC | 0 | 0 | 0 |  |  | 0% | 0 | 0
Air Handler |  |  | 0 |  |  | 0% | 0 | 0
Boiler |  |  | 0 |  |  | 0% | 0 | 0
Central AC |  |  | 0 |  |  | 0% | 0 | 0
Ductwork |  |  | 0 |  |  | 0% | 0 | 0
Furnace / Heat Pump |  |  | 0 |  |  | 0% | 0 | 0
Grilles |  |  | 0 |  |  | 0% | 0 | 0
HVAC Controls |  |  | 0 |  |  | 0% | 0 | 0
Piping |  |  | 0 |  |  | 0% | 0 | 0
Radiators |  |  | 0 |  |  | 0% | 0 | 0
Registers |  |  | 0 |  |  | 0% | 0 | 0
Solar Hot Water |  |  | 0 |  |  | 0% | 0 | 0
Whole-House Ventilation |  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
DRYWALL + PLASTER | 0 | 0 | 0 |  |  | 0% | 0 | 0
Walls |  |  | 0 |  |  | 0% | 0 | 0
Ceilings |  |  | 0 |  |  | 0% | 0 | 0
Soffits |  |  | 0 |  |  | 0% | 0 | 0
Decorative Plaster |  |  | 0 |  |  | 0% | 0 | 0
Labor Costs |  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
FINISH - INTERIOR | 0 | 0 | 0 |  |  | 0% | 0 | 0
Built-In Cabinets |  |  | 0 |  |  | 0% | 0 | 0
Built-In Shelving |  |  | 0 |  |  | 0% | 0 | 0
Ceilings - Function |  |  | 0 |  |  | 0% | 0 | 0
Ceilings - Decorative |  |  | 0 |  |  | 0% | 0 | 0
Closet Hardware |  |  | 0 |  |  | 0% | 0 | 0
Closet Shelving |  |  | 0 |  |  | 0% | 0 | 0
Flooring - Carpet |  |  | 0 |  |  | 0% | 0 | 0
Flooring - Tile / Stone Materials |  |  | 0 |  |  | 0% | 0 | 0
Flooring - Tile / Stone Prep |  |  | 0 |  |  | 0% | 0 | 0
Flooring - Vinyl |  |  | 0 |  |  | 0% | 0 | 0
Flooring - Wood |  |  | 0 |  |  | 0% | 0 | 0
Interior Door - Frames + Thresholds |  |  | 0 |  |  | 0% | 0 | 0
Interior Door - Hardware |  |  | 0 |  |  | 0% | 0 | 0
Interior Door - Prehung |  |  | 0 |  |  | 0% | 0 | 0
Interior Door - Slabs |  |  | 0 |  |  | 0% | 0 | 0
Interior Paint |  |  | 0 |  |  | 0% | 0 | 0
Interior Stain |  |  | 0 |  |  | 0% | 0 | 0
Paneling |  |  | 0 |  |  | 0% | 0 | 0
Stairs / Railings / Newels |  |  | 0 |  |  | 0% | 0 | 0
Wainscoting |  |  | 0 |  |  | 0% | 0 | 0
Labor Costs |  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
KITCHEN | 0 | 0 | 0 |  |  | 0% | 0 | 0
Accessories |  |  | 0 |  |  | 0% | 0 | 0
Backsplash |  |  | 0 |  |  | 0% | 0 | 0
Built-Ins |  |  | 0 |  |  | 0% | 0 | 0
Cabinets |  |  | 0 |  |  | 0% | 0 | 0
Cabinets - Hardware |  |  | 0 |  |  | 0% | 0 | 0
Countertops |  |  | 0 |  |  | 0% | 0 | 0
Shelving |  |  | 0 |  |  | 0% | 0 | 0
Tile / Stone |  |  | 0 |  |  | 0% | 0 | 0
Labor Costs |  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
BATH | 0 | 0 | 0 |  |  | 0% | 0 | 0
Accessories |  |  | 0 |  |  | 0% | 0 | 0
Backsplash |  |  | 0 |  |  | 0% | 0 | 0
Built-Ins |  |  | 0 |  |  | 0% | 0 | 0
Cabinets |  |  | 0 |  |  | 0% | 0 | 0
Cabinets - Hardware |  |  | 0 |  |  | 0% | 0 | 0
Countertops |  |  | 0 |  |  | 0% | 0 | 0
Medicine Cabinets |  |  | 0 |  |  | 0% | 0 | 0
Mirrors |  |  | 0 |  |  | 0% | 0 | 0
Raised Tub Platform |  |  | 0 |  |  | 0% | 0 | 0
Shelving |  |  | 0 |  |  | 0% | 0 | 0
Shower Enclosure |  |  | 0 |  |  | 0% | 0 | 0
Tile / Stone |  |  | 0 |  |  | 0% | 0 | 0
Tub Enclosure |  |  | 0 |  |  | 0% | 0 | 0
Labor Costs |  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
APPLIANCES | 0 | 0 | 0 |  |  | 0% | 0 | 0
Cooktop |  |  | 0 |  |  | 0% | 0 | 0
Deep Freeze |  |  | 0 |  |  | 0% | 0 | 0
Dishwasher |  |  | 0 |  |  | 0% | 0 | 0
Microwave Oven |  |  | 0 |  |  | 0% | 0 | 0
Oven |  |  | 0 |  |  | 0% | 0 | 0
Range Hood |  |  | 0 |  |  | 0% | 0 | 0
Refrigerator |  |  | 0 |  |  | 0% | 0 | 0
Washer + Dryer |  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
OTHER | 0 | 0 | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 100% | 0 | 0
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Contractor Estimate
Contractor Estimate Template
––––––––––– Projected –––––––––––
Job Title |  |  |  |  | Project Manager |  | Start Date | End Date
Location
| PROJECTED TOTAL | ACTUAL TOTAL | VARIANCE |  |  |  | CURRENT PAID | AMOUNT DUE
| 0 | 0 | 0 |  |  |  | 0 | 0
CATEGORY & ITEMS | PROJECTED SUBTOTAL | ACTUAL SUBTOTAL | VARIANCE | PARTY RESPONSIBLE Vendor, Contractor, etc. | STATUS | % OF TASK COMPLETE | CURRENT PAID | AMOUNT DUE | COMMENTS
PLANNING | 0 | 0 | 0 |  |  | 0% | 0 | 0
Admin Fees |  |  | 0 |  |  | 0% |  | 0
Engineering |  |  | 0 |  |  | 0% |  | 0
Financing Costs |  |  | 0 |  |  | 0% |  | 0
Legal |  |  | 0 |  |  | 0% |  | 0
Permit - Building |  |  | 0 |  |  | 0% |  | 0
Permit - Environmental |  |  | 0 |  |  | 0% |  | 0
Permit - Zoning |  |  | 0 |  |  | 0% |  | 0
Plans + Specs |  |  | 0 |  |  | 0% |  | 0
Review |  |  | 0 |  |  | 0% |  | 0
Survey |  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
SITE PREP | 0 | 0 | 0 |  |  | 0% | 0 | 0
Dumpster / Waste Removal |  |  | 0 |  |  | 0% |  | 0
Equipment Rental |  |  | 0 |  |  | 0% |  | 0
Lot Clearing |  |  | 0 |  |  | 0% |  | 0
Portable Restroom Facilities |  |  | 0 |  |  | 0% |  | 0
Remodel - Demo |  |  | 0 |  |  | 0% |  | 0
Remodel - Dust Control |  |  | 0 |  |  | 0% |  | 0
Remodel - Jacking + Shoring |  |  | 0 |  |  | 0% |  | 0
Remodel - Surface Protection |  |  | 0 |  |  | 0% |  | 0
Scaffolding Rental |  |  | 0 |  |  | 0% |  | 0
Site Access |  |  | 0 |  |  | 0% |  | 0
Site Security |  |  | 0 |  |  | 0% |  | 0
Site Storage |  |  | 0 |  |  | 0% |  | 0
Temporary Heat |  |  | 0 |  |  | 0% |  | 0
Temporary Power |  |  | 0 |  |  | 0% |  | 0
Tool Rental |  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
EARTHWORK / EXCAVATION | 0 | 0 | 0 |  |  | 0% | 0 | 0
Backfill |  |  | 0 |  |  | 0% |  | 0
Blasting |  |  | 0 |  |  | 0% |  | 0
Compaction |  |  | 0 |  |  | 0% |  | 0
Culverts |  |  | 0 |  |  | 0% |  | 0
Curtain Drains |  |  | 0 |  |  | 0% |  | 0
Cut + Fill |  |  | 0 |  |  | 0% |  | 0
Dirt + Stone Removal |  |  | 0 |  |  | 0% |  | 0
Finish Grading |  |  | 0 |  |  | 0% |  | 0
Foundation - Excavation |  |  | 0 |  |  | 0% |  | 0
Foundation - Footing Drains |  |  | 0 |  |  | 0% |  | 0
Ponds |  |  | 0 |  |  | 0% |  | 0
Retaining Walls |  |  | 0 |  |  | 0% |  | 0
Rough Grading |  |  | 0 |  |  | 0% |  | 0
Seeding / Sodding |  |  | 0 |  |  | 0% |  | 0
Site Drainage - Additional |  |  | 0 |  |  | 0% |  | 0
Swales |  |  | 0 |  |  | 0% |  | 0
Top Soil |  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
UTILITIES | 0 | 0 | 0 |  |  | 0% | 0 | 0
Electrical - Connection |  |  | 0 |  |  | 0% |  | 0
Electrical - Install |  |  | 0 |  |  | 0% |  | 0
Electrical - Permit |  |  | 0 |  |  | 0% |  | 0
Gas - Connection |  |  | 0 |  |  | 0% |  | 0
Gas - Hookup |  |  | 0 |  |  | 0% |  | 0
Gas - Permit |  |  | 0 |  |  | 0% |  | 0
Oil Tank Install |  |  | 0 |  |  | 0% |  | 0
Sewer - Tap Fees & Hookup |  |  | 0 |  |  | 0% |  | 0
Telecom - Hookup |  |  | 0 |  |  | 0% |  | 0
Telecom - Install |  |  | 0 |  |  | 0% |  | 0
Water - Tap Fees & Hookup |  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
WATER + SEWER | 0 | 0 | 0 |  |  | 0% | 0 | 0
High Water Table Dewatering |  |  | 0 |  |  | 0% |  | 0
Perc Test |  |  | 0 |  |  | 0% |  | 0
Plumbing to House |  |  | 0 |  |  | 0% |  | 0
Pressure Tank |  |  | 0 |  |  | 0% |  | 0
Pump |  |  | 0 |  |  | 0% |  | 0
Septic - Design |  |  | 0 |  |  | 0% |  | 0
Septic - Fees |  |  | 0 |  |  | 0% |  | 0
Septic - Inspection |  |  | 0 |  |  | 0% |  | 0
Septic - Permits |  |  | 0 |  |  | 0% |  | 0
Septic - Tie to House |  |  | 0 |  |  | 0% |  | 0
Soil Test |  |  | 0 |  |  | 0% |  | 0
Trenching |  |  | 0 |  |  | 0% |  | 0
Well |  |  | 0 |  |  | 0% |  | 0
Well - Fees |  |  | 0 |  |  | 0% |  | 0
Well - Permits |  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
FOUNDATION | 0 | 0 | 0 |  |  | 0% | 0 | 0
Anchor Bolts |  |  | 0 |  |  | 0% |  | 0
Bulkheads |  |  | 0 |  |  | 0% |  | 0
Crawlspace Vapor Barrier |  |  | 0 |  |  | 0% |  | 0
Crawlspace Vents |  |  | 0 |  |  | 0% |  | 0
Dam Proofing |  |  | 0 |  |  | 0% |  | 0
Exterior Foundation Insulation |  |  | 0 |  |  | 0% |  | 0
Exterior Insulation Coating |  |  | 0 |  |  | 0% |  | 0
Footings |  |  | 0 |  |  | 0% |  | 0
Foundation - Drain Board |  |  | 0 |  |  | 0% |  | 0
Foundation - Walls |  |  | 0 |  |  | 0% |  | 0
Foundation - Windows |  |  | 0 |  |  | 0% |  | 0
Grade Beams |  |  | 0 |  |  | 0% |  | 0
Hold Downs |  |  | 0 |  |  | 0% |  | 0
Pads |  |  | 0 |  |  | 0% |  | 0
Piers |  |  | 0 |  |  | 0% |  | 0
Slab - Basement |  |  | 0 |  |  | 0% |  | 0
Slab - Foundation |  |  | 0 |  |  | 0% |  | 0
Slab - Garage |  |  | 0 |  |  | 0% |  | 0
Slab Insulation |  |  | 0 |  |  | 0% |  | 0
Steel Reinforcing |  |  | 0 |  |  | 0% |  | 0
Stem Walls |  |  | 0 |  |  | 0% |  | 0
Sub-Slab Vapor Barrier |  |  | 0 |  |  | 0% |  | 0
Sump Pump |  |  | 0 |  |  | 0% |  | 0
Waterproofing |  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
ROUGH FRAMING | 0 | 0 | 0 |  |  | 0% | 0 | 0
Exterior Walls |  |  | 0 |  |  | 0% |  | 0
Fasteners / Nails / Screws |  |  | 0 |  |  | 0% |  | 0
Floor Framing |  |  | 0 |  |  | 0% |  | 0
Interior Walls |  |  | 0 |  |  | 0% |  | 0
Lally Columns |  |  | 0 |  |  | 0% |  | 0
Plaster / Drywall Prep |  |  | 0 |  |  | 0% |  | 0
Roof Framing / Trusses |  |  | 0 |  |  | 0% |  | 0
Rough Stairs |  |  | 0 |  |  | 0% |  | 0
Sheathing |  |  | 0 |  |  | 0% |  | 0
Sill + Seal |  |  | 0 |  |  | 0% |  | 0
Steel / Wood Carrying Beam |  |  | 0 |  |  | 0% |  | 0
Steel Framing Connectors |  |  | 0 |  |  | 0% |  | 0
Sub-Fascia |  |  | 0 |  |  | 0% |  | 0
Subflooring |  |  | 0 |  |  | 0% |  | 0
Labor Costs |  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
WINDOWS + DOORS (Exterior) | 0 | 0 | 0 |  |  | 0% | 0 | 0
Exterior Door - Frames + Sills |  |  | 0 |  |  | 0% |  | 0
Exterior Door - Hardware |  |  | 0 |  |  | 0% |  | 0
Exterior Door - Prehung |  |  | 0 |  |  | 0% |  | 0
Exterior Door - Slabs |  |  | 0 |  |  | 0% |  | 0
Garage Doors |  |  | 0 |  |  | 0% |  | 0
Membrane + Flashing |  |  | 0 |  |  | 0% |  | 0
Sidelights |  |  | 0 |  |  | 0% |  | 0
Sliding / Hinged Doors |  |  | 0 |  |  | 0% |  | 0
Transoms |  |  | 0 |  |  | 0% |  | 0
Windows |  |  | 0 |  |  | 0% |  | 0
Labor Costs |  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
FINISH - EXTERIOR | 0 | 0 | 0 |  |  | 0% | 0 | 0
Foam Sheathing |  |  | 0 |  |  | 0% |  | 0
Weather Barrier |  |  | 0 |  |  | 0% |  | 0
Membrane + Flashing |  |  | 0 |  |  | 0% |  | 0
Siding |  |  | 0 |  |  | 0% |  | 0
Veneer |  |  | 0 |  |  | 0% |  | 0
Stucco |  |  | 0 |  |  | 0% |  | 0
Fascia |  |  | 0 |  |  | 0% |  | 0
Soffit |  |  | 0 |  |  | 0% |  | 0
Frieze |  |  | 0 |  |  | 0% |  | 0
Corner Boards |  |  | 0 |  |  | 0% |  | 0
Water Table |  |  | 0 |  |  | 0% |  | 0
Soffit / Gable Vents |  |  | 0 |  |  | 0% |  | 0
Trim - Windows |  |  | 0 |  |  | 0% |  | 0
Trim - Doors |  |  | 0 |  |  | 0% |  | 0
Trim - Finishing |  |  | 0 |  |  | 0% |  | 0
Stairs |  |  | 0 |  |  | 0% |  | 0
Landing |  |  | 0 |  |  | 0% |  | 0
Paint |  |  | 0 |  |  | 0% |  | 0
Stain |  |  | 0 |  |  | 0% |  | 0
Caulk |  |  | 0 |  |  | 0% |  | 0
Labor Costs |  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
ROOFING | 0 | 0 | 0 |  |  | 0% | 0 | 0
Drip Edge |  |  | 0 |  |  | 0% |  | 0
Gutters + Downspouts |  |  | 0 |  |  | 0% |  | 0
Installation / Labor |  |  | 0 |  |  | 0% |  | 0
Membrane + Flashing |  |  | 0 |  |  | 0% |  | 0
Ridge & Roof Vents |  |  | 0 |  |  | 0% |  | 0
Skylights |  |  | 0 |  |  | 0% |  | 0
Underlayment |  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
MASONRY / PAVING | 0 | 0 | 0 |  |  | 0% | 0 | 0
Driveway |  |  | 0 |  |  | 0% |  | 0
Walkways |  |  | 0 |  |  | 0% |  | 0
Chimneys |  |  | 0 |  |  | 0% |  | 0
Stairs - Exterior |  |  | 0 |  |  | 0% |  | 0
Patios |  |  | 0 |  |  | 0% |  | 0
Fireplaces + Hearths |  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
PORCHES + DECKS | 0 | 0 | 0 |  |  | 0% | 0 | 0
Porch - Open |  |  | 0 |  |  | 0% |  | 0
Porch - Screened |  |  | 0 |  |  | 0% |  | 0
Deck - Composite |  |  | 0 |  |  | 0% |  | 0
Deck - Wood |  |  | 0 |  |  | 0% |  | 0
Fencing |  |  | 0 |  |  | 0% |  | 0
Railings |  |  | 0 |  |  | 0% |  | 0
Outdoor Built-Ins |  |  | 0 |  |  | 0% |  | 0
Additional Structures |  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
INSULATION + AIR SEALING | 0 | 0 | 0 |  |  | 0% | 0 | 0
Air Sealing |  |  | 0 |  |  | 0% |  | 0
Blower Door |  |  | 0 |  |  | 0% |  | 0
Infrared |  |  | 0 |  |  | 0% |  | 0
Insulation - Basement Interior |  |  | 0 |  |  | 0% |  | 0
Insulation - Crawlspace |  |  | 0 |  |  | 0% |  | 0
Insulation - Foam Board |  |  | 0 |  |  | 0% |  | 0
Insulation - Roof / Attic |  |  | 0 |  |  | 0% |  | 0
Insulation - Spray Foam |  |  | 0 |  |  | 0% |  | 0
Insulation - Wall Cavity |  |  | 0 |  |  | 0% |  | 0
Roof / Eave Baffles |  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
PLUMBING | 0 | 0 | 0 |  |  | 0% | 0 | 0
Drain |  |  | 0 |  |  | 0% |  | 0
Waste |  |  | 0 |  |  | 0% |  | 0
Vent |  |  | 0 |  |  | 0% |  | 0
Piping - Water Supply |  |  | 0 |  |  | 0% |  | 0
Piping - Gas |  |  | 0 |  |  | 0% |  | 0
Water Heater |  |  | 0 |  |  | 0% |  | 0
Water Treatment |  |  | 0 |  |  | 0% |  | 0
Toilets |  |  | 0 |  |  | 0% |  | 0
Tubs |  |  | 0 |  |  | 0% |  | 0
Sinks |  |  | 0 |  |  | 0% |  | 0
Showers |  |  | 0 |  |  | 0% |  | 0
Faucets |  |  | 0 |  |  | 0% |  | 0
Mixing Valves |  |  | 0 |  |  | 0% |  | 0
Shower Heads |  |  | 0 |  |  | 0% |  | 0
Disposal |  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
ELECTRICAL | 0 | 0 | 0 |  |  | 0% | 0 | 0
Service Panels |  |  | 0 |  |  | 0% |  | 0
Sub-Panels |  |  | 0 |  |  | 0% |  | 0
Rough Wiring |  |  | 0 |  |  | 0% |  | 0
Phone / Cable / Internet Wiring |  |  | 0 |  |  | 0% |  | 0
Lighting Fixtures |  |  | 0 |  |  | 0% |  | 0
Low-Voltage Fixtures |  |  | 0 |  |  | 0% |  | 0
Low-Voltage Transformers |  |  | 0 |  |  | 0% |  | 0
Outlets |  |  | 0 |  |  | 0% |  | 0
Switches |  |  | 0 |  |  | 0% |  | 0
Dimmers |  |  | 0 |  |  | 0% |  | 0
Lighting Control System |  |  | 0 |  |  | 0% |  | 0
Doorbell |  |  | 0 |  |  | 0% |  | 0
Smoke + CO2 Alarms |  |  | 0 |  |  | 0% |  | 0
Intercom System |  |  | 0 |  |  | 0% |  | 0
Security System |  |  | 0 |  |  | 0% |  | 0
Home Theater |  |  | 0 |  |  | 0% |  | 0
Home Entertainment System |  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
HVAC | 0 | 0 | 0 |  |  | 0% | 0 | 0
Air Handler |  |  | 0 |  |  | 0% |  | 0
Boiler |  |  | 0 |  |  | 0% |  | 0
Central AC |  |  | 0 |  |  | 0% |  | 0
Ductwork |  |  | 0 |  |  | 0% |  | 0
Furnace / Heat Pump |  |  | 0 |  |  | 0% |  | 0
Grilles |  |  | 0 |  |  | 0% |  | 0
HVAC Controls |  |  | 0 |  |  | 0% |  | 0
Piping |  |  | 0 |  |  | 0% |  | 0
Radiators |  |  | 0 |  |  | 0% |  | 0
Registers |  |  | 0 |  |  | 0% |  | 0
Solar Hot Water |  |  | 0 |  |  | 0% |  | 0
Whole-House Ventilation |  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
DRYWALL + PLASTER | 0 | 0 | 0 |  |  | 0% | 0 | 0
Walls |  |  | 0 |  |  | 0% |  | 0
Ceilings |  |  | 0 |  |  | 0% |  | 0
Soffits |  |  | 0 |  |  | 0% |  | 0
Decorative Plaster |  |  | 0 |  |  | 0% |  | 0
Labor Costs |  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
FINISH - INTERIOR | 0 | 0 | 0 |  |  | 0% | 0 | 0
Built-In Cabinets |  |  | 0 |  |  | 0% |  | 0
Built-In Shelving |  |  | 0 |  |  | 0% |  | 0
Ceilings - Function |  |  | 0 |  |  | 0% |  | 0
Ceilings - Decorative |  |  | 0 |  |  | 0% |  | 0
Closet Hardware |  |  | 0 |  |  | 0% |  | 0
Closet Shelving |  |  | 0 |  |  | 0% |  | 0
Flooring - Carpet |  |  | 0 |  |  | 0% |  | 0
Flooring - Tile / Stone Materials |  |  | 0 |  |  | 0% |  | 0
Flooring - Tile / Stone Prep |  |  | 0 |  |  | 0% |  | 0
Flooring - Vinyl |  |  | 0 |  |  | 0% |  | 0
Flooring - Wood |  |  | 0 |  |  | 0% |  | 0
Interior Door - Frames + Thresholds |  |  | 0 |  |  | 0% |  | 0
Interior Door - Hardware |  |  | 0 |  |  | 0% |  | 0
Interior Door - Prehung |  |  | 0 |  |  | 0% |  | 0
Interior Door - Slabs |  |  | 0 |  |  | 0% |  | 0
Interior Paint |  |  | 0 |  |  | 0% |  | 0
Interior Stain |  |  | 0 |  |  | 0% |  | 0
Paneling |  |  | 0 |  |  | 0% |  | 0
Stairs / Railings / Newels |  |  | 0 |  |  | 0% |  | 0
Wainscoting |  |  | 0 |  |  | 0% |  | 0
Labor Costs |  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
KITCHEN | 0 | 0 | 0 |  |  | 0% | 0 | 0
Accessories |  |  | 0 |  |  | 0% |  | 0
Backsplash |  |  | 0 |  |  | 0% |  | 0
Built-Ins |  |  | 0 |  |  | 0% |  | 0
Cabinets |  |  | 0 |  |  | 0% |  | 0
Cabinets - Hardware |  |  | 0 |  |  | 0% |  | 0
Countertops |  |  | 0 |  |  | 0% |  | 0
Shelving |  |  | 0 |  |  | 0% |  | 0
Tile / Stone |  |  | 0 |  |  | 0% |  | 0
Labor Costs |  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
BATH | 0 | 0 | 0 |  |  | 0% | 0 | 0
Accessories |  |  | 0 |  |  | 0% |  | 0
Backsplash |  |  | 0 |  |  | 0% |  | 0
Built-Ins |  |  | 0 |  |  | 0% |  | 0
Cabinets |  |  | 0 |  |  | 0% |  | 0
Cabinets - Hardware |  |  | 0 |  |  | 0% |  | 0
Countertops |  |  | 0 |  |  | 0% |  | 0
Medicine Cabinets |  |  | 0 |  |  | 0% |  | 0
Mirrors |  |  | 0 |  |  | 0% |  | 0
Raised Tub Platform |  |  | 0 |  |  | 0% |  | 0
Shelving |  |  | 0 |  |  | 0% |  | 0
Shower Enclosure |  |  | 0 |  |  | 0% |  | 0
Tile / Stone |  |  | 0 |  |  | 0% |  | 0
Tub Enclosure |  |  | 0 |  |  | 0% |  | 0
Labor Costs |  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
APPLIANCES | 0 | 0 | 0 |  |  | 0% | 0 | 0
Cooktop |  |  | 0 |  |  | 0% |  | 0
Deep Freeze |  |  | 0 |  |  | 0% |  | 0
Dishwasher |  |  | 0 |  |  | 0% |  | 0
Microwave Oven |  |  | 0 |  |  | 0% |  | 0
Oven |  |  | 0 |  |  | 0% |  | 0
Range Hood |  |  | 0 |  |  | 0% |  | 0
Refrigerator |  |  | 0 |  |  | 0% |  | 0
Washer + Dryer |  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
OTHER | 0 | 0 | 0 |  |  | 0% | 0 | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 0% |  | 0
|  |  | 0 |  |  | 100% |  | 0

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.