## EX - Stakeholder Change Mgmt
Stakeholder Change Management Analysis Template Example
Project Name | [5 empty] | Project Manager |  | Date | Version
Cloud-Based PM Software Implementation | [5 empty] | Lori Garcia |  | 01/01/20XX | 1.0.1
High – Medium – Low
Stakeholder | Role | Department | Interest(s) | Influence | Involvement | Commitment to Change | Anticipated Resistance | Change Readiness | Change Impact | Motivations for Change | Expectations | Predisposition | Training Needs | Engagement Strategy
Diana Kennedy | CEO | Executive | Organizational growth, technological innovation | High | High | High | Low | High | High | Driving company efficiency and growth | Full support of the software implementation | Supportive | None | Regular briefings, executive updates, high-level decisions
Lori Garcia | PM | Operations | Project timelines, delivery, team performance | Medium | High | Medium | Medium | Medium | High | Improving task tracking, reducing complexity | More efficient project tracking and reporting | Neutral | Training on how to use the tool for team coordination | Targeted workshops, weekly team meetings
Jason Desjardins | Software Developer | IT | Ease of use, productivity tools | Low | Low | Low | Medium | Low | Medium | Reducing redundant tasks, improving task clarity | Less redundant work | Resistant | Specific tool and feature training | Direct involvement in testing, detailed tutorials
Ambivalent
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Stakeholder Change Mgmt
Stakeholder Change Management Analysis Template
Project Name | [5 empty] | Project Manager |  | Date | Version
High – Medium – Low
Stakeholder | Role | Department | Interest(s) | Influence | Involvement | Commitment to Change | Anticipated Resistance | Change Readiness | Change Impact | Motivations for Change | Expectations | Predisposition | Training Needs | Engagement Strategy

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
Impact | Predisposition | Type | Status | Yes / No
Low | Supportive | Internal | Not Started | Yes
Medium | Neutral | External | In Progress | No
High | Ambivalent | Direct | Complete
| Resistant | Indirect | Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.