## EXAMPLE 14-Day Sprint Backlog
14-DAY SPRINT BACKLOG TEMPLATE
CURRENT DATE | SPRINT START DATE | TOTAL ASSIGNED HOURS |  | HOURS USED |  | HOURS REMAINING
MM/DD/YY | MM/DD/YY | 1163 |  | 399 |  | 764
SPRINT TRACKING |  | Enter the date of the start and the subsequent dates will populate. ---> |  |  | 2028-02-01 | 2028-02-02 | 2028-02-03 | 2028-02-04 | 2028-02-05 | 2028-02-06 | 2028-02-07 | 2028-02-08 | 2028-02-09 | 2028-02-10 | 2028-02-11 | 2028-02-12 | 2028-02-13 | 2028-02-14
TEAMS AND TASKS | ASSIGNED TO | ASSIGNED HOURS | HOURS USED | AVAILABLE HOURS REMAINING | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | DAY 11 | DAY 12 | DAY 13 | DAY 14
Scrum Team #1
Task | John K | 60 | 24 | 36 | 5 | 3 | 0 | 0 | 0 | 0 | 5 | 3 | 0 | 0 | 0 | 0 | 5 | 3
Task | Matthew M | 60 | 18 | 42 | 1 | 1 | 5 | 0 | 1 | 0 | 1 | 1 | 5 | 0 | 1 | 0 | 1 | 1
Task | Virginia W | 50 | 7.5 | 42.5 | 0.5 | 0 | 3 | 0 | 0 | 0 | 0.5 | 0 | 3 | 0 | 0 | 0 | 0.5 | 0
Task | Jeff P | 42 | 17 | 25 | 1 | 2 | 3 | 1 | 0 | 0 | 1 | 2 | 3 | 1 | 0 | 0 | 1 | 2
Scrum Team #2
Task |  | 34 | 15.5 | 18.5 | 3 | 0.5 | 0.5 | 0 | 0 | 2 | 3 | 0.5 | 0.5 | 0 | 0 | 2 | 3 | 0.5
Task |  | 70 | 36 | 34 | 5 | 5 | 1 | 1 | 1 | 0 | 5 | 5 | 1 | 1 | 1 | 0 | 5 | 5
Task |  | 50 | 25 | 25 | 2 | 5 | 0 | 1 | 0 | 1 | 2 | 5 | 0 | 1 | 0 | 1 | 2 | 5
Task |  | 80 | 24 | 56 | 5 | 0 | 5 | 1 | 0 | 1 | 5 | 0 | 0 | 1 | 0 | 1 | 5 | 0
Scrum Team #3
Task |  | 80 | 18 | 62 | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 0
Task |  | 60 | 24 | 36 | 1 | 3 | 3 | 3 | 0 | 0 | 1 | 3 | 3 | 3 | 0 | 0 | 1 | 3
Task |  | 20 | 9.5 | 10.5 | 1 | 0.5 | 0.5 | 1 | 1 | 0 | 1 | 0.5 | 0.5 | 1 | 1 | 0 | 1 | 0.5
Task |  | 20 | 7.5 | 12.5 | 0.5 | 0 | 0 | 0 | 0 | 3 | 0.5 | 0 | 0 | 0 | 0 | 3 | 0.5 | 0
Scrum Team #4
Task |  | 80 | 26 | 54 | 4 | 2 | 2 | 1 | 1 | 0 | 4 | 2 | 2 | 1 | 1 | 0 | 4 | 2
Task |  | 80 | 31 | 49 | 6 | 3 | 3 | 0 | 1 | 1 | 0 | 3 | 0 | 3 | 1 | 1 | 6 | 3
Task |  | 80 | 42 | 38 | 2 | 8 | 8 | 1 | 0 | 1 | 2 | 8 | 8 | 1 | 0 | 1 | 2 | 0
Task |  | 15 | 4 | 11 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0.5 | 0.5
Scrum Team #5
Task |  | 32 | 13 | 19 | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 1 | 1 | 0.5 | 1 | 1 | 1 | 1
Task |  | 80 | 19 | 61 | 6 | 6 | 0.5 | 3 | 0 | 0 | 0 | 0 | 0.5 | 3 | 0 | 0 | 0 | 0
Task |  | 120 | 30 | 90 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 2 | 2
Task |  | 50 | 8 | 42 | 0.5 | 0.5 | 1 | 0.5 | 0 | 1 | 0.5 | 0.5 | 1 | 0.5 | 0 | 1 | 0.5 | 0.5
TOTAL |  | 1163 | 399 | 764
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK 14-Day Sprint Backlog
14-DAY SPRINT BACKLOG TEMPLATE
CURRENT DATE | SPRINT START DATE | TOTAL ASSIGNED HOURS |  | HOURS USED |  | HOURS REMAINING
MM/DD/YY | MM/DD/YY | 0 |  | 0 |  | 0
SPRINT TRACKING |  | Enter the date of the first Monday and the subsequent dates will populate. ---> |  |  | 2028-01-01 | 2028-01-02 | 2028-01-03 | 2028-01-04 | 2028-01-05 | 2028-01-06 | 2028-01-07 | 2028-01-08 | 2028-01-09 | 2028-01-10 | 2028-01-11 | 2028-01-12 | 2028-01-13 | 2028-01-14
TEAMS AND TASKS | ASSIGNED TO | ASSIGNED HOURS | HOURS USED | AVAILABLE HOURS REMAINING | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | DAY 8 | DAY 9 | DAY 10 | DAY 11 | DAY 12 | DAY 13 | DAY 14
Scrum Team #1
Task |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scrum Team #2
Task |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scrum Team #3
Task |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scrum Team #4
Task |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scrum Team #5
Task |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Task |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  | 0 | 0 | 0

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.