## EXAMPLE - Agile Project Dash
Agile Project Dashboard Template
This tab contains example data. To begin building your Agile Project Dashboard, use the BLANK tab.
Project Name |  |  |  |  | Project Manager |  | Start Date | End Date | Overall Progress | Project Deliverable
Product Release |  |  |  |  | Brian G. |  | 2055-05-02 | 2025-10-10 | 35% | Scope Statement
At Risk | Sprint | User Story | Feature Type e.g., User Story, Bug, Spike | Priority MoSCoW method | Responsible | Story Points | Start | Finish | Duration in days | Status | Acceptance Criteria Define when a story is complete. | Comments
No | Sprint 1 | Sprint 1 |  |  | Brian G. |  | 2025-09-03 | 2025-09-13 | 11
No | Sprint 1 | Feature 1 |  | Must Have | Frank C. |  | 2025-09-03 | 2025-09-07 | 5 | Done
Yes | Sprint 1 | Feature 2 |  | Must Have | Devon G. |  | 2025-09-07 | 2025-09-12 | 6 | In Progress
No | Sprint 1 | Feature 3 |  | Should Have | Devon G. |  | 2025-09-09 | 2025-09-13 | 5 | Overdue
No | Sprint 2 | Sprint 2 |  |  | Devon G. |  | 2025-09-16 | 2025-09-24 | 9
No | Sprint 2 | Feature 4 |  | Could Have | Brian G. |  | 2025-09-16 | 2025-09-17 | 2 | In Progress
Yes | Sprint 2 | Feature 5 |  | Could Have | Diana K. |  | 2025-09-17 | 2025-09-21 | 5 | In Review
No | Sprint 2 | Feature 6 |  | Won't Have | Hilda W. |  | 2025-09-22 | 2025-09-24 | 3 | In Progress
No | Sprint 3 | Sprint 3 |  |  | Hilda W. |  | 2025-09-25 | 2025-10-05 | 11
Yes | Sprint 3 | Feature 7 |  |  | Brian G. |  | 2025-09-25 | 2025-09-29 | 5 | To Do
No | Sprint 3 | Feature 8 |  |  | Olivia C. |  | 2025-09-27 | 2025-10-02 | 6 | To Do
No | Sprint 3 | Feature 9 |  |  | Devon G. |  | 2025-10-02 | 2025-10-05 | 4 | To Do
CLICK HERE TO CREATE IN SMARTSHEET
Formulas:
Start Date = MIN([Start Date, row below]:I11)
End Date = MAX([End Date, row below]:J11)

## BLANK - Agile Project Dashboard
Agile Project Dashboard Template
Project Name |  |  |  |  | Project Manager |  | Start Date | End Date | Overall Progress | Project Deliverable
Scope Statement
At Risk | Sprint | User Story | Feature Type e.g., User Story, Bug, Spike | Priority MoSCoW method | Responsible | Story Points | Start | Finish | Duration in days | Status | Acceptance Criteria Define when a story is complete. | Comments
Double click Horizontal (Value) Axis to format Bound Minimum and Maximum settings under Axis Options.

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | Priority | STATUS
Yes | Must Have | To Do
No | Should Have | In Progress
| Could Have | Done
| Won't Have | In Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.