## EXAMPLE - Construction Budget
Sample Excel Home Construction Project Budget Template
This tab contains example data. To begin building your construction budget, use the BLANK tab.
–––––––––––––––– Budget ––––––––––––––––
|  |  | Projected Total | Actual Total | Under / Over
|  |  | 70300 | 67625 | -2675
Task | Party Responsible Vendor, Contractor, etc. | Status | Budget | Actual | Variance | Start Date | End Date | Duration in Days | Comments
Excavation |  | Complete | 3000 | 1800 | -1200 | 2025-01-16 | 2025-01-20 | 5
Foundation Cement |  | In Progress | 2000 | 2300 | 300 | 2025-01-22 | 2025-01-24 | 3
Masonry Block |  | Overdue | 2000 | 1475 | -525 | 2025-01-25 | 2025-01-31 | 7
Framing |  | Not Started | 2000 | 2800 | 800 | 2025-02-05 | 2025-02-15 | 11
Exterior |  | Approved | 2000 | 1000 | -1000 | 2025-02-22 | 2025-02-25 | 4
Windows / Exterior Doors |  | Needs Review | 2000 | 1850 | -150 | 2025-02-22 | 2025-02-28 | 7
Plumbing |  | On Hold | 3500 | 4000 | 500 | 2025-01-28 | 2025-02-11 | 15
Electrical |  |  | 6500 | 5800 | -700 | 2025-01-29 | 2025-02-25 | 28
HVAC |  |  | 2000 | 2600 | 600 | 2025-03-11 | 2025-03-16 | 6
Insulation & Air-Sealing |  |  | 2000 | 1800 | -200 | 2025-02-28 | 2025-03-01 | 2
Drywall / Plaster |  |  | 2000 | 500 | -1500 | 2025-02-28 | 2025-03-04 | 5
Interior Finish |  |  | 12000 | 15500 | 3500 | 2025-03-01 | 2025-03-16 | 16
Kitchen & Bath |  |  | 20000 | 17000 | -3000 | 2025-03-01 | 2025-03-20 | 20
Porches & Decks |  |  | 5800 | 5000 | -800 | 2025-02-15 | 2025-03-17 | 31
Appliances |  |  | 3500 | 4200 | 700 | 2025-03-18 | 2025-03-20 | 3
Other 1 |  |  |  |  | 0 | 2025-03-06 | 2025-03-20 | 15
Other 2 |  |  |  |  | 0 | 2025-03-11 | 2025-03-21 | 11
Other 3 |  |  |  |  | 0 | 2025-03-15 | 2025-03-20 | 6
Other 4 |  |  |  |  | 0 | 2025-03-18 | 2025-03-20 | 3
Other 5 |  |  |  |  | 0 | 2025-03-20 | 2025-03-23 | 4
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Construction Budget
Home Construction Project Budget Template
Enter project data in the table below. Budget totals and Gantt chart will populate automatically.
–––––––––––––––– Budget ––––––––––––––––
|  |  | Projected Total | Actual Total | Under / Over
|  |  | 0 | 0 | 0
Task | Party Responsible Vendor, Contractor, etc. | Status | Budget | Actual | Variance | Start Date | End Date | Duration in Days | Comments
Excavation |  |  |  |  | 0
Foundation Cement |  |  |  |  | 0
Masonry Block |  |  |  |  | 0
Framing |  |  |  |  | 0
Exterior |  |  |  |  | 0
Windows / Exterior Doors |  |  |  |  | 0
Plumbing |  |  |  |  | 0
Electrical |  |  |  |  | 0
HVAC |  |  |  |  | 0
Insulation & Air-Sealing |  |  |  |  | 0
Drywall / Plaster |  |  |  |  | 0
Interior Finish |  |  |  |  | 0
Kitchen & Bath |  |  |  |  | 0
Porches & Decks |  |  |  |  | 0
Appliances |  |  |  |  | 0
Other 1 |  |  |  |  | 0
Other 2 |  |  |  |  | 0
Other 3 |  |  |  |  | 0
Other 4 |  |  |  |  | 0
Other 5 |  |  |  |  | 0
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.