## EXAMPLE - Construction Budget
Sample Excel Residential Construction Budget Template
This tab contains example data. To begin building your construction budget, use the BLANK tab.
Job Title |  |  |  |  | Project Manager | Start Date | End Date
New Residential Build |  |  |  |  | Mateus Tobin | 01/15/20XX | 12/15/20XX
Location
1234 Oakwood Avenue, Anytown, USA
|  | –––––––––––––––– Budget –––––––––––––––– |  |  | –––––––––––––––– Contingency ––––––––––––––––
|  | Projected Total | Actual Total | Variance | Contingency Percentage | Budget Total w/ Contingency | Variance w/ Contingency | Current Paid Total | Amount Due Total
|  | 65200 | 67100 | 1900 | 10% | 71720 | 4620 | 58825 | 8275
WBS | Category & Items | Projected Subtotal | Actual Subtotal | Variance | Party Responsible Vendor, Contractor, etc. | Status | Pct of Task Complete | Current Paid | Amount Due | Comments
1.0 | PLANNING | 17500 | 18000 | 500 |  | Complete | 100% | 18000 | 0
1.1 | Admin Fees | 2000 | 2000 | 0 | Admin Services Co. | Complete | 100% | 2000 | 0 | Paid upfront
1.2 | Engineering | 6000 | 6500 | 500 | Smith Engineering | Complete | 100% | 6500 | 0 | Design revisions included
1.3 | Financing Costs | 4500 | 4500 | 0 | Bank of Anytown | Complete | 100% | 4500 | 0 | Paid at closing
1.4 | Permit - Building | 1800 | 1800 | 0 | City Permits Office | Complete | 100% | 1800 | 0 | Approved
1.5 | Permit - Zoning | 1200 | 1200 | 0 | Zoning Dept. | Complete | 100% | 1200 | 0 | No issues
1.6 | Survey | 2000 | 2000 | 0 | Survey Pro | Complete | 100% | 2000 | 0 | Site boundaries confirmed
1.7 |  |  |  | 0 |  |  | 0% | 0 | 0
1.8 |  |  |  | 0 |  |  | 0% | 0 | 0
1.9 |  |  |  | 0 |  |  | 0% | 0 | 0
1.10 |  |  |  | 0 |  |  | 0% | 0 | 0
2.0 | SITE PREP | 25900 | 26300 | 400 |  | In Progress | 65% | 22775 | 3525
2.1 | Dumpster / Waste Removal | 2000 | 2200 | 200 | Waste-Pro Inc | In Progress | 50% | 1100 | 1100 | Additional debris generated
2.2 | Equipment Rental | 5000 | 5000 | 0 | Ace Rentals | Complete | 100% | 5000 | 0 | On budget
2.3 | Lot Clearing | 3500 | 3800 | 300 | Green Contractors | Complete | 100% | 3800 | 0 | Unexpected tree removal
2.4 | Portable Restroom Facilities | 1500 | 1500 | 0 | Clean Site Services | In Progress | 75% | 1125 | 375 | Ongoing service
2.5 | Remodel - Demo | 8000 | 7500 | -500 | Demo Experts | Complete | 100% | 7500 | 0 | Under budget
2.6 | Remodel - Dust Control | 1200 | 1300 | 100 | Dust-Stop Solutions | In Progress | 60% | 780 | 520 | Added extra barriers
2.7 | Site Access | 1000 | 1100 | 100 | Site-Prep LLC | Complete | 100% | 1100 | 0 | Minor adjustments made
2.8 | Temporary Power | 2500 | 2500 | 0 | Power-Equip Co. | In Progress | 50% | 1250 | 1250 | Scheduled maintenance
2.9 | Tool Rental | 1200 | 1400 | 200 | Tool Works Inc. | In Progress | 80% | 1120 | 280 | Extended rental periods
2.10 |  |  |  | 0 |  |  | 0% | 0 | 0
2.11 |  |  |  | 0 |  |  | 0% | 0 | 0
2.12 |  |  |  | 0 |  |  | 0% | 0 | 0
2.13 |  |  |  | 0 |  |  | 0% | 0 | 0
3.0 | EARTHWORK / EXCAVATION | 21800 | 22800 | 1000 |  | In Progress | 50% | 18050 | 4750
3.1 | Backfill | 4000 | 4200 | 200 | Earth-Movers Inc. | In Progress | 70% | 2940 | 1260 | Extra materials used
3.2 | Foundation - Excavation | 8000 | 8500 | 500 | Digi-Tech Solutions | Complete | 100% | 8500 | 0 | Unforeseen soil conditions
3.3 | Foundation - Footing Drains | 3000 | 3000 | 0 | Drain-Flow Co. | Complete | 100% | 3000 | 0 | As planned
3.4 | Rough Grading | 2500 | 2700 | 200 | Grade Masters | In Progress | 80% | 2160 | 540 | Close to completion
3.5 | Seeding / Sodding | 1500 | 1500 | 0 | GT Landscaping | Not Started | 0% | 0 | 1500 | Scheduled for next month
3.6 | Site Drainage - Additional | 2800 | 2900 | 100 | Aqua Flow Contractors | In Progress | 50% | 1450 | 1450 | Partial completion
3.7 |  |  |  | 0 |  |  | 0% | 0 | 0
3.8 |  |  |  | 0 |  |  | 0% | 0 | 0
3.9 |  |  |  | 0 |  |  | 0% | 0 | 0
3.10 |  |  |  | 0 |  |  | 0% | 0 | 0
4.0 | UTILITIES | 0 | 0 | 0 |  |  | 0% | 0 | 0
4.1 | Electrical - Connection |  |  | 0 |  |  | 0% | 0 | 0
4.2 | Electrical - Install |  |  | 0 |  |  | 0% | 0 | 0
4.3 | Electrical - Permit |  |  | 0 |  |  | 0% | 0 | 0
4.4 | Gas - Connection |  |  | 0 |  |  | 0% | 0 | 0
4.5 | Gas - Hookup |  |  | 0 |  |  | 0% | 0 | 0
4.6 | Gas - Permit |  |  | 0 |  |  | 0% | 0 | 0
4.7 | Oil Tank Install |  |  | 0 |  |  | 0% | 0 | 0
4.8 | Sewer - Tap Fees & Hookup |  |  | 0 |  |  | 0% | 0 | 0
4.9 | Telecom - Hookup |  |  | 0 |  |  | 0% | 0 | 0
4.10 | Telecom - Install |  |  | 0 |  |  | 0% | 0 | 0
4.11 | Water - Tap Fees & Hookup |  |  | 0 |  |  | 0% | 0 | 0
4.12 |  |  |  | 0 |  |  | 0% | 0 | 0
4.13 |  |  |  | 0 |  |  | 0% | 0 | 0
4.14 |  |  |  | 0 |  |  | 0% | 0 | 0
4.15 |  |  |  | 0 |  |  | 0% | 0 | 0
5.0 | WATER + SEWER | 0 | 0 | 0 |  |  | 0% | 0 | 0
5.1 | High Water Table Dewatering |  |  | 0 |  |  | 0% | 0 | 0
5.2 | Perc Test |  |  | 0 |  |  | 0% | 0 | 0
5.3 | Plumbing to House |  |  | 0 |  |  | 0% | 0 | 0
5.4 | Pressure Tank |  |  | 0 |  |  | 0% | 0 | 0
5.5 | Pump |  |  | 0 |  |  | 0% | 0 | 0
5.6 | Septic - Design |  |  | 0 |  |  | 0% | 0 | 0
5.7 | Septic - Fees |  |  | 0 |  |  | 0% | 0 | 0
5.8 | Septic - Inspection |  |  | 0 |  |  | 0% | 0 | 0
5.9 | Septic - Permits |  |  | 0 |  |  | 0% | 0 | 0
5.10 | Septic - Tie to House |  |  | 0 |  |  | 0% | 0 | 0
5.11 | Soil Test |  |  | 0 |  |  | 0% | 0 | 0
5.12 | Trenching |  |  | 0 |  |  | 0% | 0 | 0
5.13 | Well |  |  | 0 |  |  | 0% | 0 | 0
5.14 | Well - Fees |  |  | 0 |  |  | 0% | 0 | 0
5.15 | Well - Permits |  |  | 0 |  |  | 0% | 0 | 0
5.16 |  |  |  | 0 |  |  | 0% | 0 | 0
5.17 |  |  |  | 0 |  |  | 0% | 0 | 0
5.18 |  |  |  | 0 |  |  | 0% | 0 | 0
5.19 |  |  |  | 0 |  |  | 0% | 0 | 0
6.0 | FOUNDATION | 0 | 0 | 0 |  |  | 0% | 0 | 0
6.1 | Anchor Bolts |  |  | 0 |  |  | 0% | 0 | 0
6.2 | Bulkheads |  |  | 0 |  |  | 0% | 0 | 0
6.3 | Crawlspace Vapor Barrier |  |  | 0 |  |  | 0% | 0 | 0
6.4 | Crawlspace Vents |  |  | 0 |  |  | 0% | 0 | 0
6.5 | Dam Proofing |  |  | 0 |  |  | 0% | 0 | 0
6.6 | Exterior Foundation Insulation |  |  | 0 |  |  | 0% | 0 | 0
6.7 | Exterior Insulation Coating |  |  | 0 |  |  | 0% | 0 | 0
6.8 | Footings |  |  | 0 |  |  | 0% | 0 | 0
6.9 | Foundation - Drain Board |  |  | 0 |  |  | 0% | 0 | 0
6.10 | Foundation - Walls |  |  | 0 |  |  | 0% | 0 | 0
6.11 | Foundation - Windows |  |  | 0 |  |  | 0% | 0 | 0
6.12 | Grade Beams |  |  | 0 |  |  | 0% | 0 | 0
6.13 | Hold Downs |  |  | 0 |  |  | 0% | 0 | 0
6.14 | Pads |  |  | 0 |  |  | 0% | 0 | 0
6.15 | Piers |  |  | 0 |  |  | 0% | 0 | 0
6.16 | Slab - Basement |  |  | 0 |  |  | 0% | 0 | 0
6.17 | Slab - Foundation |  |  | 0 |  |  | 0% | 0 | 0
6.18 | Slab - Garage |  |  | 0 |  |  | 0% | 0 | 0
6.19 | Slab Insulation |  |  | 0 |  |  | 0% | 0 | 0
6.20 | Steel Reinforcing |  |  | 0 |  |  | 0% | 0 | 0
6.21 | Stem Walls |  |  | 0 |  |  | 0% | 0 | 0
6.22 | Sub-Slab Vapor Barrier |  |  | 0 |  |  | 0% | 0 | 0
6.23 | Sump Pump |  |  | 0 |  |  | 0% | 0 | 0
6.24 | Waterproofing |  |  | 0 |  |  | 0% | 0 | 0
6.25 |  |  |  | 0 |  |  | 0% | 0 | 0
6.26 |  |  |  | 0 |  |  | 0% | 0 | 0
6.27 |  |  |  | 0 |  |  | 0% | 0 | 0
6.28 |  |  |  | 0 |  |  | 0% | 0 | 0
7.0 | ROUGH FRAMING | 0 | 0 | 0 |  |  | 0% | 0 | 0
7.1 | Exterior Walls |  |  | 0 |  |  | 0% | 0 | 0
7.2 | Fasteners / Nails / Screws |  |  | 0 |  |  | 0% | 0 | 0
7.3 | Floor Framing |  |  | 0 |  |  | 0% | 0 | 0
7.4 | Interior Walls |  |  | 0 |  |  | 0% | 0 | 0
7.5 | Lally Columns |  |  | 0 |  |  | 0% | 0 | 0
7.6 | Plaster / Drywall Prep |  |  | 0 |  |  | 0% | 0 | 0
7.7 | Roof Framing / Trusses |  |  | 0 |  |  | 0% | 0 | 0
7.8 | Rough Stairs |  |  | 0 |  |  | 0% | 0 | 0
7.9 | Sheathing |  |  | 0 |  |  | 0% | 0 | 0
7.10 | Sill + Seal |  |  | 0 |  |  | 0% | 0 | 0
7.11 | Steel / Wood Carrying Beam |  |  | 0 |  |  | 0% | 0 | 0
7.12 | Steel Framing Connectors |  |  | 0 |  |  | 0% | 0 | 0
7.13 | Sub-Fascia |  |  | 0 |  |  | 0% | 0 | 0
7.14 | Subflooring |  |  | 0 |  |  | 0% | 0 | 0
7.15 | Labor Costs |  |  | 0 |  |  | 0% | 0 | 0
7.16 |  |  |  | 0 |  |  | 0% | 0 | 0
7.17 |  |  |  | 0 |  |  | 0% | 0 | 0
7.18 |  |  |  | 0 |  |  | 0% | 0 | 0
7.19 |  |  |  | 0 |  |  | 0% | 0 | 0
8.0 | WINDOWS + DOORS (Exterior) | 0 | 0 | 0 |  |  | 0% | 0 | 0
8.1 | Exterior Door - Frames + Sills |  |  | 0 |  |  | 0% | 0 | 0
8.2 | Exterior Door - Hardware |  |  | 0 |  |  | 0% | 0 | 0
8.3 | Exterior Door - Prehung |  |  | 0 |  |  | 0% | 0 | 0
8.4 | Exterior Door - Slabs |  |  | 0 |  |  | 0% | 0 | 0
8.5 | Garage Doors |  |  | 0 |  |  | 0% | 0 | 0
8.6 | Membrane + Flashing |  |  | 0 |  |  | 0% | 0 | 0
8.7 | Sidelights |  |  | 0 |  |  | 0% | 0 | 0
8.8 | Sliding / Hinged Doors |  |  | 0 |  |  | 0% | 0 | 0
8.9 | Transoms |  |  | 0 |  |  | 0% | 0 | 0
8.10 | Windows |  |  | 0 |  |  | 0% | 0 | 0
8.11 | Labor Costs |  |  | 0 |  |  | 0% | 0 | 0
8.12 |  |  |  | 0 |  |  | 0% | 0 | 0
8.13 |  |  |  | 0 |  |  | 0% | 0 | 0
8.14 |  |  |  | 0 |  |  | 0% | 0 | 0
8.15 |  |  |  | 0 |  |  | 0% | 0 | 0
9.0 | FINISH - EXTERIOR | 0 | 0 | 0 |  |  | 0% | 0 | 0
9.1 | Foam Sheathing |  |  | 0 |  |  | 0% | 0 | 0
9.2 | Weather Barrier |  |  | 0 |  |  | 0% | 0 | 0
9.3 | Membrane + Flashing |  |  | 0 |  |  | 0% | 0 | 0
9.4 | Siding |  |  | 0 |  |  | 0% | 0 | 0
9.5 | Veneer |  |  | 0 |  |  | 0% | 0 | 0
9.6 | Stucco |  |  | 0 |  |  | 0% | 0 | 0
9.7 | Fascia |  |  | 0 |  |  | 0% | 0 | 0
9.8 | Soffit |  |  | 0 |  |  | 0% | 0 | 0
9.9 | Frieze |  |  | 0 |  |  | 0% | 0 | 0
9.10 | Corner Boards |  |  | 0 |  |  | 0% | 0 | 0
9.11 | Water Table |  |  | 0 |  |  | 0% | 0 | 0
9.12 | Soffit / Gable Vents |  |  | 0 |  |  | 0% | 0 | 0
9.13 | Trim - Windows |  |  | 0 |  |  | 0% | 0 | 0
9.14 | Trim - Doors |  |  | 0 |  |  | 0% | 0 | 0
9.15 | Trim - Finishing |  |  | 0 |  |  | 0% | 0 | 0
9.16 | Stairs |  |  | 0 |  |  | 0% | 0 | 0
9.17 | Landing |  |  | 0 |  |  | 0% | 0 | 0
9.18 | Paint |  |  | 0 |  |  | 0% | 0 | 0
9.19 | Stain |  |  | 0 |  |  | 0% | 0 | 0
9.20 | Caulk |  |  | 0 |  |  | 0% | 0 | 0
9.21 | Labor Costs |  |  | 0 |  |  | 0% | 0 | 0
9.22 |  |  |  | 0 |  |  | 0% | 0 | 0
9.23 |  |  |  | 0 |  |  | 0% | 0 | 0
9.24 |  |  |  | 0 |  |  | 0% | 0 | 0
9.25 |  |  |  | 0 |  |  | 0% | 0 | 0
10.0 | ROOFING | 0 | 0 | 0 |  |  | 0% | 0 | 0
10.1 | Drip Edge |  |  | 0 |  |  | 0% | 0 | 0
10.2 | Gutters + Downspouts |  |  | 0 |  |  | 0% | 0 | 0
10.3 | Installation / Labor |  |  | 0 |  |  | 0% | 0 | 0
10.4 | Membrane + Flashing |  |  | 0 |  |  | 0% | 0 | 0
10.5 | Ridge & Roof Vents |  |  | 0 |  |  | 0% | 0 | 0
10.6 | Skylights |  |  | 0 |  |  | 0% | 0 | 0
10.7 | Underlayment |  |  | 0 |  |  | 0% | 0 | 0
10.8 |  |  |  | 0 |  |  | 0% | 0 | 0
10.9 |  |  |  | 0 |  |  | 0% | 0 | 0
10.10 |  |  |  | 0 |  |  | 0% | 0 | 0
10.11 |  |  |  | 0 |  |  | 0% | 0 | 0
11.0 | MASONRY / PAVING | 0 | 0 | 0 |  |  | 0% | 0 | 0
11.1 | Driveway |  |  | 0 |  |  | 0% | 0 | 0
11.2 | Walkways |  |  | 0 |  |  | 0% | 0 | 0
11.3 | Chimneys |  |  | 0 |  |  | 0% | 0 | 0
11.4 | Stairs - Exterior |  |  | 0 |  |  | 0% | 0 | 0
11.5 | Patios |  |  | 0 |  |  | 0% | 0 | 0
11.6 | Fireplaces + Hearths |  |  | 0 |  |  | 0% | 0 | 0
11.7 |  |  |  | 0 |  |  | 0% | 0 | 0
11.8 |  |  |  | 0 |  |  | 0% | 0 | 0
11.9 |  |  |  | 0 |  |  | 0% | 0 | 0
11.10 |  |  |  | 0 |  |  | 0% | 0 | 0
12.0 | PORCHES + DECKS | 0 | 0 | 0 |  |  | 0% | 0 | 0
12.1 | Porch - Open |  |  | 0 |  |  | 0% | 0 | 0
12.2 | Porch - Screened |  |  | 0 |  |  | 0% | 0 | 0
12.3 | Deck - Composite |  |  | 0 |  |  | 0% | 0 | 0
12.4 | Deck - Wood |  |  | 0 |  |  | 0% | 0 | 0
12.5 | Fencing |  |  | 0 |  |  | 0% | 0 | 0
12.6 | Railings |  |  | 0 |  |  | 0% | 0 | 0
12.7 | Outdoor Built-Ins |  |  | 0 |  |  | 0% | 0 | 0
12.8 | Additional Structures |  |  | 0 |  |  | 0% | 0 | 0
12.9 |  |  |  | 0 |  |  | 0% | 0 | 0
12.10 |  |  |  | 0 |  |  | 0% | 0 | 0
12.11 |  |  |  | 0 |  |  | 0% | 0 | 0
12.12 |  |  |  | 0 |  |  | 0% | 0 | 0
13.0 | INSULATION + AIR SEALING | 0 | 0 | 0 |  |  | 0% | 0 | 0
13.1 | Air Sealing |  |  | 0 |  |  | 0% | 0 | 0
13.2 | Blower Door |  |  | 0 |  |  | 0% | 0 | 0
13.3 | Infrared |  |  | 0 |  |  | 0% | 0 | 0
13.4 | Insulation - Basement Interior |  |  | 0 |  |  | 0% | 0 | 0
13.5 | Insulation - Crawlspace |  |  | 0 |  |  | 0% | 0 | 0
13.6 | Insulation - Foam Board |  |  | 0 |  |  | 0% | 0 | 0
13.7 | Insulation - Roof / Attic |  |  | 0 |  |  | 0% | 0 | 0
13.8 | Insulation - Spray Foam |  |  | 0 |  |  | 0% | 0 | 0
13.9 | Insulation - Wall Cavity |  |  | 0 |  |  | 0% | 0 | 0
13.10 | Roof / Eave Baffles |  |  | 0 |  |  | 0% | 0 | 0
13.11 |  |  |  | 0 |  |  | 0% | 0 | 0
13.12 |  |  |  | 0 |  |  | 0% | 0 | 0
13.13 |  |  |  | 0 |  |  | 0% | 0 | 0
13.14 |  |  |  | 0 |  |  | 0% | 0 | 0
14.0 | PLUMBING | 0 | 0 | 0 |  |  | 0% | 0 | 0
14.1 | Drain |  |  | 0 |  |  | 0% | 0 | 0
14.2 | Waste |  |  | 0 |  |  | 0% | 0 | 0
14.3 | Vent |  |  | 0 |  |  | 0% | 0 | 0
14.4 | Piping - Water Supply |  |  | 0 |  |  | 0% | 0 | 0
14.5 | Piping - Gas |  |  | 0 |  |  | 0% | 0 | 0
14.6 | Water Heater |  |  | 0 |  |  | 0% | 0 | 0
14.7 | Water Treatment |  |  | 0 |  |  | 0% | 0 | 0
14.8 | Toilets |  |  | 0 |  |  | 0% | 0 | 0
14.9 | Tubs |  |  | 0 |  |  | 0% | 0 | 0
14.10 | Sinks |  |  | 0 |  |  | 0% | 0 | 0
14.11 | Showers |  |  | 0 |  |  | 0% | 0 | 0
14.12 | Faucets |  |  | 0 |  |  | 0% | 0 | 0
14.13 | Mixing Valves |  |  | 0 |  |  | 0% | 0 | 0
14.14 | Shower Heads |  |  | 0 |  |  | 0% | 0 | 0
14.15 | Disposal |  |  | 0 |  |  | 0% | 0 | 0
14.16 |  |  |  | 0 |  |  | 0% | 0 | 0
14.17 |  |  |  | 0 |  |  | 0% | 0 | 0
14.18 |  |  |  | 0 |  |  | 0% | 0 | 0
14.19 |  |  |  | 0 |  |  | 0% | 0 | 0
15.0 | ELECTRICAL | 0 | 0 | 0 |  |  | 0% | 0 | 0
15.1 | Service Panels |  |  | 0 |  |  | 0% | 0 | 0
15.2 | Sub-Panels |  |  | 0 |  |  | 0% | 0 | 0
15.3 | Rough Wiring |  |  | 0 |  |  | 0% | 0 | 0
15.4 | Phone / Cable / Internet Wiring |  |  | 0 |  |  | 0% | 0 | 0
15.5 | Lighting Fixtures |  |  | 0 |  |  | 0% | 0 | 0
15.6 | Low-Voltage Fixtures |  |  | 0 |  |  | 0% | 0 | 0
15.7 | Low-Voltage Transformers |  |  | 0 |  |  | 0% | 0 | 0
15.8 | Outlets |  |  | 0 |  |  | 0% | 0 | 0
15.9 | Switches |  |  | 0 |  |  | 0% | 0 | 0
15.10 | Dimmers |  |  | 0 |  |  | 0% | 0 | 0
15.11 | Lighting Control System |  |  | 0 |  |  | 0% | 0 | 0
15.12 | Doorbell |  |  | 0 |  |  | 0% | 0 | 0
15.13 | Smoke + CO2 Alarms |  |  | 0 |  |  | 0% | 0 | 0
15.14 | Intercom System |  |  | 0 |  |  | 0% | 0 | 0
15.15 | Security System |  |  | 0 |  |  | 0% | 0 | 0
15.16 | Home Theater |  |  | 0 |  |  | 0% | 0 | 0
15.17 | Home Entertainment System |  |  | 0 |  |  | 0% | 0 | 0
15.18 |  |  |  | 0 |  |  | 0% | 0 | 0
15.19 |  |  |  | 0 |  |  | 0% | 0 | 0
15.20 |  |  |  | 0 |  |  | 0% | 0 | 0
15.21 |  |  |  | 0 |  |  | 0% | 0 | 0
16.0 | HVAC | 0 | 0 | 0 |  |  | 0% | 0 | 0
16.1 | Air Handler |  |  | 0 |  |  | 0% | 0 | 0
16.2 | Boiler |  |  | 0 |  |  | 0% | 0 | 0
16.3 | Central AC |  |  | 0 |  |  | 0% | 0 | 0
16.4 | Ductwork |  |  | 0 |  |  | 0% | 0 | 0
16.5 | Furnace / Heat Pump |  |  | 0 |  |  | 0% | 0 | 0
16.6 | Grilles |  |  | 0 |  |  | 0% | 0 | 0
16.7 | HVAC Controls |  |  | 0 |  |  | 0% | 0 | 0
16.8 | Piping |  |  | 0 |  |  | 0% | 0 | 0
16.9 | Radiators |  |  | 0 |  |  | 0% | 0 | 0
16.10 | Registers |  |  | 0 |  |  | 0% | 0 | 0
16.11 | Solar Hot Water |  |  | 0 |  |  | 0% | 0 | 0
16.12 | Whole-House Ventilation |  |  | 0 |  |  | 0% | 0 | 0
16.13 |  |  |  | 0 |  |  | 0% | 0 | 0
16.14 |  |  |  | 0 |  |  | 0% | 0 | 0
16.15 |  |  |  | 0 |  |  | 0% | 0 | 0
16.16 |  |  |  | 0 |  |  | 0% | 0 | 0
17.0 | DRYWALL + PLASTER | 0 | 0 | 0 |  |  | 0% | 0 | 0
17.1 | Walls |  |  | 0 |  |  | 0% | 0 | 0
17.2 | Ceilings |  |  | 0 |  |  | 0% | 0 | 0
17.3 | Soffits |  |  | 0 |  |  | 0% | 0 | 0
17.4 | Decorative Plaster |  |  | 0 |  |  | 0% | 0 | 0
17.5 | Labor Costs |  |  | 0 |  |  | 0% | 0 | 0
17.6 |  |  |  | 0 |  |  | 0% | 0 | 0
17.7 |  |  |  | 0 |  |  | 0% | 0 | 0
17.8 |  |  |  | 0 |  |  | 0% | 0 | 0
17.9 |  |  |  | 0 |  |  | 0% | 0 | 0
18.0 | FINISH - INTERIOR | 0 | 0 | 0 |  |  | 0% | 0 | 0
18.1 | Built-In Cabinets |  |  | 0 |  |  | 0% | 0 | 0
18.2 | Built-In Shelving |  |  | 0 |  |  | 0% | 0 | 0
18.3 | Ceilings - Function |  |  | 0 |  |  | 0% | 0 | 0
18.4 | Ceilings - Decorative |  |  | 0 |  |  | 0% | 0 | 0
18.5 | Closet Hardware |  |  | 0 |  |  | 0% | 0 | 0
18.6 | Closet Shelving |  |  | 0 |  |  | 0% | 0 | 0
18.7 | Flooring - Carpet |  |  | 0 |  |  | 0% | 0 | 0
18.8 | Flooring - Tile / Stone Materials |  |  | 0 |  |  | 0% | 0 | 0
18.9 | Flooring - Tile / Stone Prep |  |  | 0 |  |  | 0% | 0 | 0
18.10 | Flooring - Vinyl |  |  | 0 |  |  | 0% | 0 | 0
18.11 | Flooring - Wood |  |  | 0 |  |  | 0% | 0 | 0
18.12 | Interior Door - Frames + Thresholds |  |  | 0 |  |  | 0% | 0 | 0
18.13 | Interior Door - Hardware |  |  | 0 |  |  | 0% | 0 | 0
18.14 | Interior Door - Prehung |  |  | 0 |  |  | 0% | 0 | 0
18.15 | Interior Door - Slabs |  |  | 0 |  |  | 0% | 0 | 0
18.16 | Interior Paint |  |  | 0 |  |  | 0% | 0 | 0
18.17 | Interior Stain |  |  | 0 |  |  | 0% | 0 | 0
18.18 | Paneling |  |  | 0 |  |  | 0% | 0 | 0
18.19 | Stairs / Railings / Newels |  |  | 0 |  |  | 0% | 0 | 0
18.20 | Wainscoting |  |  | 0 |  |  | 0% | 0 | 0
18.21 | Labor Costs |  |  | 0 |  |  | 0% | 0 | 0
18.22 |  |  |  | 0 |  |  | 0% | 0 | 0
18.23 |  |  |  | 0 |  |  | 0% | 0 | 0
18.24 |  |  |  | 0 |  |  | 0% | 0 | 0
18.25 |  |  |  | 0 |  |  | 0% | 0 | 0
19.0 | KITCHEN | 0 | 0 | 0 |  |  | 0% | 0 | 0
19.1 | Accessories |  |  | 0 |  |  | 0% | 0 | 0
19.2 | Backsplash |  |  | 0 |  |  | 0% | 0 | 0
19.3 | Built-Ins |  |  | 0 |  |  | 0% | 0 | 0
19.4 | Cabinets |  |  | 0 |  |  | 0% | 0 | 0
19.5 | Cabinets - Hardware |  |  | 0 |  |  | 0% | 0 | 0
19.6 | Countertops |  |  | 0 |  |  | 0% | 0 | 0
19.7 | Shelving |  |  | 0 |  |  | 0% | 0 | 0
19.8 | Tile / Stone |  |  | 0 |  |  | 0% | 0 | 0
19.9 | Labor Costs |  |  | 0 |  |  | 0% | 0 | 0
19.10 |  |  |  | 0 |  |  | 0% | 0 | 0
19.11 |  |  |  | 0 |  |  | 0% | 0 | 0
19.12 |  |  |  | 0 |  |  | 0% | 0 | 0
19.13 |  |  |  | 0 |  |  | 0% | 0 | 0
20.0 | BATH | 0 | 0 | 0 |  |  | 0% | 0 | 0
20.1 | Accessories |  |  | 0 |  |  | 0% | 0 | 0
20.2 | Backsplash |  |  | 0 |  |  | 0% | 0 | 0
20.3 | Built-Ins |  |  | 0 |  |  | 0% | 0 | 0
20.4 | Cabinets |  |  | 0 |  |  | 0% | 0 | 0
20.5 | Cabinets - Hardware |  |  | 0 |  |  | 0% | 0 | 0
20.6 | Countertops |  |  | 0 |  |  | 0% | 0 | 0
20.7 | Medicine Cabinets |  |  | 0 |  |  | 0% | 0 | 0
20.8 | Mirrors |  |  | 0 |  |  | 0% | 0 | 0
20.9 | Raised Tub Platform |  |  | 0 |  |  | 0% | 0 | 0
20.10 | Shelving |  |  | 0 |  |  | 0% | 0 | 0
20.11 | Shower Enclosure |  |  | 0 |  |  | 0% | 0 | 0
20.12 | Tile / Stone |  |  | 0 |  |  | 0% | 0 | 0
20.13 | Tub Enclosure |  |  | 0 |  |  | 0% | 0 | 0
20.14 | Labor Costs |  |  | 0 |  |  | 0% | 0 | 0
20.15 |  |  |  | 0 |  |  | 0% | 0 | 0
20.16 |  |  |  | 0 |  |  | 0% | 0 | 0
20.17 |  |  |  | 0 |  |  | 0% | 0 | 0
20.18 |  |  |  | 0 |  |  | 0% | 0 | 0
21.0 | APPLIANCES | 0 | 0 | 0 |  |  | 0% | 0 | 0
21.1 | Cooktop |  |  | 0 |  |  | 0% | 0 | 0
21.2 | Deep Freeze |  |  | 0 |  |  | 0% | 0 | 0
21.3 | Dishwasher |  |  | 0 |  |  | 0% | 0 | 0
21.4 | Microwave Oven |  |  | 0 |  |  | 0% | 0 | 0
21.5 | Oven |  |  | 0 |  |  | 0% | 0 | 0
21.6 | Range Hood |  |  | 0 |  |  | 0% | 0 | 0
21.7 | Refrigerator |  |  | 0 |  |  | 0% | 0 | 0
21.8 | Washer + Dryer |  |  | 0 |  |  | 0% | 0 | 0
21.9 |  |  |  | 0 |  |  | 0% | 0 | 0
21.10 |  |  |  | 0 |  |  | 0% | 0 | 0
21.11 |  |  |  | 0 |  |  | 0% | 0 | 0
21.12 |  |  |  | 0 |  |  | 0% | 0 | 0
22.0 | OTHER | 0 | 0 | 0 |  |  | 0% | 0 | 0
22.1 |  |  |  | 0 |  |  | 0% | 0 | 0
22.2 |  |  |  | 0 |  |  | 0% | 0 | 0
22.3 |  |  |  | 0 |  |  | 0% | 0 | 0
22.4 |  |  |  | 0 |  |  | 0% | 0 | 0
22.5 |  |  |  | 0 |  |  | 0% | 0 | 0
22.6 |  |  |  | 0 |  |  | 0% | 0 | 0
22.7 |  |  |  | 0 |  |  | 0% | 0 | 0
22.8 |  |  |  | 0 |  |  | 0% | 0 | 0
22.9 |  |  |  | 0 |  |  | 0% | 0 | 0
22.10 |  |  |  | 0 |  |  | 0% | 0 | 0
22.11 |  |  |  | 0 |  |  | 0% | 0 | 0
22.12 |  |  |  | 0 |  |  | 0% | 0 | 0
22.13 |  |  |  | 0 |  |  | 0% | 0 | 0
22.14 |  |  |  | 0 |  |  | 0% | 0 | 0
22.15 |  |  |  | 0 |  |  | 0% | 0 | 0
22.16 |  |  |  | 0 |  |  | 0% | 0 | 0
22.17 |  |  |  | 0 |  |  | 100% | 0 | 0
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Construction Budget
Residential Construction Budget Template
Job Title |  |  |  |  | Project Manager | Start Date | End Date
Location
|  | –––––––––––––––– Budget –––––––––––––––– |  |  | –––––––––––––––– Contingency ––––––––––––––––
|  | Projected Total | Actual Total | Variance | Contingency Percentage | Budget Total w/ Contingency | Variance w/ Contingency | Current Paid Total | Amount Due Total
|  | 0 | 0 | 0 | 10% | 0 | 0 | 0 | 0
WBS | Category & Items | Projected Subtotal | Actual Subtotal | Variance | Party Responsible Vendor, Contractor, etc. | Status | Pct of Task Complete | Current Paid | Amount Due | Comments
1.0 | PLANNING | 0 | 0 | 0 |  |  | 0% | 0 | 0
1.1 | Admin Fees |  |  | 0 |  |  | 0% |  | 0
1.2 | Engineering |  |  | 0 |  |  | 0% |  | 0
1.3 | Financing Costs |  |  | 0 |  |  | 0% |  | 0
1.4 | Permit - Building |  |  | 0 |  |  | 0% |  | 0
1.5 | Permit - Zoning |  |  | 0 |  |  | 0% |  | 0
1.6 | Survey |  |  | 0 |  |  | 0% |  | 0
1.7 |  |  |  | 0 |  |  | 0% |  | 0
1.8 |  |  |  | 0 |  |  | 0% |  | 0
1.9 |  |  |  | 0 |  |  | 0% |  | 0
1.10 |  |  |  | 0 |  |  | 0% |  | 0
2.0 | SITE PREP | 0 | 0 | 0 |  |  | 0% | 0 | 0
2.1 | Dumpster / Waste Removal |  |  | 0 |  |  | 0% |  | 0
2.2 | Equipment Rental |  |  | 0 |  |  | 0% |  | 0
2.3 | Lot Clearing |  |  | 0 |  |  | 0% |  | 0
2.4 | Portable Restroom Facilities |  |  | 0 |  |  | 0% |  | 0
2.5 | Remodel - Demo |  |  | 0 |  |  | 0% |  | 0
2.6 | Remodel - Dust Control |  |  | 0 |  |  | 0% |  | 0
2.7 | Site Access |  |  | 0 |  |  | 0% |  | 0
2.8 | Temporary Power |  |  | 0 |  |  | 0% |  | 0
2.9 | Tool Rental |  |  | 0 |  |  | 0% |  | 0
2.10 |  |  |  | 0 |  |  | 0% |  | 0
2.11 |  |  |  | 0 |  |  | 0% |  | 0
2.12 |  |  |  | 0 |  |  | 0% |  | 0
2.13 |  |  |  | 0 |  |  | 0% |  | 0
3.0 | EARTHWORK / EXCAVATION | 0 | 0 | 0 |  |  | 0% | 0 | 0
3.1 | Backfill |  |  | 0 |  |  | 0% |  | 0
3.2 | Foundation - Excavation |  |  | 0 |  |  | 0% |  | 0
3.3 | Foundation - Footing Drains |  |  | 0 |  |  | 0% |  | 0
3.4 | Rough Grading |  |  | 0 |  |  | 0% |  | 0
3.5 | Seeding / Sodding |  |  | 0 |  |  | 0% |  | 0
3.6 | Site Drainage - Additional |  |  | 0 |  |  | 0% |  | 0
3.7 |  |  |  | 0 |  |  | 0% |  | 0
3.8 |  |  |  | 0 |  |  | 0% |  | 0
3.9 |  |  |  | 0 |  |  | 0% |  | 0
3.10 |  |  |  | 0 |  |  | 0% |  | 0
4.0 | UTILITIES | 0 | 0 | 0 |  |  | 0% | 0 | 0
4.1 | Electrical - Connection |  |  | 0 |  |  | 0% |  | 0
4.2 | Electrical - Install |  |  | 0 |  |  | 0% |  | 0
4.3 | Electrical - Permit |  |  | 0 |  |  | 0% |  | 0
4.4 | Gas - Connection |  |  | 0 |  |  | 0% |  | 0
4.5 | Gas - Hookup |  |  | 0 |  |  | 0% |  | 0
4.6 | Gas - Permit |  |  | 0 |  |  | 0% |  | 0
4.7 | Oil Tank Install |  |  | 0 |  |  | 0% |  | 0
4.8 | Sewer - Tap Fees & Hookup |  |  | 0 |  |  | 0% |  | 0
4.9 | Telecom - Hookup |  |  | 0 |  |  | 0% |  | 0
4.10 | Telecom - Install |  |  | 0 |  |  | 0% |  | 0
4.11 | Water - Tap Fees & Hookup |  |  | 0 |  |  | 0% |  | 0
4.12 |  |  |  | 0 |  |  | 0% |  | 0
4.13 |  |  |  | 0 |  |  | 0% |  | 0
4.14 |  |  |  | 0 |  |  | 0% |  | 0
4.15 |  |  |  | 0 |  |  | 0% |  | 0
5.0 | WATER + SEWER | 0 | 0 | 0 |  |  | 0% | 0 | 0
5.1 | High Water Table Dewatering |  |  | 0 |  |  | 0% |  | 0
5.2 | Perc Test |  |  | 0 |  |  | 0% |  | 0
5.3 | Plumbing to House |  |  | 0 |  |  | 0% |  | 0
5.4 | Pressure Tank |  |  | 0 |  |  | 0% |  | 0
5.5 | Pump |  |  | 0 |  |  | 0% |  | 0
5.6 | Septic - Design |  |  | 0 |  |  | 0% |  | 0
5.7 | Septic - Fees |  |  | 0 |  |  | 0% |  | 0
5.8 | Septic - Inspection |  |  | 0 |  |  | 0% |  | 0
5.9 | Septic - Permits |  |  | 0 |  |  | 0% |  | 0
5.10 | Septic - Tie to House |  |  | 0 |  |  | 0% |  | 0
5.11 | Soil Test |  |  | 0 |  |  | 0% |  | 0
5.12 | Trenching |  |  | 0 |  |  | 0% |  | 0
5.13 | Well |  |  | 0 |  |  | 0% |  | 0
5.14 | Well - Fees |  |  | 0 |  |  | 0% |  | 0
5.15 | Well - Permits |  |  | 0 |  |  | 0% |  | 0
5.16 |  |  |  | 0 |  |  | 0% |  | 0
5.17 |  |  |  | 0 |  |  | 0% |  | 0
5.18 |  |  |  | 0 |  |  | 0% |  | 0
5.19 |  |  |  | 0 |  |  | 0% |  | 0
6.0 | FOUNDATION | 0 | 0 | 0 |  |  | 0% | 0 | 0
6.1 | Anchor Bolts |  |  | 0 |  |  | 0% |  | 0
6.2 | Bulkheads |  |  | 0 |  |  | 0% |  | 0
6.3 | Crawlspace Vapor Barrier |  |  | 0 |  |  | 0% |  | 0
6.4 | Crawlspace Vents |  |  | 0 |  |  | 0% |  | 0
6.5 | Dam Proofing |  |  | 0 |  |  | 0% |  | 0
6.6 | Exterior Foundation Insulation |  |  | 0 |  |  | 0% |  | 0
6.7 | Exterior Insulation Coating |  |  | 0 |  |  | 0% |  | 0
6.8 | Footings |  |  | 0 |  |  | 0% |  | 0
6.9 | Foundation - Drain Board |  |  | 0 |  |  | 0% |  | 0
6.10 | Foundation - Walls |  |  | 0 |  |  | 0% |  | 0
6.11 | Foundation - Windows |  |  | 0 |  |  | 0% |  | 0
6.12 | Grade Beams |  |  | 0 |  |  | 0% |  | 0
6.13 | Hold Downs |  |  | 0 |  |  | 0% |  | 0
6.14 | Pads |  |  | 0 |  |  | 0% |  | 0
6.15 | Piers |  |  | 0 |  |  | 0% |  | 0
6.16 | Slab - Basement |  |  | 0 |  |  | 0% |  | 0
6.17 | Slab - Foundation |  |  | 0 |  |  | 0% |  | 0
6.18 | Slab - Garage |  |  | 0 |  |  | 0% |  | 0
6.19 | Slab Insulation |  |  | 0 |  |  | 0% |  | 0
6.20 | Steel Reinforcing |  |  | 0 |  |  | 0% |  | 0
6.21 | Stem Walls |  |  | 0 |  |  | 0% |  | 0
6.22 | Sub-Slab Vapor Barrier |  |  | 0 |  |  | 0% |  | 0
6.23 | Sump Pump |  |  | 0 |  |  | 0% |  | 0
6.24 | Waterproofing |  |  | 0 |  |  | 0% |  | 0
6.25 |  |  |  | 0 |  |  | 0% |  | 0
6.26 |  |  |  | 0 |  |  | 0% |  | 0
6.27 |  |  |  | 0 |  |  | 0% |  | 0
6.28 |  |  |  | 0 |  |  | 0% |  | 0
7.0 | ROUGH FRAMING | 0 | 0 | 0 |  |  | 0% | 0 | 0
7.1 | Exterior Walls |  |  | 0 |  |  | 0% |  | 0
7.2 | Fasteners / Nails / Screws |  |  | 0 |  |  | 0% |  | 0
7.3 | Floor Framing |  |  | 0 |  |  | 0% |  | 0
7.4 | Interior Walls |  |  | 0 |  |  | 0% |  | 0
7.5 | Lally Columns |  |  | 0 |  |  | 0% |  | 0
7.6 | Plaster / Drywall Prep |  |  | 0 |  |  | 0% |  | 0
7.7 | Roof Framing / Trusses |  |  | 0 |  |  | 0% |  | 0
7.8 | Rough Stairs |  |  | 0 |  |  | 0% |  | 0
7.9 | Sheathing |  |  | 0 |  |  | 0% |  | 0
7.10 | Sill + Seal |  |  | 0 |  |  | 0% |  | 0
7.11 | Steel / Wood Carrying Beam |  |  | 0 |  |  | 0% |  | 0
7.12 | Steel Framing Connectors |  |  | 0 |  |  | 0% |  | 0
7.13 | Sub-Fascia |  |  | 0 |  |  | 0% |  | 0
7.14 | Subflooring |  |  | 0 |  |  | 0% |  | 0
7.15 | Labor Costs |  |  | 0 |  |  | 0% |  | 0
7.16 |  |  |  | 0 |  |  | 0% |  | 0
7.17 |  |  |  | 0 |  |  | 0% |  | 0
7.18 |  |  |  | 0 |  |  | 0% |  | 0
7.19 |  |  |  | 0 |  |  | 0% |  | 0
8.0 | WINDOWS + DOORS (Exterior) | 0 | 0 | 0 |  |  | 0% | 0 | 0
8.1 | Exterior Door - Frames + Sills |  |  | 0 |  |  | 0% |  | 0
8.2 | Exterior Door - Hardware |  |  | 0 |  |  | 0% |  | 0
8.3 | Exterior Door - Prehung |  |  | 0 |  |  | 0% |  | 0
8.4 | Exterior Door - Slabs |  |  | 0 |  |  | 0% |  | 0
8.5 | Garage Doors |  |  | 0 |  |  | 0% |  | 0
8.6 | Membrane + Flashing |  |  | 0 |  |  | 0% |  | 0
8.7 | Sidelights |  |  | 0 |  |  | 0% |  | 0
8.8 | Sliding / Hinged Doors |  |  | 0 |  |  | 0% |  | 0
8.9 | Transoms |  |  | 0 |  |  | 0% |  | 0
8.10 | Windows |  |  | 0 |  |  | 0% |  | 0
8.11 | Labor Costs |  |  | 0 |  |  | 0% |  | 0
8.12 |  |  |  | 0 |  |  | 0% |  | 0
8.13 |  |  |  | 0 |  |  | 0% |  | 0
8.14 |  |  |  | 0 |  |  | 0% |  | 0
8.15 |  |  |  | 0 |  |  | 0% |  | 0
9.0 | FINISH - EXTERIOR | 0 | 0 | 0 |  |  | 0% | 0 | 0
9.1 | Foam Sheathing |  |  | 0 |  |  | 0% |  | 0
9.2 | Weather Barrier |  |  | 0 |  |  | 0% |  | 0
9.3 | Membrane + Flashing |  |  | 0 |  |  | 0% |  | 0
9.4 | Siding |  |  | 0 |  |  | 0% |  | 0
9.5 | Veneer |  |  | 0 |  |  | 0% |  | 0
9.6 | Stucco |  |  | 0 |  |  | 0% |  | 0
9.7 | Fascia |  |  | 0 |  |  | 0% |  | 0
9.8 | Soffit |  |  | 0 |  |  | 0% |  | 0
9.9 | Frieze |  |  | 0 |  |  | 0% |  | 0
9.10 | Corner Boards |  |  | 0 |  |  | 0% |  | 0
9.11 | Water Table |  |  | 0 |  |  | 0% |  | 0
9.12 | Soffit / Gable Vents |  |  | 0 |  |  | 0% |  | 0
9.13 | Trim - Windows |  |  | 0 |  |  | 0% |  | 0
9.14 | Trim - Doors |  |  | 0 |  |  | 0% |  | 0
9.15 | Trim - Finishing |  |  | 0 |  |  | 0% |  | 0
9.16 | Stairs |  |  | 0 |  |  | 0% |  | 0
9.17 | Landing |  |  | 0 |  |  | 0% |  | 0
9.18 | Paint |  |  | 0 |  |  | 0% |  | 0
9.19 | Stain |  |  | 0 |  |  | 0% |  | 0
9.20 | Caulk |  |  | 0 |  |  | 0% |  | 0
9.21 | Labor Costs |  |  | 0 |  |  | 0% |  | 0
9.22 |  |  |  | 0 |  |  | 0% |  | 0
9.23 |  |  |  | 0 |  |  | 0% |  | 0
9.24 |  |  |  | 0 |  |  | 0% |  | 0
9.25 |  |  |  | 0 |  |  | 0% |  | 0
10.0 | ROOFING | 0 | 0 | 0 |  |  | 0% | 0 | 0
10.1 | Drip Edge |  |  | 0 |  |  | 0% |  | 0
10.2 | Gutters + Downspouts |  |  | 0 |  |  | 0% |  | 0
10.3 | Installation / Labor |  |  | 0 |  |  | 0% |  | 0
10.4 | Membrane + Flashing |  |  | 0 |  |  | 0% |  | 0
10.5 | Ridge & Roof Vents |  |  | 0 |  |  | 0% |  | 0
10.6 | Skylights |  |  | 0 |  |  | 0% |  | 0
10.7 | Underlayment |  |  | 0 |  |  | 0% |  | 0
10.8 |  |  |  | 0 |  |  | 0% |  | 0
10.9 |  |  |  | 0 |  |  | 0% |  | 0
10.10 |  |  |  | 0 |  |  | 0% |  | 0
10.11 |  |  |  | 0 |  |  | 0% |  | 0
11.0 | MASONRY / PAVING | 0 | 0 | 0 |  |  | 0% | 0 | 0
11.1 | Driveway |  |  | 0 |  |  | 0% |  | 0
11.2 | Walkways |  |  | 0 |  |  | 0% |  | 0
11.3 | Chimneys |  |  | 0 |  |  | 0% |  | 0
11.4 | Stairs - Exterior |  |  | 0 |  |  | 0% |  | 0
11.5 | Patios |  |  | 0 |  |  | 0% |  | 0
11.6 | Fireplaces + Hearths |  |  | 0 |  |  | 0% |  | 0
11.7 |  |  |  | 0 |  |  | 0% |  | 0
11.8 |  |  |  | 0 |  |  | 0% |  | 0
11.9 |  |  |  | 0 |  |  | 0% |  | 0
11.10 |  |  |  | 0 |  |  | 0% |  | 0
12.0 | PORCHES + DECKS | 0 | 0 | 0 |  |  | 0% | 0 | 0
12.1 | Porch - Open |  |  | 0 |  |  | 0% |  | 0
12.2 | Porch - Screened |  |  | 0 |  |  | 0% |  | 0
12.3 | Deck - Composite |  |  | 0 |  |  | 0% |  | 0
12.4 | Deck - Wood |  |  | 0 |  |  | 0% |  | 0
12.5 | Fencing |  |  | 0 |  |  | 0% |  | 0
12.6 | Railings |  |  | 0 |  |  | 0% |  | 0
12.7 | Outdoor Built-Ins |  |  | 0 |  |  | 0% |  | 0
12.8 | Additional Structures |  |  | 0 |  |  | 0% |  | 0
12.9 |  |  |  | 0 |  |  | 0% |  | 0
12.10 |  |  |  | 0 |  |  | 0% |  | 0
12.11 |  |  |  | 0 |  |  | 0% |  | 0
12.12 |  |  |  | 0 |  |  | 0% |  | 0
13.0 | INSULATION + AIR SEALING | 0 | 0 | 0 |  |  | 0% | 0 | 0
13.1 | Air Sealing |  |  | 0 |  |  | 0% |  | 0
13.2 | Blower Door |  |  | 0 |  |  | 0% |  | 0
13.3 | Infrared |  |  | 0 |  |  | 0% |  | 0
13.4 | Insulation - Basement Interior |  |  | 0 |  |  | 0% |  | 0
13.5 | Insulation - Crawlspace |  |  | 0 |  |  | 0% |  | 0
13.6 | Insulation - Foam Board |  |  | 0 |  |  | 0% |  | 0
13.7 | Insulation - Roof / Attic |  |  | 0 |  |  | 0% |  | 0
13.8 | Insulation - Spray Foam |  |  | 0 |  |  | 0% |  | 0
13.9 | Insulation - Wall Cavity |  |  | 0 |  |  | 0% |  | 0
13.10 | Roof / Eave Baffles |  |  | 0 |  |  | 0% |  | 0
13.11 |  |  |  | 0 |  |  | 0% |  | 0
13.12 |  |  |  | 0 |  |  | 0% |  | 0
13.13 |  |  |  | 0 |  |  | 0% |  | 0
13.14 |  |  |  | 0 |  |  | 0% |  | 0
14.0 | PLUMBING | 0 | 0 | 0 |  |  | 0% | 0 | 0
14.1 | Drain |  |  | 0 |  |  | 0% |  | 0
14.2 | Waste |  |  | 0 |  |  | 0% |  | 0
14.3 | Vent |  |  | 0 |  |  | 0% |  | 0
14.4 | Piping - Water Supply |  |  | 0 |  |  | 0% |  | 0
14.5 | Piping - Gas |  |  | 0 |  |  | 0% |  | 0
14.6 | Water Heater |  |  | 0 |  |  | 0% |  | 0
14.7 | Water Treatment |  |  | 0 |  |  | 0% |  | 0
14.8 | Toilets |  |  | 0 |  |  | 0% |  | 0
14.9 | Tubs |  |  | 0 |  |  | 0% |  | 0
14.10 | Sinks |  |  | 0 |  |  | 0% |  | 0
14.11 | Showers |  |  | 0 |  |  | 0% |  | 0
14.12 | Faucets |  |  | 0 |  |  | 0% |  | 0
14.13 | Mixing Valves |  |  | 0 |  |  | 0% |  | 0
14.14 | Shower Heads |  |  | 0 |  |  | 0% |  | 0
14.15 | Disposal |  |  | 0 |  |  | 0% |  | 0
14.16 |  |  |  | 0 |  |  | 0% |  | 0
14.17 |  |  |  | 0 |  |  | 0% |  | 0
14.18 |  |  |  | 0 |  |  | 0% |  | 0
14.19 |  |  |  | 0 |  |  | 0% |  | 0
15.0 | ELECTRICAL | 0 | 0 | 0 |  |  | 0% | 0 | 0
15.1 | Service Panels |  |  | 0 |  |  | 0% |  | 0
15.2 | Sub-Panels |  |  | 0 |  |  | 0% |  | 0
15.3 | Rough Wiring |  |  | 0 |  |  | 0% |  | 0
15.4 | Phone / Cable / Internet Wiring |  |  | 0 |  |  | 0% |  | 0
15.5 | Lighting Fixtures |  |  | 0 |  |  | 0% |  | 0
15.6 | Low-Voltage Fixtures |  |  | 0 |  |  | 0% |  | 0
15.7 | Low-Voltage Transformers |  |  | 0 |  |  | 0% |  | 0
15.8 | Outlets |  |  | 0 |  |  | 0% |  | 0
15.9 | Switches |  |  | 0 |  |  | 0% |  | 0
15.10 | Dimmers |  |  | 0 |  |  | 0% |  | 0
15.11 | Lighting Control System |  |  | 0 |  |  | 0% |  | 0
15.12 | Doorbell |  |  | 0 |  |  | 0% |  | 0
15.13 | Smoke + CO2 Alarms |  |  | 0 |  |  | 0% |  | 0
15.14 | Intercom System |  |  | 0 |  |  | 0% |  | 0
15.15 | Security System |  |  | 0 |  |  | 0% |  | 0
15.16 | Home Theater |  |  | 0 |  |  | 0% |  | 0
15.17 | Home Entertainment System |  |  | 0 |  |  | 0% |  | 0
15.18 |  |  |  | 0 |  |  | 0% |  | 0
15.19 |  |  |  | 0 |  |  | 0% |  | 0
15.20 |  |  |  | 0 |  |  | 0% |  | 0
15.21 |  |  |  | 0 |  |  | 0% |  | 0
16.0 | HVAC | 0 | 0 | 0 |  |  | 0% | 0 | 0
16.1 | Air Handler |  |  | 0 |  |  | 0% |  | 0
16.2 | Boiler |  |  | 0 |  |  | 0% |  | 0
16.3 | Central AC |  |  | 0 |  |  | 0% |  | 0
16.4 | Ductwork |  |  | 0 |  |  | 0% |  | 0
16.5 | Furnace / Heat Pump |  |  | 0 |  |  | 0% |  | 0
16.6 | Grilles |  |  | 0 |  |  | 0% |  | 0
16.7 | HVAC Controls |  |  | 0 |  |  | 0% |  | 0
16.8 | Piping |  |  | 0 |  |  | 0% |  | 0
16.9 | Radiators |  |  | 0 |  |  | 0% |  | 0
16.10 | Registers |  |  | 0 |  |  | 0% |  | 0
16.11 | Solar Hot Water |  |  | 0 |  |  | 0% |  | 0
16.12 | Whole-House Ventilation |  |  | 0 |  |  | 0% |  | 0
16.13 |  |  |  | 0 |  |  | 0% |  | 0
16.14 |  |  |  | 0 |  |  | 0% |  | 0
16.15 |  |  |  | 0 |  |  | 0% |  | 0
16.16 |  |  |  | 0 |  |  | 0% |  | 0
17.0 | DRYWALL + PLASTER | 0 | 0 | 0 |  |  | 0% | 0 | 0
17.1 | Walls |  |  | 0 |  |  | 0% |  | 0
17.2 | Ceilings |  |  | 0 |  |  | 0% |  | 0
17.3 | Soffits |  |  | 0 |  |  | 0% |  | 0
17.4 | Decorative Plaster |  |  | 0 |  |  | 0% |  | 0
17.5 | Labor Costs |  |  | 0 |  |  | 0% |  | 0
17.6 |  |  |  | 0 |  |  | 0% |  | 0
17.7 |  |  |  | 0 |  |  | 0% |  | 0
17.8 |  |  |  | 0 |  |  | 0% |  | 0
17.9 |  |  |  | 0 |  |  | 0% |  | 0
18.0 | FINISH - INTERIOR | 0 | 0 | 0 |  |  | 0% | 0 | 0
18.1 | Built-In Cabinets |  |  | 0 |  |  | 0% |  | 0
18.2 | Built-In Shelving |  |  | 0 |  |  | 0% |  | 0
18.3 | Ceilings - Function |  |  | 0 |  |  | 0% |  | 0
18.4 | Ceilings - Decorative |  |  | 0 |  |  | 0% |  | 0
18.5 | Closet Hardware |  |  | 0 |  |  | 0% |  | 0
18.6 | Closet Shelving |  |  | 0 |  |  | 0% |  | 0
18.7 | Flooring - Carpet |  |  | 0 |  |  | 0% |  | 0
18.8 | Flooring - Tile / Stone Materials |  |  | 0 |  |  | 0% |  | 0
18.9 | Flooring - Tile / Stone Prep |  |  | 0 |  |  | 0% |  | 0
18.10 | Flooring - Vinyl |  |  | 0 |  |  | 0% |  | 0
18.11 | Flooring - Wood |  |  | 0 |  |  | 0% |  | 0
18.12 | Interior Door - Frames + Thresholds |  |  | 0 |  |  | 0% |  | 0
18.13 | Interior Door - Hardware |  |  | 0 |  |  | 0% |  | 0
18.14 | Interior Door - Prehung |  |  | 0 |  |  | 0% |  | 0
18.15 | Interior Door - Slabs |  |  | 0 |  |  | 0% |  | 0
18.16 | Interior Paint |  |  | 0 |  |  | 0% |  | 0
18.17 | Interior Stain |  |  | 0 |  |  | 0% |  | 0
18.18 | Paneling |  |  | 0 |  |  | 0% |  | 0
18.19 | Stairs / Railings / Newels |  |  | 0 |  |  | 0% |  | 0
18.20 | Wainscoting |  |  | 0 |  |  | 0% |  | 0
18.21 | Labor Costs |  |  | 0 |  |  | 0% |  | 0
18.22 |  |  |  | 0 |  |  | 0% |  | 0
18.23 |  |  |  | 0 |  |  | 0% |  | 0
18.24 |  |  |  | 0 |  |  | 0% |  | 0
18.25 |  |  |  | 0 |  |  | 0% |  | 0
19.0 | KITCHEN | 0 | 0 | 0 |  |  | 0% | 0 | 0
19.1 | Accessories |  |  | 0 |  |  | 0% |  | 0
19.2 | Backsplash |  |  | 0 |  |  | 0% |  | 0
19.3 | Built-Ins |  |  | 0 |  |  | 0% |  | 0
19.4 | Cabinets |  |  | 0 |  |  | 0% |  | 0
19.5 | Cabinets - Hardware |  |  | 0 |  |  | 0% |  | 0
19.6 | Countertops |  |  | 0 |  |  | 0% |  | 0
19.7 | Shelving |  |  | 0 |  |  | 0% |  | 0
19.8 | Tile / Stone |  |  | 0 |  |  | 0% |  | 0
19.9 | Labor Costs |  |  | 0 |  |  | 0% |  | 0
19.10 |  |  |  | 0 |  |  | 0% |  | 0
19.11 |  |  |  | 0 |  |  | 0% |  | 0
19.12 |  |  |  | 0 |  |  | 0% |  | 0
19.13 |  |  |  | 0 |  |  | 0% |  | 0
20.0 | BATH | 0 | 0 | 0 |  |  | 0% | 0 | 0
20.1 | Accessories |  |  | 0 |  |  | 0% |  | 0
20.2 | Backsplash |  |  | 0 |  |  | 0% |  | 0
20.3 | Built-Ins |  |  | 0 |  |  | 0% |  | 0
20.4 | Cabinets |  |  | 0 |  |  | 0% |  | 0
20.5 | Cabinets - Hardware |  |  | 0 |  |  | 0% |  | 0
20.6 | Countertops |  |  | 0 |  |  | 0% |  | 0
20.7 | Medicine Cabinets |  |  | 0 |  |  | 0% |  | 0
20.8 | Mirrors |  |  | 0 |  |  | 0% |  | 0
20.9 | Raised Tub Platform |  |  | 0 |  |  | 0% |  | 0
20.10 | Shelving |  |  | 0 |  |  | 0% |  | 0
20.11 | Shower Enclosure |  |  | 0 |  |  | 0% |  | 0
20.12 | Tile / Stone |  |  | 0 |  |  | 0% |  | 0
20.13 | Tub Enclosure |  |  | 0 |  |  | 0% |  | 0
20.14 | Labor Costs |  |  | 0 |  |  | 0% |  | 0
20.15 |  |  |  | 0 |  |  | 0% |  | 0
20.16 |  |  |  | 0 |  |  | 0% |  | 0
20.17 |  |  |  | 0 |  |  | 0% |  | 0
20.18 |  |  |  | 0 |  |  | 0% |  | 0
21.0 | APPLIANCES | 0 | 0 | 0 |  |  | 0% | 0 | 0
21.1 | Cooktop |  |  | 0 |  |  | 0% |  | 0
21.2 | Deep Freeze |  |  | 0 |  |  | 0% |  | 0
21.3 | Dishwasher |  |  | 0 |  |  | 0% |  | 0
21.4 | Microwave Oven |  |  | 0 |  |  | 0% |  | 0
21.5 | Oven |  |  | 0 |  |  | 0% |  | 0
21.6 | Range Hood |  |  | 0 |  |  | 0% |  | 0
21.7 | Refrigerator |  |  | 0 |  |  | 0% |  | 0
21.8 | Washer + Dryer |  |  | 0 |  |  | 0% |  | 0
21.9 |  |  |  | 0 |  |  | 0% |  | 0
21.10 |  |  |  | 0 |  |  | 0% |  | 0
21.11 |  |  |  | 0 |  |  | 0% |  | 0
21.12 |  |  |  | 0 |  |  | 0% |  | 0
22.0 | OTHER | 0 | 0 | 0 |  |  | 0% | 0 | 0
22.1 |  |  |  | 0 |  |  | 0% |  | 0
22.2 |  |  |  | 0 |  |  | 0% |  | 0
22.3 |  |  |  | 0 |  |  | 0% |  | 0
22.4 |  |  |  | 0 |  |  | 0% |  | 0
22.5 |  |  |  | 0 |  |  | 0% |  | 0
22.6 |  |  |  | 0 |  |  | 0% |  | 0
22.7 |  |  |  | 0 |  |  | 0% |  | 0
22.8 |  |  |  | 0 |  |  | 0% |  | 0
22.9 |  |  |  | 0 |  |  | 0% |  | 0
22.10 |  |  |  | 0 |  |  | 0% |  | 0
22.11 |  |  |  | 0 |  |  | 0% |  | 0
22.12 |  |  |  | 0 |  |  | 0% |  | 0
22.13 |  |  |  | 0 |  |  | 0% |  | 0
22.14 |  |  |  | 0 |  |  | 0% |  | 0
22.15 |  |  |  | 0 |  |  | 0% |  | 0
22.16 |  |  |  | 0 |  |  | 0% |  | 0
22.17 |  |  |  | 0 |  |  | 100% |  | 0

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.