## EXAMPLE Construction Path
Construction Project Critical Path Dashboard Template Example
Dashboard
Enter information in the Duration, Slack, and Category fields to populate the chart. Gray cells in the table below will auto-fill and update your Critical Path chart.
Task Name | Expected Duration (Days) | Slack (Days) | Category | Expected (Critical) | Expected (Flexible) | Slack (Critical) | Slack (Flexible) | Events/Milestones | Status
Project Planning and Initiation
Site Analysis | 12 | 0 | Critical | 12 | 0 | 12 | 0 | Start Site Planning | In Progress
Permitting & Approvals | 20 | 5 | Flexible | 0 | 5 | 0 | 5 | Permit Issued | On Hold
Preliminary Budget | 8 | 1 | Flexible | 0 | 1 | 0 | 1 | Budget Approved | Complete
Project Design and Pre-Construction
Scope & Goal Setting | 10 | 0 | Critical | 10 | 0 | 10 | 0 | Define Project Goals | In Progress
Architectural & Engineering Plans | 30 | 5 | Flexible | 0 | 5 | 0 | 5 | Design Finalized | Not Started
Site Surveys & Soil Testing | 14 | 2 | Flexible | 0 | 2 | 0 | 2 | Survey Completed | Complete
Project Execution and Construction
Foundation & Structural Work | 25 | 0 | Critical | 25 | 0 | 25 | 0 | Pour Foundation | Not Started
Equipment & Crew Coordination | 20 | 3 | Flexible | 0 | 3 | 0 | 3 | Resources Allocated | In Progress
Inspections & Compliance Checks | 15 | 5 | Flexible | 0 | 5 | 0 | 5 | Safety Inspection Passed | Not Started
Project Completion and Closeout
Final Walkthrough & Punch List | 10 | 3 | Flexible | 0 | 3 | 0 | 3 | Final Walkthrough Completed | Not Started
Substantial Completion Certification | 7 | 0 | Critical | 7 | 0 | 7 | 0 | Certificate Issued | On Hold
Documentation & As-Built Plans | 8 | 1 | Flexible | 0 | 1 | 0 | 1 | Final Documents Approved | In Progress
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Construction Path
Construction Project Critical Path Dashboard Template
Dashboard
Enter information in the Duration, Slack, and Category fields to populate the chart. Gray cells in the table below will auto-fill and update your Critical Path chart.
Task Name | Expected Duration (Days) | Slack (Days) | Category | Expected (Critical) | Expected (Flexible) | Slack (Critical) | Slack (Flexible) | Events/Milestones | Status
Phase
Task 1 | 0 | 0 | Critical | 0 | 0 | 0 | 0 |  | In Progress
Task 2 | 0 | 0 | Flexible | 0 | 0 | 0 | 0 |  | On Hold
Task 3 | 0 | 0 | Flexible | 0 | 0 | 0 | 0 |  | Complete
Phase
Task 4 | 0 | 0 | Critical | 0 | 0 | 0 | 0 |  | In Progress
Task 5 | 0 | 0 | Flexible | 0 | 0 | 0 | 0 |  | Not Started
Task 6 | 0 | 0 | Flexible | 0 | 0 | 0 | 0 |  | Complete
Phase
Task 7 | 0 | 0 | Critical | 0 | 0 | 0 | 0 |  | Not Started
Task 8 | 0 | 0 | Flexible | 0 | 0 | 0 | 0 |  | In Progress
Task 9 | 0 | 0 | Flexible | 0 | 0 | 0 | 0 |  | Not Started
Phase
Task 10 | 0 | 0 | Flexible | 0 | 0 | 0 | 0 |  | Not Started
Task 11 | 0 | 0 | Critical | 0 | 0 | 0 | 0 |  | On Hold
Task 12 | 0 | 0 | Flexible | 0 | 0 | 0 | 0 |  | In Progress

## Key - DO NOT DELETE
Status Key - Do Not Delete
In Progress | Critical
On Hold | Flexible
Complete
Not Started

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.