## EXAMPLE Construction Risk Dash
Construction Project Risk Dashboard Template Example
Note: Enter data in the tables on the Example Notes tab (only non-shaded cells) to populate the charts on this tab.
Construction Project Name | Project Alpha
Report Date | MM/DD/YY
Project Status | On Track
Completed | 27%
Tasks | Assigned To | Priority | Risk
Regulatory Compliance | Aviv Perez, Devon Gomez |  | HIGH
Design Errors | Henry McNeal |  | HIGH
Scope Creep | Aviv Perez |  | LOW
Labor Shortages | Brian Gorman, Hazel Christensen | ★ | MEDIUM
Material Delivery | Fiorella Fitzgerald | ★ | MEDIUM
Schedule Delays | Carmen Robertson, Aviv Perez |  | HIGH
Cost Overruns | Jason Desjardins, Aviv Perez | ★ | HIGH
Equipment Downtime | Brian Gorman |  | LOW
Weather Disruptions | Carmen Robertson |  | MEDIUM
Safety Hazards | Everett Crosse, Brian Gorman | ★ | EXTREME
Stakeholder Disputes | Aviv Perez, Devon Gomez |  | MEDIUM
Launch
CLICK HERE TO CREATE IN SMARTSHEET

## EXAMPLE Notes
Task Table Example
Note: Enter data in the example tables (only non-shaded cells) to populate the charts on the Example Construction Risk tab.
Tasks | Assigned To | Start | End | Days | Status | Risk
Regulatory Compliance | Aviv Perez, Devon Gomez | 2031-09-15 | 2031-11-14 | 60 | Complete | HIGH
Design Errors | Henry McNeal | 2031-09-15 | 2031-12-14 | 90 | Complete | HIGH
Scope Creep | Aviv Perez | 2031-09-15 | 2032-03-13 | 180 | In Progress | LOW
Labor Shortages | Brian Gorman, Hazel Christensen | 2031-11-14 | 2031-12-14 | 30 | Overdue | MEDIUM
Material Delivery | Fiorella Fitzgerald | 2031-11-29 | 2031-12-14 | 15 | In Progress | MEDIUM
Schedule Delays | Carmen Robertson, Aviv Perez | 2031-12-14 | 2032-01-03 | 20 | Not Started | HIGH
Cost Overuns | Jason Desjardins, Aviv Perez | 2031-09-15 | 2032-03-13 | 180 | In Progress | HIGH
Equipment Downtime | Brian Gorman | 2031-12-19 | 2031-12-26 | 7 | Not Started | LOW
Weather Disruptions | Carmen Robertson | 2031-12-23 | 2031-12-30 | 7 | Not Started | MEDIUM
Safety Hazards | Everett Crosse, Brian Gorman | 2031-09-15 | 2032-03-13 | 180 | In Progress | EXTREME
Stakeholder Disputes | Aviv Perez, Devon Gomez | 2031-11-13 | 2031-11-28 | 15 | Complete | MEDIUM
Launch |  | 2032-03-13 | 2032-03-13 | 0
Project Risk Status
Extreme | 9.091%
High | 36.36%
Medium | 36.36%
Low | 18.18%
Budget
Planned | 80000
Actual | 50000
Pending Items
Decisions | 5
Actions | 2
Change Requests | 4

## Construction Risk Dashboard
Construction Project Risk Dashboard Template
Note: Enter data in the tables on the Dashboard Notes tab (only non-shaded cells) to populate the charts on this tab.
Construction Project Name | Name
Report Date | MM/DD/YY
Project Status
Completed | 0%
Tasks | Assigned To | Priority | Risk
|  | ★ | HIGH
|  | ★ | LOW
MEDIUM
Launch
CLICK HERE TO CREATE IN SMARTSHEET

## Dashboard Notes
Task Table Example
Note: Enter data in the tables (only non-shaded cells) to populate the charts on the Construction Risk tab.
Tasks | Assigned To | Start | End | Days | Status | Risk
Task A | Name | 2031-09-15 | 2031-11-14 | 60 | Complete | HIGH
Task B | Name |  |  | 0 | Complete | HIGH
|  |  |  | 0 | In Progress | LOW
|  |  |  | 0 | Overdue | MEDIUM
|  |  |  | 0 | In Progress | MEDIUM
|  |  |  | 0 | Not Started | HIGH
|  |  |  | 0 | In Progress | HIGH
|  |  |  | 0 | Not Started | LOW
|  |  |  | 0 | Not Started | MEDIUM
|  |  |  | 0 | In Progress | EXTREME
|  |  |  | 0 | Complete | MEDIUM
Launch |  | 2032-03-13 | 2032-03-13 | 0
Project Risk Status
Extreme | 9.091%
High | 36.36%
Medium | 36.36%
Low | 18.18%
Budget
Planned | 0
Actual | 0
Pending Items
Decisions | 0
Actions | 0
Change Requests | 0

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.