## EXAMPLE Landscape Construct
Landscaping Construction Schedule Template Example
Project Name |  | Start Date
Greenery Way |  | 2035-09-02 |  |  | <-- Enter the start date at the top of the template to populate the timeline and auto-fill the shaded start and end dates below.
[5 empty] | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7
Tasks | Status | Start | End | Days | 2035-08-27 | 2035-08-28 | 2035-08-29 | 2035-08-30 | 2035-08-31 | 2035-09-03 | 2035-09-04 | 2035-09-05 | 2035-09-06 | 2035-09-07 | 2035-09-10 | 2035-09-11 | 2035-09-12 | 2035-09-13 | 2035-09-14 | 2035-09-17 | 2035-09-18 | 2035-09-19 | 2035-09-20 | 2035-09-21 | 2035-09-24 | 2035-09-25 | 2035-09-26 | 2035-09-27 | 2035-09-28 | 2035-10-01 | 2035-10-02 | 2035-10-03 | 2035-10-04 | 2035-10-05 | 2035-10-08 | 2035-10-09 | 2035-10-10 | 2035-10-11 | 2035-10-12
Planning | Complete | 2035-09-01 | 2035-09-05 | 3 | [5 empty] | A | A | A
Site Assessment | On Hold | 2035-09-01 | 2035-09-02 | 0
Budget Estimation | In Progress | 2035-09-02 | 2035-09-02 | 0
Initial Design | Overdue | 2035-09-03 | 2035-09-03 | 1 | [5 empty] | A
Revise & Finalize Design | Needs Review | 2035-09-04 | 2035-09-04 | 1 | [6 empty] | A
Permits & Approvals | Needs Update | 2035-09-05 | 2035-09-05 | 1 | [7 empty] | A
Site Prep | In Progress | 2035-09-05 | 2035-09-15 | 8 | [7 empty] | A | A | A | A | A | A | A | A
Site Clearing | In Progress | 2035-09-05 | 2035-09-05 | 1 | [7 empty] | A
Excavation | Complete | 2035-09-05 | 2035-09-05 | 1 | [7 empty] | A
Soil Prep | Canceled | 2035-09-08 | 2035-09-12 | 3 | [10 empty] | A | A | A
Grading | Complete | 2035-09-11 | 2035-09-15 | 4 | [11 empty] | A | A | A | A
Hardscaping | In Progress | 2035-09-15 | 2035-09-16 | 0
Foundation | In Progress | 2035-09-15 | 2035-09-16 | 0
Retaining Walls | In Progress | 2035-09-17 | 2035-09-17 | 1 | [15 empty] | A
Patios | In Progress | 2035-09-18 | 2035-09-19 | 2 | [16 empty] | A | A
Pathways | In Progress | 2035-09-19 | 2035-09-20 | 2 | [17 empty] | A | A
Outdoor Structures | In Progress | 2035-09-15 | 2035-09-17 | 1 | [15 empty] | A
Drainage | In Progress | 2035-09-17 | 2035-09-18 | 2 | [15 empty] | A | A
Irrigation System | In Progress | 2035-09-18 | 2035-09-19 | 2 | [16 empty] | A | A
Softscaping | Not Started | 2035-09-24 | 2035-09-25 | 2 | [20 empty] | A | A
Tress & Shrubs | Not Started | 2035-09-24 | 2035-09-25 | 2 | [20 empty] | A | A
Flower Beds & Ground Cover | Not Started | 2035-09-25 | 2035-09-26 | 2 | [21 empty] | A | A
Seeding & Sodding | Not Started | 2035-09-25 | 2035-09-29 | 4 | [21 empty] | A | A | A | A
Mulching | Not Started | 2035-09-30 | 2035-10-03 | 3 | [25 empty] | A | A | A
Lighting & Electrical | Complete | 2035-09-25 | 2035-09-29 | 4 | [21 empty] | A | A | A | A
Wiring & Setup | Complete | 2035-09-25 | 2035-09-29 | 4 | [21 empty] | A | A | A | A
Installation | Complete | 2035-09-25 | 2035-09-29 | 4 | [21 empty] | A | A | A | A
Water Features | On Hold | 2035-10-03 | 2035-10-07 | 3 | [27 empty] | A | A | A
Pond & Fountain Installation | On Hold | 2035-10-03 | 2035-10-07 | 3 | [27 empty] | A | A | A
Water Pump & Filtration System | On Hold | 2035-10-03 | 2035-10-07 | 3 | [27 empty] | A | A | A
Stones & Foliage | On Hold | 2035-10-07 | 2035-10-08 | 1 | [30 empty] | A
Final Touches | Overdue | 2025-10-10 | 2025-10-14 | 3
Lawn Care | In Progress | 2035-10-01 | 2035-10-02 | 2 | [25 empty] | A | A
Stone & Gravel | In Progress | 2035-10-02 | 2035-10-06 | 4 | [26 empty] | A | A | A | A
Clean-Up | Complete | 2025-10-10 | 2025-10-14 | 3
CLICK HERE TO CREATE IN SMARTSHEET

## Landscape Construct Schedule
Landscaping Construction Schedule Template
Project Name |  | Start Date
|  | 2035-09-02 |  |  | <-- Enter the start date at the top of the template to populate the timeline and auto-fill the shaded start and end dates below.
[5 empty] | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk 4 |  |  |  |  | Wk 5 |  |  |  |  | Wk 6 |  |  |  |  | Wk 7
Tasks | Status | Start | End | Days | 2035-08-27 | 2035-08-28 | 2035-08-29 | 2035-08-30 | 2035-08-31 | 2035-09-03 | 2035-09-04 | 2035-09-05 | 2035-09-06 | 2035-09-07 | 2035-09-10 | 2035-09-11 | 2035-09-12 | 2035-09-13 | 2035-09-14 | 2035-09-17 | 2035-09-18 | 2035-09-19 | 2035-09-20 | 2035-09-21 | 2035-09-24 | 2035-09-25 | 2035-09-26 | 2035-09-27 | 2035-09-28 | 2035-10-01 | 2035-10-02 | 2035-10-03 | 2035-10-04 | 2035-10-05 | 2035-10-08 | 2035-10-09 | 2035-10-10 | 2035-10-11 | 2035-10-12
Category | Complete | 0 | 0 | 0
Task | On Hold |  |  | 0
Task | In Progress |  |  | 0
| Overdue |  |  | 0
| Needs Review |  |  | 0
| Needs Update |  |  | 0
Category | In Progress | 0 | 0 | 0
Task | In Progress |  |  | 0
| Complete |  |  | 0
| Canceled |  |  | 0
| Complete |  |  | 0
Category | In Progress | 0 | 0 | 0
Task | In Progress |  |  | 0
| In Progress |  |  | 0
| In Progress |  |  | 0
| In Progress |  |  | 0
| In Progress |  |  | 0
| In Progress |  |  | 0
| In Progress |  |  | 0
Category | Not Started | 0 | 0 | 0
Task | Not Started |  |  | 0
| Not Started |  |  | 0
| Not Started |  |  | 0
| Not Started |  |  | 0
Category | Complete | 0 | 0 | 0
Task | Complete |  |  | 0
| Complete |  |  | 0
Category | On Hold | 0 | 0 | 0
Task | On Hold |  |  | 0
| On Hold |  |  | 0
| On Hold |  |  | 0
Category | Overdue | 0 | 0 | 0
Task | In Progress |  |  | 0
| In Progress |  |  | 0
| Complete |  |  | 0

## Status Keys - DO NOT DELETE
Drop-Down Key - DO NOT DELETE
STATUS
Not Started
In Progress
Complete
On Hold
Overdue
Needs Review
Needs Update
Canceled

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.