## EXAMPLE Construction RFP
Simple Construction RFP Template Example
Wilson and King Construction, LLC
Project Name | Project Location | Solicitation Date | Solicitation Number
Northridge Community Center | 1245 Elm Street | MM/DD/YY | 12345-ABCD
Company Name | Wilson and King Construction, LLC
Contracting Point of Contact | Jamal King, Project Manager
Address | 456 Main Street, Metro NJ
Phone | 503-555-1234
Email | jamal.king@wkconstruction.com
1. Project Overview
Summary
Wilson & King Construction, LLC is currently accepting proposals for your services on the Northridge Community Center Renovation Project, located at 1245 Elm Street. This project involves the renovation and modernization of a 15,000 sq. ft. community center to enhance energy efficiency, accessibility, and functionality. Our objective is to partner with a qualified contractor to deliver high-quality results while adhering to the outlined timeline, budget, and specifications.
Description
Provide an overview of the project’s purpose, size, and scope, including key goals such as sustainability or safety improvements.
The project entails structural upgrades, HVAC system replacement, ADA-compliant restroom renovations, and installation of energy-efficient lighting throughout the facility.
Objectives and Goals
Highlight some specific outcomes that the project aims to achieve.
The renovation aims to achieve compliance with LEED Silver certification standards, improve accessibility, and create a welcoming environment for community activities.
Scope of Work Summary
Provide a high-level overview of key deliverables to set clear expectations for contractors.
This project includes site preparation, demolition of outdated structures, installation of new systems and materials, and final inspections to ensure code compliance.
2. Background Information
Issuing Organization Details
Include the name, contact information, and role of the organization overseeing the project (developer, owner, etc.).
The project is being led by Wilson and King Construction, LLC, a Portland-based developer specializing in public infrastructure projects. For questions or clarifications, contact Jamal King at jamal.king@wkconstruction.com or call 503-555-1234.
Project Context
Detail relevant site or project conditions.
The community center was built in 1972 and requires significant updates to meet current energy and accessibility standards. The surrounding area has existing utilities and sufficient space for contractor staging.
Relevant Documentation
List any supplemental materials provided with the RFP to give bidders a better understanding of the project’s framework.
1. Geotechnical survey of the site (included as Appendix A) 2. Preliminary design plans and zoning reports (included as Appendix B)
3. Scope of Work
Detailed Tasks
Provide a comprehensive breakdown of construction tasks.
Demolition: Removal of outdated HVAC equipment, fixtures, and flooring Structural Upgrades: Reinforcement of load-bearing walls and roof Systems Installation: Replacement of HVAC systems, plumbing, and electrical wiring Finishing Work: Installation of ADA-compliant fixtures, new flooring, and energy-efficient lighting
Material Specifications
Define materials to be used, ensuring compliance with quality standards.
The project will use sustainable materials, including recycled steel and low-VOC paint, and ENERGY STAR-certified HVAC systems.
Standards and Guidelines
List applicable standards.
1. OSHA compliance for all on-site work 2. LEED Silver certification requirements
Design Requirements
Include any specific design elements that must be integrated.
All renovations must align with the architectural plans provided in Appendix B.
4. Project Requirements
Deliverables
Outline key deliverables for each project phase.
Phase 1 | Completion of structural upgrades by April 15, 20XX
Phase 2 | Final walkthrough and inspection by June 1, 20XX
Phase 3 | N/A
Milestones
Provide a timeline of critical project milestones, such as major construction phases or inspection deadlines.
Milestones | Date | Description
Site Preparation | MM/DD/YY
HVAC Installation | MM/DD/YY
Final Inspections | MM/DD/YY
MM/DD/YY
MM/DD/YY
Compliance and Approvals
Specify necessary permits, safety protocols, and compliance requirements.
All necessary permits must be obtained prior to the start of construction.
Insurance, Bonding, and Licensing
Explain the required proof of appropriate coverage and contractor licensing.
Contractors must provide proof of liability insurance and state licensing.
5. Proposal Requirements
Submission Format
Detail how the proposal should be structured.
Proposals must include an executive summary, technical details, and a cost breakdown.
Required Documentation
1. Cover letter summarizing the contractor’s experience and qualifications 2. References and examples of similar completed projects 3. Detailed work plan, safety protocols, and proposed timeline
Key Questions to Address
Include specific questions, such as how contractors will handle material sourcing, manage subcontractors, or address site-specific challenges.
1. How will you source materials for the project? 2. What steps will you take to ensure adherence to OSHA and LEED guidelines?
6. Selection Criteria
Evaluation Factors
Clearly define the factors that will influence the decision.
1. Experience with similar projects 2. Proposed timeline and ability to meet deadlines 3. Pricing and cost transparency
Weighting
Optionally, provide a percentage-based weighting for each criterion.
Evaluation criteria will be weighted as follows: 30% cost; 40% experience and qualifications; and 30% timeline adherence.
Additional Considerations
Emphasize innovation, value engineering, or other advantageous differentiators.
Innovative approaches or value engineering suggestions are encouraged.
7. Budget and Pricing
Cost Breakdown
Require detailed pricing for labor, materials, equipment, and subcontractors.
Detailed cost breakdown should include labor, materials, equipment, and contingency costs.
Contingency Planning
Request contingency costs for unforeseen circumstances.
Not applicable
Unit Pricing
Specify pricing on a per-unit basis for materials or labor, where applicable.
Per-unit pricing is used for applicable materials and labor to simplify adjustments.
8. Schedule and Timeline
Key Dates
Include deadlines for RFP submission, review periods, and award announcements.
RFP submission deadline: February 10, 20XX. Review period: February 11–17, 20XX. Contractor selection: February 20, 20XX.
Phased Timeline
Break down project phases with expected start and completion dates for each.
Phase 1 | Site preparation: March 20XX
Phase 2 | HVAC installation: April 20XX
Phase 3 | Final inspections: June 20XX
9. Contract Terms and Conditions
Contract Type
Indicate the preferred contract type.
Preferred contract type is fixed-price.
Payment Schedule
Provide details for milestone-based payments.
Milestone-based payments as follows: 20% at project start; 50% upon completion of HVAC installation; and remaining balance upon final walkthrough.
Warranties
Specify minimum warranty requirements for materials and workmanship.
Provide a minimum one-year warranty on materials and workmanship.
Termination Clauses
Outline conditions for early termination of the contract.
Grounds for termination include failure to meet milestones or safety violations.
10. Submission Instructions
Deadline | Contact Details |  | Submission Method
2/10/20XX 5:00 PM | Submit to Jamal King at jamal.king@wkconstruction.com |  | Proposals can be submitted via email.
11. Appendices
Supporting Documents
Attach any necessary documentation, such as site plans, CAD drawings, or zoning reports.
1. Site plans and CAD drawings (Appendix A) 2. Zoning and environmental reports (Appendix B)
Forms
Include pre-filled templates for bid submissions, subcontractor details, and material specifications.
1. Bid submission template 2. Subcontractor details form
Sample Contract
Provide a draft agreement for contractors to review.
A draft contract is included for your review (Appendix C).
CLICK HERE TO CREATE IN SMARTSHEET

## Construction RFP
Simple Construction RFP Template
Your Logo Here
Project Name | Project Location | Solicitation Date | Solicitation Number
MM/DD/YY
Company Name
Contracting Point of Contact
Address
Phone
Email
1. Project Overview
Summary
[Company Name] is currently accepting proposals for your services on [Project Name], located at [Project Location]. This project involves [brief project type or description, e.g., the construction of a commercial building, residential complex, or infrastructure upgrade]. Our objective is to partner with a qualified contractor to deliver high-quality results while adhering to the outlined timeline, budget, and specifications.
Description
Provide an overview of the project’s purpose, size, and scope, including key goals such as sustainability or safety improvements.
For example: "This project involves the construction of a 10,000 sq. ft. energy-efficient office building in downtown Portland, OR."
Objectives and Goals
Highlight specific outcomes the project aims to achieve.
For example: Compliance with LEED certification, enhanced accessibility, meeting specific safety standards, etc.
Scope of Work Summary
Provide a high-level overview of key deliverables to set clear expectations for contractors.
For example: Site preparation, construction phases, final inspections, etc.
2. Background Information
Issuing Organization Details
Include the name, contact information, and role of the organization overseeing the project (developer, owner, etc.).
Description
Project Context
Detail relevant site or project conditions.
For example: Existing infrastructure, zoning considerations, unique challenges, etc.
Relevant Documentation
List any supplemental materials provided with the RFP to give bidders a better understanding of the project's framework.
For example: Surveys, zoning reports, existing design plans, etc.
3. Scope of Work
Detailed Tasks
Provide a comprehensive breakdown of construction tasks.
For example: Excavation, framing, plumbing, electrical work, finishes, etc.
Material Specifications
Define materials to be used, ensuring compliance with quality standards.
For example: Sustainable wood, reinforced concrete, etc.
Standards and Guidelines
List applicable standards.
For example: OSHA compliance, local building codes, LEED certification requirements or sustainability requirements, etc.
Design Requirements
Include any specific design elements that must be integrated
For example: Architectural, structural, or mechanical details
4. Project Requirements
Deliverables
Outline key deliverables for each project phase.
Phase 1 | For example: Surveys, zoning reports, existing design plans, etc.
Phase 2 | For example: Surveys, zoning reports, existing design plans, etc.
Phase 3 | For example: Surveys, zoning reports, existing design plans, etc.
Milestones
Provide a timeline of critical project milestones, such as major construction phases or inspection deadlines.
Milestones | Date | Description
MM/DD/YY
MM/DD/YY
MM/DD/YY
MM/DD/YY
MM/DD/YY
Compliance and Approvals
Specify necessary permits, safety protocols, and compliance requirements.
Description
Insurance, Bonding, and Licensing
Require proof of appropriate coverage and contractor licensing.
Description
5. Proposal Requirements
Submission Format
Detail how the proposal should be structured.
For example, include an executive summary, technical details, and budget.
Required Documentation
1. Cover letter outlining the contractor's suitability for the project 2. Contractor qualifications, including licensing and certifications 3. References or examples of similar completed projects 4. Detailed work plan, safety protocols, and approach to meeting project goals
Key Questions to Address
Include specific questions, such as how contractors will handle material sourcing, manage subcontractors, or address site-specific challenges.
1. How will you source materials for the project? 2. What steps will you take to ensure adherence to OSHA and LEED guidelines?
6. Selection Criteria
Evaluation Factors
Clearly define the factors that will influence the decision.
1. Experience with similar projects 2. Proposed timeline and ability to meet deadlines 3. Pricing and cost transparency
Weighting
Optionally, provide a percentage-based weighting for each criterion.
30% cost, 40% experience, 30% timeline
Additional Considerations
Emphasize innovation, value engineering, or other advantageous differentiators.
Description
7. Budget and Pricing
Cost Breakdown
Require detailed pricing for labor, materials, equipment, and subcontractors.
Description
Contingency Planning
Request contingency costs for unforeseen circumstances.
Description
Unit Pricing
Specify pricing on a per-unit basis for materials or labor, where applicable.
Description
8. Schedule and Timeline
Key Dates
Include deadlines for RFP submission, review periods, and award announcements.
Description
Phased Timeline
Break down project phases with expected start and completion dates for each.
Phase 1 | Start Dates / Completion Dates
Phase 2 | Start Dates / Completion Dates
Phase 3 | Start Dates / Completion Dates
9. Contract Terms and Conditions
Contract Type
Indicate the preferred contract type.
For example, fixed-price, cost-plus
Payment Schedule
Provide details for milestone-based payments
For example: 20% upfront, 50% at framing completion
Warranties
Specify minimum warranty requirements for materials and workmanship.
Description
Termination Clauses
Outline conditions for early termination of the contract.
Description
10. Submission Instructions
Deadline | Contact Details |  | Submission Method
MM/DD/YY 0:00 PM | Name, title, email, phone |  | Electronic, hard copy
11. Appendices
Supporting Documents
Attach any necessary documentation, such as site plans, CAD drawings, or zoning reports.
Description
Forms
Include pre-filled templates for bid submissions, subcontractor details, and material specifications.
Description
Sample Contract
Provide a draft agreement for contractors to review.
Description

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.