## EXAMPLE - Agile Product Sprint
AGILE PRODUCT SPRINT ROADMAP TEMPLATE – EXAMPLE
SPRINT 0 | SPRINT 1 | SPRINT 2 | SPRINT 3 | SPRINT 4 | SPRINT 5 | SPRINT 6 | SPRINT 7
2031-01-01 | 2031-01-15 | 2031-02-01 | 2031-02-15 | 2031-03-01 | 2031-03-15 | 2031-04-01 | 2031-04-15
1. Project Setup
2. Requirements Gathering
3. Design and Prototyping
4. Software Development - Phase 1
5. Testing and Quality Assurance
6. Software Development - Phase 2
7. Deployment and Delivery
8. Post-Launch Support and Maintenance
CLICK HERE TO CREATE IN SMARTSHEET
MILESTONE
00/00
Define project scope and objectives.
Set up development and collaboration tools.
Establish Agile teams and roles.
Conduct stakeholder interviews.
Prioritize and categorize user stories.
Create initial design mockups.
Conduct user testing and gather feedback.
Develop interactive prototypes.
Develop core functionalities.
Implement user interface components.
Integrate back-end and front-end systems.
Perform unit testing.
Conduct integration testing.
Execute system and acceptance testing.
Prepare deployment environment.
Deploy beta version for real-world testing.
Finalize and release product.
Compile user stories and requirements.
Develop advanced features.
Optimize performance and scalability.
Enhance user experience based on feedback.
Monitor and address immediate post-launch issues.
Plan and prioritize ongoing maintenance tasks.
Gather user feedback for future updates.
TEAM KEY
TEAM 1
TEAM 4
TEAM 2
TEAM 3
TEAM 5

## BLANK - Agile Product Sprint
AGILE PRODUCT SPRINT ROADMAP TEMPLATE
SPRINT 0 | SPRINT 1 | SPRINT 2 | SPRINT 3 | SPRINT 4 | SPRINT 5 | SPRINT 6 | SPRINT 7
00/00 | 00/00 | 00/00 | 00/00 | 00/00 | 00/00 | 00/00 | 00/00
Category 1
Category 2
Category 3
Category 4
Category 5
Category 6
Category 7
Category 8
MILESTONE
00/00
Sprint Task
Sprint Task
Sprint Task
Sprint Task
Sprint Task
Sprint Task
Sprint Task
Sprint Task
Sprint Task
Sprint Task
Sprint Task
Sprint Task
Sprint Task
Sprint Task
Sprint Task
Sprint Task
Sprint Task
Sprint Task
Sprint Task
Sprint Task
Sprint Task
Sprint Task
Sprint Task
Sprint Task
Sprint Task
Sprint Task
Sprint Task
Sprint Task
Sprint Task
Sprint Task
Sprint Task
Sprint Task
TEAM KEY
TEAM 1
TEAM 4
TEAM 2
TEAM 3
TEAM 5

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.