## EXAMPLE - Agile Release Plan
Agile Release Plan Template Example
Project Name |  | Product Release |  |  |  | Start Date | End Date | Overall Progress
Project Manager |  | Alex B. |  |  |  | 2025-09-02 | 2025-10-10 | 35%
Project Deliverable |  | Description
Scope Statement |  | Description
At Risk | Task Name | Feature Type | Responsible | Story Points | Start | Finish | Duration in Days | Status | Comments
No | SPRINT 1 |  | Alex B. |  | 2035-09-03 | 2035-09-13 | 11
Yes | Feature 1 |  | Frank C. |  | 2035-09-03 | 2035-09-07 | 5 | Complete
No | Feature 2 |  | Jacob S. |  | 2035-09-07 | 2035-09-12 | 6 | In Progress
No | Feature 3 |  | Jacob S. |  | 2035-09-09 | 2035-09-13 | 5 | Overdue
No | SPRINT 2 |  | Jacob S. |  | 2035-09-16 | 2035-09-24 | 9
No | Feature 4 |  | Alex B. |  | 2035-09-16 | 2035-09-17 | 2 | Approved
Yes | Feature 5 |  | Frank C. |  | 2035-09-17 | 2035-09-21 | 5 | Needs Review
No | Feature 6 |  | Shari W. |  | 2035-09-22 | 2035-09-24 | 3 | On Hold
No | SPRINT 3 |  | Shari W. |  | 2035-09-24 | 2035-10-05 | 12
No | Feature 7 |  | Alex B. |  | 2035-09-25 | 2035-09-29 | 5 | Not Started
No | Feature 8 |  | Kennedy K. |  | 2035-09-24 | 2035-10-02 | 9 | Not Started
No | Feature 9 |  | Jacob S. |  | 2035-10-02 | 2035-10-05 | 4 | Not Started
CLICK HERE TO CREATE IN SMARTSHEET
Formulas:
Start = MIN([Start, row below]:G13)
Start Date = MAX([Start Date, row below]:H13)

## BLANK - Agile Release Plan
Agile Release Plan Template
Project Name |  | Name |  |  |  | Start Date | End Date | Overall Progress
Project Manager |  | Name | [5 empty] | 0%
Project Deliverable |  | Description
Scope Statement |  | Description
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION in days | STATUS | COMMENTS
| SPRINT 1 |  |  |  | 0 | 0
Feature 1
Feature 2
Feature 3
| SPRINT 2 |  |  |  | 0 | 0
Feature 4
Feature 5
Feature 6
| SPRINT 3 |  |  |  | 0 | 0
Feature 7
Feature 8
Feature 9
Formulas:
START = MIN([START, row below]:G12)
Start Date = MAX([Start Date, row below]:H12)
Double click Horizontal (Value) Axis to format Bound Minimum and Maximum settings under Axis Options.

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | STATUS
Yes | Not Started
No | In Progress
Complete
Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.