## EXAMPLE - IT Project Management
IT Project Management Template Example
Project Name | Product Release
Project Manager | Alex B.
Project Phase | Initiation, Planning, Development, Testing, Deployment
Start Date | 2025-09-02
End Date | 2025-10-09
Overall Progress | 20%
Phase | Task Name | Assigned To | Start Date | End Date | Duration (Days) | Status | 2015-09-02 | 2015-09-03 | 2015-09-04 | 2015-09-05 | 2015-09-06 | 2015-09-07 | 2015-09-08 | 2015-09-09 | 2015-09-10 | 2015-09-11 | 2015-09-12 | 2015-09-13 | 2015-09-14 | 2015-09-15 | 2015-09-16 | 2015-09-17 | 2015-09-18 | 2015-09-19 | 2015-09-20 | 2015-09-21 | 2015-09-22 | 2015-09-23 | 2015-09-24 | 2015-09-25 | 2015-09-26 | 2015-09-27 | 2015-09-28 | 2015-09-29 | 2015-09-30 | 2015-10-01 | 2015-10-02 | 2015-10-03 | 2015-10-04 | 2015-10-05 | 2015-10-06 | 2015-10-07 | 2015-10-08 | 2015-10-09 | Status Key
Initiation | [44 empty] | Completed
| Project Kickoff Meeting | Alex B. | 2015-09-02 | 2015-09-02 | 0 | In Progress | [38 empty] | In Progress
| Define Project Objectives | Frank C. | 2015-09-03 | 2015-09-07 | 4 | Completed | [38 empty] | Not Started
Planning
| Gather Detailed Requirements | Jacob S. | 2015-09-07 | 2015-09-09 | 2 | Not Started
| Define Hardware Requirements | Jacob S. | 2015-09-09 | 2015-09-11 | 2
| Finalize Resource Plan | Jacob S. | 2015-09-11 | 2015-09-15 | 4
| Staffing & Assignments | Alex B. | 2015-09-15 | 2015-09-17 | 2
Development
| Define Technical Requirements | Frank C. | 2015-09-17 | 2015-09-21 | 4
| Backend Database Development | Shari W. | 2015-09-21 | 2015-09-23 | 2
| API Development | Shari W. | 2015-09-23 | 2015-09-25 | 2
| Frontend UI Development | Alex B. | 2015-09-25 | 2015-09-29 | 4
| Development Complete | Jacob S. | 2015-09-29 | 2015-10-02 | 3
Testing
| QA/Test Plan Execution | Kennedy K.
| System Integration Testing | Kennedy K.
Deployment
| Hardware Configuration | Alex B. | 2015-10-05 | 2015-10-07 | 2
| Go-Live / Production Launch |  | 2015-10-07 | 2015-10-09 | 2
CLICK HERE TO CREATE IN SMARTSHEET

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.