## Slide 1
One-Page Project Schedule Template Example
PROJECT SCHEDULE
Project Name
YOUR
LOGO

## Slide 2
PROJECT SCHEDULE
Project Manager |  | Start Date | 09/02/20XX
Project Deliverable |  | End Date | 10/09/20XX
Scope Statement |  | Overall Progress | 0%
Task Name | Assigned To | Start Date | End Date | Duration in Days | Status | Comments
Set Kickoff Meeting | Sasha Petrov | 09/02 | 09/03 | 2 | Complete | 
Agree on Objectives | Romy Bailey | 09/03 | 09/07 | 5 | Complete | 
Detailed Requirements | Petrus Nishimura | 09/07 | 09/12 | 6 | Complete | 
Hardware Requirements | Petrus Nishimura | 09/09 | 09/11 | 3 | Overdue | 
Final Resource Plan | Petrus Nishimura | 09/11 | 09/15 | 5 | In Progress | 
Staffing | Sasha Petrov | 09/16 | 09/17 | 2 | In Progress | 
Technical Requirements | Romy Bailey | 09/17 | 09/21 | 5 | Not Started | 
DB Development | Olivia Carter | 09/22 | 09/24 | 3 | Not Started | 
API Development | Olivia Carter | 09/23 | 09/27 | 5 | Not Started | 
UI Client | Sasha Petrov | 09/25 | 09/29 | 5 | Not Started | 
Testing | Mateus Tobin | 09/24 | 10/02 | 9 | Not Started | 
Development Complete | Petrus Nishimura | 10/02 | 10/05 | 4 | Not Started | 

## Slide 3
One-Page Project Schedule Template
PROJECT SCHEDULE
Project Name
YOUR
LOGO

## Slide 4
PROJECT SCHEDULE
Project Manager |  | Start Date | 
Project Deliverable |  | End Date | 
Scope Statement |  | Overall Progress | 
Task Name | Assigned To | Start Date | End Date | Duration in Days | Status | Comments
 |  |  |  |  | Complete | 
 |  |  |  |  | Not Started | 
 |  |  |  |  | Overdue | 
 |  |  |  |  | In Progress | 
Provided by Smartsheet, Inc.

## Slide 5
DISCLAIMER Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.