## EXAMPLE - Project Charter
Project Charter Template With Example Data
GENERAL PROJECT INFORMATION
PROJECT NAME |  |  | PROJECT MANAGER |  | PROJECT SPONSOR
Positive Charge EMV Station Installations |  |  | Jane Matthews |  | Jill DeGrassio
EMAIL |  | PHONE | ORGANIZATIONAL UNIT(S)
jane.matthews@positivecharge.com |  | 000-000-0000 | Field Engineering, Operations, and Project Management
GREEN BELTS ASSIGNED |  |  | EXPECTED START DATE |  | EXPECTED COMPLETION DATE
Wendy Williams (Project Management) |  |  | 2/19/20XX |  | 11/30/20XX
BLACK BELTS ASSIGNED |  |  | EXPECTED SAVINGS |  | ESTIMATED COSTS
Rakesh Agarwal (Director of Operations) |  |  | 237750 |  | 441855
PROJECT OVERVIEW
PROBLEM OR ISSUE | Our goal for this project is to install 1,125 EV charging stations at 116 locations across the US, Mexico and Canada to accommodate malls' and service stations' EV-charging needs.
PURPOSE OF PROJECT | The implementation of the 1,125 EV charging stations will reduce fossil-fuel emissions, and have a positive impact on the environment. This will help fulfill Positive Charge's mission of being the world's largest EV-charging provider and reduce the environmental impact of fossil-fuel cars through our services.
BUSINESS CASE | As EVs become more prevalent, more EV-charging stations are needed to accommodate EV drivers' charging needs. The implementation of the 1,125 EV charging stations at 116 locations across the US, Mexico, and Canada to accommodate malls' and service stations' EV-charging "traffic" will reduce the lengths to which EV drivers would have to travel for their next charge. The implementation of the EV-charging stations will also result in a 24% profit for Positive Charge.
GOALS / METRICS | The project goal is to install 1,125 EV charging stations at 116 locations across the US, Mexico and Canada. The metrics used to measure success will primarily be the following key performance indicators (KPIs): Revenue Growth, Client Retention Rate, and Customer Satisfaction.
EXPECTED DELIVERABLES | Install 1,125 EV charging stations at 116 locations across the US, Mexico and Canada to accommodate malls' and service stations' EV-charging needs.
PROJECT SCOPE
WITHIN SCOPE | Operations engineers, project managers and field implementation engineers will work with third-party client site personnel to install 1,125 EV charging stations at 116 locations across the US, Mexico and Canada.
OUTSIDE OF SCOPE | Positive Charge is not responsible for third-party / clients locations preparatory work (e.g., permits for digging, city region electricity-availability logistics, etc.). However, Positive Charge project managers can provide clients with a checklist to ensure their locations are adequately prepared for the installation of our EV charging stations.
TENTATIVE SCHEDULE
KEY MILESTONE |  |  | START |  | FINISH
Form Project Team / Preliminary Review / Scope |  |  | 12/05/20XX |  | 01/11/20XX
Finalize Project Plan / Charter / Kick Off |  |  | 12/06/20XX |  | 02/01/20XX
Define Phase |  |  | 12/07/20XX |  | 02/02/20XX
Measurement Phase |  |  | 12/08/20XX |  | 02/10/20XX
Analysis Phase |  |  | 12/09/20XX |  | 02/26/20XX
Improvement Phase |  |  | 01/10/20XX |  | 03/10/20XX
Control Phase |  |  | 02/08/20XX |  | 03/08/20XX
Project Summary Report and Close Out |  |  | 04/23/20XX |  | 06/23/20XX
RESOURCES
PROJECT TEAM | Janine Remagio - Project Manager David Coen - Chief Engineer Rita Preze - CFO |  | Lisa Jones - QA Director Donald Smythe - Field Engineer
SUPPORT RESOURCES | Operations, Sales, Project Management, Engineering
SPECIAL NEEDS | TBD
COSTS
COST TYPE | VENDOR / LABOR NAMES |  | RATE | QTY | AMOUNT
Labor | Electro Charge Logistics, Inc. |  | 78 | 200 | 15600
Labor | Level 1 EVS |  | 46 | 100 | 4600
Labor | Level 2 EVS |  | 58 | 50 | 2900
Labor | EVC Fast Chargers |  | 85000 | 1 | 85000
Labor | Battery Vendor |  | 79879 | 3 | 239637
Supplies | Power Conversion System Vendor |  | 68686 | 1 | 68686
Miscellaneous | Third-Party Software |  | 25432 | 1 | 25432
|  |  | TOTAL COSTS |  | 441855
BENEFITS AND CUSTOMERS
PROCESS OWNER | Jane Matthews - Project Manager
KEY STAKEHOLDERS | Jill DeGrassio
FINAL CUSTOMER | 116 clients across the US, Mexico and Canada (see attached client list).
EXPECTED BENEFITS | The implementation of the 1,125 EV charging stations at 116 locations across the US, Mexico and Canada to accommodate malls' and service stations' EV-charging "traffic" will reduce the lengths to which EV drivers would have to trave for their next charge. The implementation of the EV-charging stations will also result in a 24% profit for Positive Charge.
TYPE OF BENEFIT | BASIS OF ESTIMATE |  |  |  | ESTIMATED BENEFIT AMOUNT
Specific Cost Savings | Estimator's projections |  |  |  | 25000
Enhanced Revenues | Finance's projections |  |  |  | 92500
Higher Productivity (Soft) | Project management's estimations |  |  |  | 17500
Improved Compliance | Operations' estimations |  |  |  | 12000
Better Decision Making | Project management's estimations |  |  |  | 18500
Less Maintenance | Project management's estimations |  |  |  | 26000
Other Costs Avoided | Finance's projections |  |  |  | 46250
|  |  | TOTAL BENEFIT |  | 237750
RISKS, CONSTRAINTS, AND ASSUMPTIONS
RISKS | Though contract is signed, Operations still does not have approval for installation from cities of Denver and Yuma. Project management to work with both cities to ensure proper permitting, etc. in time for scheduled installations.
CONSTRAINTS | We have to "backfill" some key project management and field engineer positions to ensure we have people "on the ground" to manage EV stations' implementation.
ASSUMPTIONS | We assume that all permits for installation of EV-charging stations will be provided by clients by time of implementation.
PREPARED BY | TITLE |  |  |  | DATE
Jane Matthews | Senior Project Manager |  |  |  | 04/22/20XX
CLICK HERE TO CREATE IN SMARTSHEET
IMPORTANT REMINDER
A narrative written charter must be circulated and signed by the project sponsors. You can attach a completed version of this template to your narrative written charter in an effort to keep it short and concise.
Please make sure you meet with the project team and sponsors before completing this template. Much of the information required will need to come from a discussion with team members and sponsors.

## BLANK - Project Charter
Project Charter
GENERAL PROJECT INFORMATION
PROJECT NAME |  |  | PROJECT MANAGER |  | PROJECT SPONSOR
EMAIL |  | PHONE | ORGANIZATIONAL UNIT(S)
GREEN BELTS ASSIGNED |  |  | EXPECTED START DATE |  | EXPECTED COMPLETION DATE
BLACK BELTS ASSIGNED |  |  | EXPECTED SAVINGS |  | ESTIMATED COSTS
|  |  | 0 |  | 0
PROJECT OVERVIEW
PROBLEM OR ISSUE
PURPOSE OF PROJECT
BUSINESS CASE
GOALS / METRICS
EXPECTED DELIVERABLES
PROJECT SCOPE
WITHIN SCOPE
OUTSIDE OF SCOPE
TENTATIVE SCHEDULE
KEY MILESTONE |  |  | START |  | FINISH
RESOURCES
PROJECT TEAM
SUPPORT RESOURCES
SPECIAL NEEDS
COSTS
COST TYPE | VENDOR / LABOR NAMES |  | RATE | QTY | AMOUNT
Labor |  |  |  | 0 | 0
Labor |  |  |  | 0 | 0
Labor |  |  |  | 0 | 0
Labor |  |  |  | 0 | 0
Labor |  |  |  | 0 | 0
Supplies |  |  |  | 0 | 0
Miscellaneous |  |  |  | 0 | 0
|  |  | TOTAL COSTS |  | 0
BENEFITS AND CUSTOMERS
PROCESS OWNER
KEY STAKEHOLDERS
FINAL CUSTOMER
EXPECTED BENEFITS
TYPE OF BENEFIT | BASIS OF ESTIMATE |  |  |  | ESTIMATED BENEFIT AMOUNT
Specific Cost Savings |  |  |  |  | 0
Enhanced Revenues |  |  |  |  | 0
Higher Productivity (Soft) |  |  |  |  | 0
Improved Compliance |  |  |  |  | 0
Better Decision Making |  |  |  |  | 0
Less Maintenance |  |  |  |  | 0
Other Costs Avoided |  |  |  |  | 0
|  |  | TOTAL BENEFIT |  | 0
RISKS, CONSTRAINTS, AND ASSUMPTIONS
RISKS
CONSTRAINTS
ASSUMPTIONS
PREPARED BY | TITLE |  |  |  | DATE
IMPORTANT REMINDER
A narrative written charter must be circulated and signed by the project sponsors. You can attach a completed version of this template to your narrative written charter in an effort to keep it short and concise.
Please make sure you meet with the project team and sponsors before completing this template. Much of the information required will need to come from a discussion with team members and sponsors.

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.