## Slide 1
Project Schedule Template Example
PROJECT SCHEDULE
Internal Platform Revamp
YOUR
LOGO
Project Manager | Start Date | End Date
Sarah Goodwin | 01/08/20xx | 10/20/20xx

## Slide 2
PROJECT SCHEDULE
Phase Title | Start Date | End Date | Duration in days | Schedule | Budget | Resources | Risks | Issues | Comments
Project Planning | 5/5 | 7/1 | 58 | On Track | $ 4,500.00 | PM, BA | Misalignment with exec priorities | None | Stakeholder kickoff completed
Design Phase | 5/10 | 8/10 | 93 | Slightly Behind | $ 12,000.00 | UX, UI Designer, Product Owner | Approval delays on mockups | Pending feedback from the marketing team | Final prototype review scheduled 2/21
Sprint 1 Development | 6/10 | 3/1 | 265 | On Track | $ 22,000.00 | Backend Dev, API Lead | Integration delays with legacy systems | LDAP connector not syncing in dev | Dependencies mapped, daily standups started
Sprint 2 Development | 6/22 | 8/4 | 44 | On Track | $ 25,000.00 | Frontend Dev, QA | Resource availability conflicts | QA lead unavailable last week | Sprint backlog approved 3/20
Testing & QA | 7/14 | 11/1 | 111 | Not Started | $ 8,000.00 | QA, Business Analyst | Test coverage gaps | Test plan needs revisions | UAT kickoff scheduled 5/8
Training & Documentation | 7/14 | 1/20 | 191 | Not Started | $ 6,500.00 | Instructional Designer, Support | Team unfamiliarity with internal wiki tool | Style guide incomplete | Live sessions scheduled 6/28–6/30
Go-Live | 8/1 | 10/1 | 62 | Not Started | $ 3,200.00 | DevOps, PM | Final approval delayed | Security review incomplete | Target launch date scheduled 7/15
Enter Text |  |  |  |  |  |  |  |  | 
Enter Text |  |  |  |  |  |  |  |  | 
Enter Text |  |  |  |  |  |  |  |  | 
Enter Text |  |  |  |  |  |  |  |  | 
Enter Text |  |  |  |  |  |  |  |  | 
Enter Text |  |  |  |  |  |  |  |  | 
Enter Text |  |  |  |  |  |  |  |  | 
Timeline
Project Notes

## Slide 3
Project Planning |  |  |  |  |  |  |  |  | 
Design Phase |  |  |  |  |  |  |  |  | 
Sprint 1 Development |  |  |  |  |  |  |  |  | 
Sprint 2 Development |  |  |  |  |  |  |  |  | 
Testing & QA |  |  |  |  |  |  |  |  | 
Training & Documentation |  |  |  |  |  |  |  |  | 
Go-Live |  |  |  |  |  |  |  |  | 
Enter Text |  |  |  |  |  |  |  |  | 
Enter Text |  |  |  |  |  |  |  |  | 
Enter Text |  |  |  |  |  |  |  |  | 
Enter Text |  |  |  |  |  |  |  |  | 
Enter Text |  |  |  |  |  |  |  |  | 
Enter Text |  |  |  |  |  |  |  |  | 
Enter Text |  |  |  |  |  |  |  |  | 
PROJECT SCHEDULE GRAPH
05/03/XX
06/02/XX
07/02/XX
08/01/XX
08/31/XX
09/30/XX
10/30/XX
11/29/XX
12/29/XX

## Slide 4
Project Schedule Template
PROJECT SCHEDULE
Project Title
YOUR
LOGO
Project Manager | Start Date | End Date

## Slide 5
PROJECT SCHEDULE
Phase Title | Start Date | End Date | Duration in days | Schedule | Budget | Resources | Risks | Issues | Comments
Phase A |  |  |  |  |  |  |  |  | 
Phase B |  |  |  |  |  |  |  |  | 
Phase C |  |  |  |  |  |  |  |  | 
Phase D |  |  |  |  |  |  |  |  | 
Phase E |  |  |  |  |  |  |  |  | 
Phase F |  |  |  |  |  |  |  |  | 
Phase G |  |  |  |  |  |  |  |  | 
Phase H |  |  |  |  |  |  |  |  | 
Phase I |  |  |  |  |  |  |  |  | 
Phase J |  |  |  |  |  |  |  |  | 
Phase K |  |  |  |  |  |  |  |  | 
Phase L |  |  |  |  |  |  |  |  | 
Phase M |  |  |  |  |  |  |  |  | 
Phase N |  |  |  |  |  |  |  |  | 
Timeline
Project Notes

## Slide 6
Phase A |  |  |  |  |  |  |  |  | 
Phase B |  |  |  |  |  |  |  |  | 
Phase C |  |  |  |  |  |  |  |  | 
Phase D |  |  |  |  |  |  |  |  | 
Phase E |  |  |  |  |  |  |  |  | 
Phase F |  |  |  |  |  |  |  |  | 
Phase G |  |  |  |  |  |  |  |  | 
Phase H |  |  |  |  |  |  |  |  | 
Phase I |  |  |  |  |  |  |  |  | 
Phase J |  |  |  |  |  |  |  |  | 
Phase K |  |  |  |  |  |  |  |  | 
Phase L |  |  |  |  |  |  |  |  | 
Phase M |  |  |  |  |  |  |  |  | 
Phase N |  |  |  |  |  |  |  |  | 
PROJECT SCHEDULE GRAPH
00/00/00
00/00/00
00/00/00
00/00/00
00/00/00
00/00/00
00/00/00
00/00/00
00/00/00

## Slide 7
DISCLAIMER Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.