## EXAMPLE - Project Schedule
Project Schedule Template Example
Project Name |  |  |  | Start Date
Internal Platform Revamp |  |  |  | 05/05/20xx
Project Manager |  |  |  | End Date
Sarah Goodwin |  |  |  | 10/01/20xx
| Timeline |  |  | Project Notes
Phase Title | Start Date | End Date | Duration (in days) | Schedule | Budget | Resources | Risks | Issues | Comments | Schedule
Project Planning | 2025-05-05 | 2025-07-01 | 58 | On Track | 4500 | PM, BA | Misalignment with exec priorities | None | Stakeholder kickoff completed | On Track
Design Phase | 2025-05-10 | 2025-08-10 | 93 | Slightly Behind | 12000 | UX, UI Designer, Product Owner | Approval delays on mockups | Pending feedback from the marketing team | Final prototype review scheduled 2/21 | Slightly Behind
Sprint 1 Development | 2025-06-10 | 2026-03-01 | 265 | On Track | 22000 | Backend Dev, API Lead | Integration delays with legacy systems | LDAP connector not syncing in dev | Dependencies mapped, daily standups started | Not Started
Sprint 2 Development | 2025-06-22 | 2025-08-04 | 44 | On Track | 25000 | Frontend Dev, QA | Resource availability conflicts | QA lead unavailable last week | Sprint backlog approved 3/20
Testing & QA | 2025-07-14 | 2025-11-01 | 111 | Not Started | 8000 | QA, Business Analyst | Test coverage gaps | Test plan needs revisions | UAT kickoff scheduled 5/8
Training & Documentation | 2025-07-14 | 2026-01-20 | 191 | Not Started | 6500 | Instructional Designer, Support | Team unfamiliarity with internal wiki tool | Style guide incomplete | Live sessions scheduled 6/28–6/30
Go-Live | 2025-08-01 | 2025-10-01 | 62 | Not Started | 3200 | DevOps, PM | Final approval delayed | Security review incomplete | Target launch date scheduled 7/15
Enter Text |  |  | 1
Enter Text |  |  | 1
Enter Text |  |  | 1
Enter Text |  |  | 1
Enter Text |  |  | 1
Enter Text |  |  | 1
Enter Text |  |  | 1
Delivery Timeline
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Project Schedule
Project Schedule
Project Name |  |  |  | Start Date
Project Manager |  |  |  | End Date
| Timeline |  |  | Project Notes
Phase Title | Start Date | End Date | Duration (in days) | Schedule | Budget | Resources | Risks | Issues | Comments | Schedule
|  |  | 1 | [6 empty] | On Track
|  |  | 1 | [6 empty] | Slightly Behind
|  |  | 1 | [6 empty] | Not Started
1
1
1
1
1
1
1
1
1
1
1
Delivery Timeline
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.