## EX - Project Work Schedule
Project Work Schedule Template Example
Project Name | Product Release |  |  |  |  | Start Date |  |  |  |  | 2025-09-02
Project Manager | Alexandra Mattson |  |  |  |  | End Date |  |  |  |  | 2025-10-09
Project Deliverable | [5 empty] | Overall Progress |  |  |  |  | 20%
Task | Owner | Start | End | Days | Status | 2015-09-02 | 2015-09-03 | 2015-09-04 | 2015-09-05 | 2015-09-06 | 2015-09-07 | 2015-09-08 | 2015-09-09 | 2015-09-10 | 2015-09-11 | 2015-09-12 | 2015-09-13 | 2015-09-14 | 2015-09-15 | 2015-09-16 | 2015-09-17 | 2015-09-18 | 2015-09-19 | 2015-09-20 | 2015-09-21 | 2015-09-22 | 2015-09-23 | 2015-09-24 | 2015-09-25 | 2015-09-26 | 2015-09-27 | 2015-09-28 | 2015-09-29 | 2015-09-30 | 2015-10-01 | 2015-10-02 | 2015-10-03 | 2015-10-04 | 2015-10-05 | 2015-10-06 | 2015-10-07 | 2015-10-08 | 2015-10-09 | Status
2032-03-16 | [43 empty] | Complete
Kick-Off Meeting | Alexandra Mattson | 2032-09-02 | 2032-09-02 | 0 | Complete | [38 empty] | In Progress
Objectives Planning | Brian Gorman | 2032-09-03 | 2032-09-07 | 4 | In Progress | [38 empty] | Not Started
Initiation | [43 empty] | Overdue
Detailed Requirements | Aviv Perez | 2032-09-07 | 2032-09-09 | 2 | Complete
Hardward Requirements | Aviv Perez | 2032-09-09 | 2032-09-11 | 2 | Overdue
Final Resource Plan | Aviv Perez | 2032-09-11 | 2032-09-15 | 4 | In Progress
Staffing | Alexandra Mattson | 2032-09-15 | 2032-09-17 | 2 | Not Started
Development
Techincal Requirements | Brian Gorman | 2032-09-17 | 2032-09-21 | 4 | Not Started
DB Development | Brooklyn Jansen | 2032-09-21 | 2032-09-23 | 2 | Not Started
API Development | Brooklyn Jansen | 2032-09-23 | 2032-09-25 | 2 | Not Started
UI Client | Alexandra Mattson | 2032-09-25 | 2032-09-29 | 4 | Not Started
Testing | Carmen Robertson | 2032-09-29 | 2032-10-02 | 3 | Not Started
Development Complete | Aviv Perez | 2032-10-02 | 2032-10-05 | 3 | Not Started
Operations
Hardware Configuration | Alexandra Mattson | 2032-10-05 | 2032-10-07 | 2 | Not Started
System Testing | Carmen Robertson | 2032-10-07 | 2032-10-09 | 2 | Not Started
Launch |  | 2032-10-09 | 2032-10-09
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Project Work Schedule
Project Work Schedule Template
Project Name | [5 empty] | Start Date
Project Manager | [5 empty] | End Date
Project Deliverable | [5 empty] | Overall Progress
Tasks | Owner | Start | End | Days | Status | 2015-09-02 | 2015-09-03 | 2015-09-04 | 2015-09-05 | 2015-09-06 | 2015-09-07 | 2015-09-08 | 2015-09-09 | 2015-09-10 | 2015-09-11 | 2015-09-12 | 2015-09-13 | 2015-09-14 | 2015-09-15 | 2015-09-16 | 2015-09-17 | 2015-09-18 | 2015-09-19 | 2015-09-20 | 2015-09-21 | 2015-09-22 | 2015-09-23 | 2015-09-24 | 2015-09-25 | 2015-09-26 | 2015-09-27 | 2015-09-28 | 2015-09-29 | 2015-09-30 | 2015-10-01 | 2015-10-02 | 2015-10-03 | 2015-10-04 | 2015-10-05 | 2015-10-06 | 2015-10-07 | 2015-10-08 | 2015-10-09 | Status
3/16/XX | [43 empty] | Complete
In Progress
Not Started
Initiation | [43 empty] | Overdue
Development
Operations
Launch

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.