## EXAMPLE - Product Launch
Software Product Launch Plan Example
Product Launch Plan |  |  |  | Start Date
2035-03-05
Use "BLANK" version tab for additional Task listings and weeks. | [6 empty] | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk 4 |  |  |  |  | Wk 5 |  |  |  |  | Wk 6 |  |  |  |  | Wk 7
TASK NAME | STATUS | PRIORITY | TASK OWNER | START DATE | END DATE | # of Days | 2035-03-05 | 2035-03-06 | 2035-03-07 | 2035-03-08 | 2035-03-09 | 2035-03-12 | 2035-03-13 | 2035-03-14 | 2035-03-15 | 2035-03-16 | 2035-03-19 | 2035-03-20 | 2035-03-21 | 2035-03-22 | 2035-03-23 | 2035-03-26 | 2035-03-27 | 2035-03-28 | 2035-03-29 | 2035-03-30 | 2035-04-02 | 2035-04-03 | 2035-04-04 | 2035-04-05 | 2035-04-06 | 2035-04-09 | 2035-04-10 | 2035-04-11 | 2035-04-12 | 2035-04-13 | 2035-04-16 | 2035-04-17 | 2035-04-18 | 2035-04-19 | 2035-04-20
PLANNING PHASE | In Progress | MED |  | 2035-03-05 | 2035-04-17 | 32 | bar: 2035-03-05 to 2035-04-20
Market Requirements Definition | Complete | LOW |  | 2035-03-05 | 2035-04-03 | 22 | bar: 2035-03-05 to 2035-04-03
Business Case | On Hold | LOW |  | 2035-04-02 | 2035-04-13 | 10 | bar: 2035-04-02 to 2035-04-13
Launch Plan | In Progress | HIGH |  | 2035-04-13 | 2035-04-17 | 3 | bar: 2035-04-13 to 2035-04-17
Target Metrics | Needs Review | LOW |  | 2035-04-11 | 2035-04-11 | 1 | bar: 2035-04-11
SALES TOOLS | Needs Update | MED |  | 2035-04-17 | 2035-04-25 | 7 | bar: 2035-03-05 to 2035-04-20
Prospect Presentation | Complete | MED |  | 2035-04-17 | 2035-04-23 | 5 | bar: 2035-04-17 to 2035-04-20
Demo | Not Started | MED |  | 2035-04-24 | 2035-04-25 | 2
Competitive Positioning | In Progress | LOW |  | 2035-04-23 | 2035-04-25 | 3
– FAQ sheet | Overdue | HIGH |  | 2035-04-23 | 2035-04-25 | 3
PRODUCT MARKETING | Overdue | HIGH |  | 2035-04-14 | 2035-04-30 | 11 | bar: 2035-03-05 to 2035-04-20
Pricing Strategy | Not Started | LOW |  | 2035-04-14 | 2035-04-18 | 3 | bar: 2035-04-16 to 2035-04-18
Product Positioning | On Hold | MED |  | 2035-04-15 | 2035-04-16 | 1 | bar: 2035-04-16
– Define Audience | On Hold | LOW |  | 2035-04-17 | 2035-04-17 | 1 | bar: 2035-04-17
– Core Messaging | On Hold | HIGH |  | 2035-04-21 | 2035-04-24 | 2
– Executive Approval | On Hold | LOW |  | 2035-04-25 | 2035-04-30 | 4
SOCIAL | Needs Review | LOW |  | 2025-04-28 | 2025-05-01 | 4
Define social media strategy | Needs Review | MED |  | 2025-04-28 | 2025-04-30 | 3
Schedule social media posts | Needs Review | MED |  | 2025-04-29 | 2025-05-01 | 3
PRODUCT RELEASE | Not Started | LOW |  | 2035-05-01 | 2035-05-16 | 12
Alpha Release | Not Started | LOW |  | 2035-05-01 | 2035-05-01 | 1
Beta Release | Not Started | LOW |  | 2035-05-05 | 2035-05-05 | 0
V1 General Availability | Not Started | LOW |  | 2035-05-12 | 2035-05-12 | 0
R2 Press Event | Not Started | LOW |  | 2035-05-16 | 2035-05-16 | 1
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Product Launch
Software Product Launch Plan
Product Launch Plan |  |  |  | Start Date
|  |  |  | 2035-03-05 |  |  | <-- Enter initial Start Date to populate Timeline dates.
User to complete non-shaded cells only. | [6 empty] | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk 4 |  |  |  |  | Wk 5 |  |  |  |  | Wk 6 |  |  |  |  | Wk 7 |  |  |  |  | Wk 8 |  |  |  |  | Wk 9 |  |  |  |  | Wk 10 |  |  |  |  | Wk 11 |  |  |  |  | Wk 12 |  |  |  |  | Wk 13 |  |  |  |  | Wk 14 |  |  |  |  | Wk 15 |  |  |  |  | Wk 16 |  |  |  |  | Wk 17 |  |  |  |  | Wk 18 |  |  |  |  | Wk 19 |  |  |  |  | Wk 20
TASK NAME | STATUS | PRIORITY | TASK OWNER | START DATE | END DATE | # of Days | [100 empty] | STATUS | PRIORITY | time axis 2035-03-05 to 2035-07-20
PLANNING PHASE |  |  |  | 0 | 0 | 0 | [100 empty] | Not Started | LOW
Market Requirements Definition | [5 empty] | 0 | [100 empty] | In Progress | MED
Business Case | [5 empty] | 0 | [100 empty] | Complete | HIGH
Launch Plan | [5 empty] | 0 | [100 empty] | On Hold
Target Metrics | [5 empty] | 0 | [100 empty] | Overdue
[6 empty] | 0 | [100 empty] | Needs Review
[6 empty] | 0 | [100 empty] | Needs Update
SALES TOOLS |  |  |  | 0 | 0 | 0
Prospect Presentation | [5 empty] | 0
Demo | [5 empty] | 0
Competitive Positioning | [5 empty] | 0
– FAQ sheet | [5 empty] | 0
0
0
PRODUCT MARKETING |  |  |  | 0 | 0 | 0
Pricing Strategy | [5 empty] | 0
Product Positioning | [5 empty] | 0
– Define Audience | [5 empty] | 0
– Core Messaging | [5 empty] | 0
– Executive Approval | [5 empty] | 0
0
SOCIAL |  |  |  | 0 | 0 | 0
Define social media strategy | [5 empty] | 0
Schedule social media posts | [5 empty] | 0
0
0
0
0
PRODUCT RELEASE |  |  |  | 0 | 0 | 0
Alpha Release | [5 empty] | 0
Beta Release | [5 empty] | 0
V1 General Availability | [5 empty] | 0
R2 Press Event | [5 empty] | 0
0
0

## Dropdown Keys - Do Not Delete
Dropdown Keys - Do Not Delete
Status | Priority
Not Started | LOW
In Progress | MED
Complete | HIGH
On Hold
Overdue
Needs Review
Needs Update

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.