## EXAMPLE Construction Dashboard
Construction Project Management Dashboard Example
Enter project data below; charts, graphs, and summary info will populate automatically. Shaded cells also will auto-populate.
This tab contains example data. To begin building your dashboard, use the BLANK tab. If necessary, enter alternate dropdown menu data in the tables at the bottom of this tab.
Portfolio Name |  |  |  |  | Portfolio Manager | Total Projects | Date of Last Update
Infrastructure and Roads Division |  |  |  |  | Marta Hicks | 14 | 10/21/20XX
Total Budget |  |  | Cost Variance |  | Average % Complete | Projects on Track |  | High-Risk Projects
4085000 |  |  | 669000 |  | 7.143% | 2% |  | 21.43%
Portfolio Financing | [5 empty] | Project Progress | [5 empty] | Risk Radar
Budget |  | 4085000
Actual |  | 3416000
Balance |  | 669000
Project Health Level |  |  |  | Priority Level | [7 empty] | Project Strategic Objective
Project Data
Project Health Level | Priority | Project ID | Project Name | Status | Project Summary | Project Manager | Budget | Actual | Budget Less Actual | Expected Date of Completion | Number of Days Remaining | Percent Of Project Complete | Risk Level | Associated Risks | Strategic Objective | Cost-Benefit Analysis Outcome | Comments | Attachments / Links
1 | High | IT-P12001 |  | On Hold |  | Olivia Carter | 800000 | 500000 | 300000 |  | – | 90% | Highly Unlikely |  | Improve Customer Loyalty
2 | Medium | IT-P12002 |  | Complete |  | Petrus Nishimura | 285000 | 312000 | -27000 |  | – | 100% | Unlikely |  | Increase Customer Value
3 | High | IT-P12003 |  | In Progress |  | Raghu Prakash | 430000 | 384000 | 46000 |  | – | 50% | Possible |  | Increase Brand Awareness
4 | Extreme | IT-P12004 |  | Planning |  | Olivia Carter | 1624000 | 1500000 | 124000 |  | – | 8% | Likely |  | Expand Market Reach
5 | Extreme | IT-P12005 |  | Approved |  | Sarah Goodwin | 946000 | 720000 | 226000 |  | – | 11% | Likely |  | Expand Market Reach
4 | Low | IT-P12006 |  | Approved |  | Henry McNeal | 0 | 0 | 0 |  | – | 17% | Highly Likely |  | Increase Revenue
4 | Low | IT-P12007 |  | Proposed |  | Tamika Marshall | 0 | 0 | 0 |  | – | 20% | Likely |  | Generate Leads
2 | Medium | IT-P12008 |  | Monitor |  | Victoria Pearson | 0 | 0 | 0 |  | – | 30% | Highly Likely |  | Increase Sales
1 | Medium | IT-P12009 |  | In Progress |  | Olivia Carter | 0 | 0 | 0 |  | – | 45% | Highly Likely |  | Modernize Technology
4 | High | IT-P12010 |  | Requested |  | Henry McNeal | 0 | 0 | 0 |  | – | 0% | Unlikely |  | Increase Customer Value
2 | High | IT-P12011 |  | Requested |  | Romy Bailey |  |  | – |  | – | 0% | Highly Unlikely |  | Increase Sales
3 | High | IT-P12012 |  | Monitor |  | Olivia Carter |  |  | – |  | – | 15% | Unlikely |  | Improve Customer Loyalty
4 | Extreme | IT-P12013 |  | Planning |  | Romy Bailey |  |  | – |  | – | 20% | Unlikely |  | Increase Sales
5 | High | IT-P12014 |  | In Progress |  | Henry McNeal |  |  | – |  | – | 75% | Unlikely |  | Grow & Innovate
Dropdown Menu and Chart Data
If necessary, enter alternate dropdown menu data in the tables below.
Quantity columns calculate automatically to populate Dashboard charts; do not alter.
Health Level | Health Quantity | Priority Level | Priority Quantity | Project Status | Status Quantity | Risk Level | Risk Quantity |  |  |  |  | Strategic Objective | Quantity
1 | 2 | Low | 2 | Proposed | 1 | Highly Unlikely | 2 |  |  |  |  | Improve Customer Loyalty | 2
2 | 3 | Medium | 3 | Requested | 2 | Unlikely | 5 |  |  |  |  | Modernize Technology | 1
3 | 2 | High | 6 | Approved | 2 | Possible | 1 |  |  |  |  | Expand Through M&A | 0
4 | 5 | Extreme | 3 | Planning | 2 | Likely | 3 |  |  |  |  | Grow & Innovate | 1
5 | 2 |  |  | In Progress | 3 | Highly Likely | 3 |  |  |  |  | Increase Brand Awareness | 1
|  |  |  | Complete | 1 | [6 empty] | Increase Customer Value | 2
|  |  |  | On Hold | 1 | [6 empty] | Expand Market Reach | 2
|  |  |  | Monitor | 2 | [6 empty] | Increase Revenue | 1
|  |  |  | Other | 0 | [6 empty] | Generate Leads | 1
[12 empty] | Increase Sales | 3
[12 empty] | Other | 0
[12 empty] | Other 2 | 0
[12 empty] | Other 3 | 0
[12 empty] | Other 4 | 0
[12 empty] | Other 5 | 0
[12 empty] | Other 6 | 0
[12 empty] | Other 7 | 0
CLICK HERE TO CREATE IN SMARTSHEET
Formulas:
Number of Days Remaining = IF(PROJECTS4[[#This Row],[Expected Date of Completion]]="","–",(PROJECTS4[[#This Row],[Expected Date of Completion]]-TODAY()))

## BLANK Construction Dashboard
Construction Project Management Dashboard
Enter project data below; charts, graphs, and summary info will populate automatically. Shaded cells also will auto-populate.
If necessary, enter alternate dropdown menu data in the tables at the bottom of this tab.
Portfolio Name |  |  |  |  | Portfolio Manager | Total Projects | Date of Last Update
[6 empty] | 14 | MM/DD/YY
Total Budget |  |  | Cost Variance |  | Average % Complete | Projects on Track |  | High-Risk Projects
0 |  |  | 0 |  | 7.143% | 0% |  | 21.43%
Portfolio Financing | [5 empty] | Project Progress | [5 empty] | Risk Radar
Budget |  | 0
Actual |  | 0
Balance |  | 0
Project Health Level |  |  |  | Priority Level | [7 empty] | Project Strategic Objective
Project Data
Project Health Level | Priority | Project ID | Project Name | Status | Project Summary | Project Manager | Budget | Actual | Budget Less Actual | Expected Date of Completion | Number of Days Remaining | Percent Of Project Complete | Risk Level | Associated Risks | Strategic Objective | Cost-Benefit Analysis Outcome | Comments | Attachments / Links
1 | High |  |  | On Hold |  |  | 0 | 0 | 0 |  | – | 90% | Highly Unlikely |  | Improve Customer Loyalty
2 | Medium |  |  | Complete |  |  | 0 | 0 | 0 |  | – | 100% | Unlikely |  | Increase Customer Value
3 | High |  |  | In Progress |  |  | 0 | 0 | 0 |  | – | 50% | Possible |  | Increase Brand Awareness
4 | Extreme |  |  | Planning |  |  | 0 | 0 | 0 |  | – | 8% | Likely |  | Expand Market Reach
5 | Extreme |  |  | Approved |  |  | 0 | 0 | 0 |  | – | 11% | Likely |  | Expand Market Reach
4 | Low |  |  | Approved |  |  | 0 | 0 | 0 |  | – | 17% | Highly Likely |  | Increase Revenue
4 | Low |  |  | Proposed |  |  | 0 | 0 | 0 |  | – | 20% | Likely |  | Generate Leads
2 | Medium |  |  | Monitor |  |  | 0 | 0 | 0 |  | – | 30% | Highly Likely |  | Increase Sales
1 | Medium |  |  | In Progress |  |  | 0 | 0 | 0 |  | – | 45% | Highly Likely |  | Modernize Technology
4 | High |  |  | Requested |  |  | 0 | 0 | 0 |  | – | 0% | Unlikely |  | Increase Customer Value
2 | High |  |  | Requested |  |  |  |  | – |  | – | 0% | Highly Unlikely |  | Increase Sales
3 | High |  |  | Monitor |  |  |  |  | – |  | – | 15% | Unlikely |  | Improve Customer Loyalty
4 | Extreme |  |  | Planning |  |  |  |  | – |  | – | 20% | Unlikely |  | Increase Sales
5 | High |  |  | In Progress |  |  |  |  | – |  | – | 75% | Unlikely |  | Grow & Innovate
Dropdown Menu and Chart Data
If necessary, enter alternate dropdown menu data in the tables below.
Quantity columns calculate automatically to populate Dashboard charts; do not alter.
Health Level | Health Quantity | Priority Level | Priority Quantity | Project Status | Status Quantity | Risk Level | Risk Quantity |  |  |  |  | Strategic Objective | Quantity
1 | 2 | Low | 2 | Proposed | 1 | Highly Unlikely | 2 |  |  |  |  | Improve Customer Loyalty | 2
2 | 3 | Medium | 3 | Requested | 2 | Unlikely | 5 |  |  |  |  | Modernize Technology | 1
3 | 2 | High | 6 | Approved | 2 | Possible | 1 |  |  |  |  | Expand Through M&A | 0
4 | 5 | Extreme | 3 | Planning | 2 | Likely | 3 |  |  |  |  | Grow & Innovate | 1
5 | 2 |  |  | In Progress | 3 | Highly Likely | 3 |  |  |  |  | Increase Brand Awareness | 1
|  |  |  | Complete | 1 | [6 empty] | Increase Customer Value | 2
|  |  |  | On Hold | 1 | [6 empty] | Expand Market Reach | 2
|  |  |  | Monitor | 2 | [6 empty] | Increase Revenue | 1
|  |  |  | Other | 0 | [6 empty] | Generate Leads | 1
[12 empty] | Increase Sales | 3
[12 empty] | Other | 0
[12 empty] | Other 2 | 0
[12 empty] | Other 3 | 0
[12 empty] | Other 4 | 0
[12 empty] | Other 5 | 0
[12 empty] | Other 6 | 0
[12 empty] | Other 7 | 0
Formulas:
Number of Days Remaining = IF(PROJECTS[[#This Row],[Expected Date of Completion]]="","–",(PROJECTS[[#This Row],[Expected Date of Completion]]-TODAY()))

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.