## EX - CPM Const Sched
Critical Path Method (CPM) Construction Schedule Template Example
Complete non-shaded fields, only. |  |  |  | Start Date | [5 empty] | 2025-01-17
| – CRITICAL ACTIVITIES |  |  | Finish Date excluding wknds & holidays | [5 empty] | 2025-09-26 | DURATION in days | 175.3333
DURATION in days
|  |  |  | Predecessor Activities | [5 empty] | Optimistic | Most Likely | Pessimistic | Expected | Early Start | Early Finish | Late Start | Late Finish
ID | Task Name | Assigned To | Status | PA – enter separately in columns | [5 empty] | MIN | AVG | MAX | DURATION | ES | EF | LS | LF | SLACK | Status
1 | START |  | In Progress | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | Not Started
2 | Task 2 |  | Complete | 1 | [5 empty] | 8 | 10 | 12 | 10 | 0 | 10 | 0 | 0 | 0 | In Progress
3 | Task 3 |  | Not Started | 1 | [5 empty] | 2 | 5 | 8 | 5 | 0 | 5 | 0 | 0 | 0 | Complete
4 | Task 4 |  | Overdue | 2 | [5 empty] | 30 | 45 | 60 | 45 | 10 | 55 | 0 | 0 | 0 | On Hold
5 | Task 5 |  | On Hold | 1 | 2 | 3 |  |  |  | 8 | 11 | 14 | 11 | 10 | 21 | 0 | 0 | 0 | Overdue
6 | Task 6 |  | Needs Review | 3 | 4 | 5 |  |  |  | 10 | 14 | 18 | 14 | 55 | 69 | 0 | 0 | 0 | Needs Review
7 | Task 7 |  | Needs Update | 6 | [5 empty] | 12 | 14 | 16 | 14 | 69 | 83 | 0 | 0 | 0 | Needs Update
8 | Task 8 |  |  | 7 | [5 empty] | 15 | 19 | 25 | 19.6667 | 83 | 102.6667 | 0 | 0 | 0
9 | Task 9 |  |  | 6 | 7 | 8 |  |  |  | 1 | 3 | 5 | 3 | 102.6667 | 105.6667 | 0 | 0 | 0
10 | Task 10 |  |  | 8 | [5 empty] | 8 | 10 | 20 | 12.6667 | 102.6667 | 115.3333 | 0 | 0 | 0
11 | Task 11 |  |  | 9 | 10 |  |  |  |  | 1 | 3 | 5 | 3 | 115.3333 | 118.3333 | 0 | 0 | 0
12 | Task 12 |  |  | 10 | [5 empty] | 5 | 9 | 15 | 9.6667 | 115.3333 | 125 | 0 | 0 | 0
13 | Task 13 |  |  | 12 | [5 empty] | 4 | 9 | 13 | 8.6667 | 125 | 133.6667 | 0 | 0 | 0
14 | Task 14 |  |  | 11 | 12 | 13 | [6 empty] | 0 | 133.6667 | 133.6667 | 32 | 32 | 0
15 | Task 15 |  |  | 11 | 14 |  |  |  |  | 1 | 3 | 5 | 3 | 133.6667 | 136.6667 | 0 | 0 | 0
16 | Task 16 |  |  | 14 | 15 |  |  |  |  | 3 | 6 | 7 | 5.3333 | 136.6667 | 142 | 0 | 0 | 0
17 | Task 17 |  |  | 13 | 15 | 16 |  |  |  | 5 | 9 | 12 | 8.6667 | 142 | 150.6667 | 0 | 0 | 0
18 | Task 18 |  |  | 11 | 12 | 13 | 14 | 16 | 17 | 1 | 3 | 5 | 3 | 150.6667 | 153.6667 | 0 | 0 | 0
19 | Task 19 |  |  | 12 | 18 |  |  |  |  | 1 | 2 | 5 | 2.6667 | 153.6667 | 156.3333 | 0 | 0 | 0
20 | Task 20 |  |  | 18 | 19 |  |  |  |  | 2 | 4 | 6 | 4 | 156.3333 | 160.3333 | 0 | 0 | 0
21 | Task 21 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0
22 | Task 22 |  |  | 13 | 15 | 16 |  |  |  | 3 | 7 | 10 | 6.6667 | 142 | 148.6667 | 0 | 0 | 0
23 | Task 23 |  |  | 11 | 12 | 13 | 14 | 16 | 17 | 7 | 11 | 15 | 11 | 150.6667 | 161.6667 | 164.3333 | 175.3333 | 13.6667
24 | Task 24 |  |  | 12 | 18 |  |  |  |  | 20 | 20 | 25 | 21.6667 | 153.6667 | 175.3333 | 153.6667 | 175.3333 | 0
25 | FINISH |  |  | 23 | 24 | [7 empty] | 0 | 175.3333 | 175.3333 | 175.3333 | 175.3333 | 0
CLICK HERE TO CREATE IN SMARTSHEET
CALCULATIONS FOR CHART AREA
[19 empty] | PA EF | [5 empty] | SA | [23 empty] | SA LS | [23 empty] | ES | C | over | under | DURATION | over | under | SLACK | EVENTS | EVENTS | AXIS
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 3 |  | 5 | [20 empty] | 0 | 0 |  | 0 | [19 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | -0.5
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4 | 5 | [22 empty] | 0 | 0 | [19 empty] | 0 | 10 | 2 | 2 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 0.5
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 5 | 6 | [22 empty] | 0 | 0 | [18 empty] | 0 | 5 | 3 | 3 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 1.5
[19 empty] | 10 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 6 | [23 empty] | 0 | [18 empty] | 10 | 45 | 15 | 15 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 2.5
[19 empty] | 0 | 10 | 5 | 0 | 0 | 0 | [5 empty] | 6 | [23 empty] | 0 | [18 empty] | 10 | 11 | 3 | 3 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 3.5
[19 empty] | 5 | 55 | 21 | 0 | 0 | 0 | [6 empty] | 7 |  | 9 | [21 empty] | 0 |  | 0 | [15 empty] | 55 | 14 | 4 | 4 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 4.5
[19 empty] | 69 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 8 | 9 | [22 empty] | 0 | 0 | [15 empty] | 69 | 14 | 2 | 2 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 5.5
[19 empty] | 83 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 9 | 10 | [22 empty] | 0 | 0 | [14 empty] | 83 | 19.6667 | 5.3333 | 4.6667 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 6.5
[19 empty] | 69 | 83 | 102.6667 | 0 | 0 | 0 | [10 empty] | 11 | [23 empty] | 0 | [13 empty] | 102.6667 | 3 | 2 | 2 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 7.5
[19 empty] | 102.6667 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 11 | 12 | [22 empty] | 0 | 0 | [12 empty] | 102.6667 | 12.6667 | 7.3333 | 4.6667 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 8.5
[19 empty] | 105.6667 | 115.3333 | 0 | 0 | 0 | 0 | [13 empty] | 14 | 15 |  |  | 18 |  |  |  | 23 | [15 empty] | 32 | 0 |  |  | 0 |  |  |  | 164.3333 |  |  | 115.3333 | 3 | 2 | 2 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 9.5
[19 empty] | 115.3333 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 13 | 14 |  |  |  | 18 | 19 |  |  | 23 | 24 | [13 empty] | 0 | 32 |  |  |  | 0 | 0 |  |  | 164.3333 | 153.6667 |  | 115.3333 | 9.6667 | 5.3333 | 4.6667 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 10.5
[19 empty] | 125 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 14 |  |  | 17 | 18 |  |  | 22 | 23 | [15 empty] | 32 |  |  | 0 | 0 |  |  | 0 | 164.3333 |  |  | 125 | 8.6667 | 4.3333 | 4.6667 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 11.5
[19 empty] | 118.3333 | 125 | 133.6667 | 0 | 0 | 0 | [14 empty] | 15 | 16 |  | 18 |  |  |  | 23 | [16 empty] | 0 | 0 |  | 0 |  |  |  | 164.3333 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.4 | 32 | 12.5
[19 empty] | 118.3333 | 133.6667 | 0 | 0 | 0 | 0 | [15 empty] | 16 | 17 |  |  |  | 22 | [18 empty] | 0 | 0 |  |  |  | 0 |  |  |  | 133.6667 | 3 | 2 | 2 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 13.5
[19 empty] | 133.6667 | 136.6667 | 0 | 0 | 0 | 0 | [16 empty] | 17 | 18 |  |  | 22 | 23 | [18 empty] | 0 | 0 |  |  | 0 | 164.3333 |  |  | 136.6667 | 5.3333 | 1.6667 | 2.3333 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 14.5
[19 empty] | 133.6667 | 136.6667 | 142 | 0 | 0 | 0 | [17 empty] | 18 |  |  |  | 23 | [19 empty] | 0 |  |  |  | 164.3333 |  |  | 142 | 8.6667 | 3.3333 | 3.6667 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 15.5
[19 empty] | 118.3333 | 125 | 133.6667 | 133.6667 | 142 | 150.6667 | [18 empty] | 19 | 20 |  |  | 24 | [19 empty] | 0 | 0 |  |  | 153.6667 |  | 150.6667 | 3 | 2 | 2 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 16.5
[19 empty] | 125 | 153.6667 | 0 | 0 | 0 | 0 | [19 empty] | 20 | [23 empty] | 0 |  |  |  |  | 153.6667 | 2.6667 | 2.3333 | 1.6667 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 17.5
[19 empty] | 153.6667 | 156.3333 | 0 | 0 | 0 | 0 | [48 empty] | 156.3333 | 4 | 2 | 2 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 18.5
[19 empty] | 0 | 0 | 0 | 0 | 0 | 0 | [48 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 19.5
[19 empty] | 133.6667 | 136.6667 | 142 | 0 | 0 | 0 | [48 empty] | 142 | 6.6667 | 3.3333 | 3.6667 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 20.5
[19 empty] | 118.3333 | 125 | 133.6667 | 133.6667 | 142 | 150.6667 | [23 empty] | 25 | [23 empty] | 175.3333 | 150.6667 | #N/A | #N/A | #N/A | 11 | 4 | 4 | 13.6667 | #N/A | #N/A | 21.5
[19 empty] | 125 | 153.6667 | 0 | 0 | 0 | 0 | [23 empty] | 25 | [23 empty] | 175.3333 | 153.6667 | 21.6667 | 3.3333 | 1.6667 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 22.5
[19 empty] | 161.6667 | 175.3333 | 0 | 0 | 0 | 0 | [48 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 35.0667 | 175.3333 | 23.5

## BLANK - CPM Const Sched
Critical Path Method (CPM) Construction Schedule Template
Complete non-shaded fields, only. |  |  |  | Start Date
| – CRITICAL ACTIVITIES |  |  | Finish Date excluding wknds & holidays | 0 | DURATION in days | 0
DURATION in days
|  |  |  | Predecessor Activities | Optimistic | Most Likely | Pessimistic | Expected | Early Start | Early Finish | Late Start | Late Finish
ID | Task Name | Assigned To | Status | PA – enter separately in columns | MIN | AVG | MAX | DURATION | ES | EF | LS | LF | SLACK | Status
1 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | Not Started
2 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | In Progress
3 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | Complete
4 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | On Hold
5 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | Overdue
6 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | Needs Review
7 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | Needs Update
8 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
9 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
10 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
11 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
12 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
13 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
14 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
15 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
16 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
17 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
18 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
19 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
20 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
21 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
22 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
23 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
24 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
25 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0
CALCULATIONS FOR CHART AREA
[14 empty] | PA EF | [5 empty] | SA | SA LS | ES | C | over | under | DURATION | over | under | SLACK | EVENTS | EVENTS | AXIS
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | -0.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 1.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 3.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 4.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 5.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 6.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 7.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 8.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 9.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 11.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 12.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 13.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 14.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 15.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 16.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 17.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 18.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 19.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 20.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 21.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 22.5
[14 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 23.5

## Holidays - customize
Enter Non-Working Holidays, below.
DATE | DESCRIPTION
2025-01-01 | New Year's Day
2025-01-20 | Martin Luther King Jr.'s Birthday
2025-02-17 | Washington's Birthday
2025-05-26 | Memorial Day
2025-07-04 | Independence Day
2025-09-01 | Labor Day
2025-10-13 | Columbus Day
2025-11-11 | Veterans Day
2025-11-27 | Thanksgiving Day
2025-12-25 | Christmas Day
2026-01-01 | New Year's Day
2026-01-19 | Martin Luther King Jr.'s Birthday
2026-02-16 | Washington's Birthday
2026-05-25 | Memorial Day
2026-07-04 | Independence Day
2026-09-07 | Labor Day
2026-10-12 | Columbus Day
2026-11-11 | Veterans Day
2026-11-26 | Thanksgiving Day
2026-12-25 | Christmas Day
2027-01-01 | New Year's Day
2027-01-18 | Martin Luther King Jr.'s Birthday
2027-02-15 | Washington's Birthday
2027-05-31 | Memorial Day
2027-07-04 | Independence Day
2027-09-06 | Labor Day
2027-10-10 | Columbus Day
2027-11-11 | Veterans Day
2027-11-25 | Thanksgiving Day
2027-12-24 | Christmas Day observed
2028-01-01 | New Year's Day
2028-01-17 | Martin Luther King Jr.'s Birthday
2028-02-21 | Washington's Birthday
2028-05-29 | Memorial Day
2028-07-04 | Independence Day
2028-09-04 | Labor Day
2028-10-09 | Columbus Day
2028-11-10 | Veterans Day
2028-11-23 | Thanksgiving Day
2028-12-25 | Christmas Day
2029-01-01 | New Year's Day
2029-01-15 | Martin Luther King Jr.'s Birthday
2029-02-19 | Washington's Birthday
2029-05-28 | Memorial Day
2029-07-04 | Independence Day
2029-09-03 | Labor Day
2029-10-08 | Columbus Day
2029-11-12 | Veterans Day
2029-11-22 | Thanksgiving Day
2029-12-25 | Christmas Day
2030-01-01 | New Year's Day
2030-01-21 | Martin Luther King Jr.'s Birthday
2030-02-18 | Washington's Birthday
2030-05-27 | Memorial Day
2030-07-04 | Independence Day
2030-09-02 | Labor Day
2030-10-14 | Columbus Day
2030-11-11 | Veterans Day
2030-11-28 | Thanksgiving Day
2030-12-25 | Christmas Day

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.