## Multiple Project Tracking
Multiple Construction Project Tracking Template
Date | Total Active Projects | Projects on Track (auto-populates) | Project Schedules at Risk (auto-populates) | Average % Complete Across All Projects | Project Summary
MM/DD/YY | 0 | 0 | 0 | 95.91% | Description of the project:
Project Key Status Indicators: The table below will highlight project names based on whether…
The project schedule is on time |  | The project schedule is over the estimated timeframe
[6 empty] | Auto-populates | Auto-populates |  |  |  | Auto-populates
Project Name | Client Name | Project Manager | Start Date | Estimated End Date | Actual End Date | Duration (in days from actual end date) | Percent Complete (based on actual end date) | Current Phase | Budget Total | Budget Spent | Variance | Notes / Action Items
Whispering Pines Homes | Name | Name | 2025-05-01 | 2025-05-10 | 2025-05-16 | 15 | 100% | In Progress | 50000000 | 45000000 | 5000000 | Notes
Blue Alder Business Park | Name | Name | 2025-05-01 | 2025-05-10 | 2025-05-10 | 9 | 100% | Complete | 150000000 | 160000000 | -10000000 | Notes
Orchard Creek Center | Name | Name | 2025-04-15 | 2025-05-02 | 2025-05-01 | 16 | 100% | Complete | 35000000 | 18654000 | 16346000 | Notes
Iron Hollow Logistics Hub | Name | Name | 2025-05-01 | 2025-05-10 | 2025-05-16 | 15 | 100% | In Progress | 80000000 | 42100000 | 37900000
RedFern Rowhouses | Name | Name | 2025-05-10 | 2025-06-02 | 2025-06-02 | 23 | 73.91% | Planning | 120000000 | 35000000 | 85000000
Hearthstone Senior Living | Name | Name | 2025-05-14 | 2025-05-18 | 2025-05-25 | 11 | 100% | In Progress | 150000000 | 160000000 | -10000000
Foxglove Transit Depot | Name | Name | 2025-02-02 | 2025-05-01 | 2025-05-30 | 117 | 97.44% | Complete | 50000000 | 45000000 | 5000000
[7 empty] | #VALUE! | Complete | 0 | 0 | 0
[7 empty] | #VALUE! | In Progress | 0 | 0 | 0
[7 empty] | #VALUE! | Planning | 0 | 0 | 0
[7 empty] | #VALUE! | In Progress | 0 | 0 | 0
[7 empty] | #VALUE! | Complete | 0 | 0 | 0
[7 empty] | #VALUE! | Complete | 0 | 0 | 0
[7 empty] | #VALUE! | In Progress | 0 | 0 | 0
[7 empty] | #VALUE! | Planning | 0 | 0 | 0
[7 empty] | #VALUE! | In Progress | 0 | 0 | 0
[7 empty] | #VALUE! | Complete | 0 | 0 | 0
[7 empty] | #VALUE! | Complete | 0 | 0 | 0
[7 empty] | #VALUE! | In Progress | 0 | 0 | 0
[7 empty] | #VALUE! | Planning | 0 | 0 | 0
[7 empty] | #VALUE! | In Progress | 0 | 0 | 0
[7 empty] | #VALUE! | Complete | 0 | 0 | 0
[7 empty] | #VALUE! | Complete | 0 | 0 | 0
[7 empty] | #VALUE! | In Progress | 0 | 0 | 0
[7 empty] | #VALUE! | Planning | 0 | 0 | 0
[7 empty] | #VALUE! | In Progress | 0 | 0 | 0
[7 empty] | #VALUE! | Complete | 0 | 0 | 0
CLICK HERE TO CREATE IN SMARTSHEET
Formulas:
Auto-populates = IF([Start Date]="", "", MAX(0, IF([Project Summary]="", TODAY() - [Start Date], [Project Summary] - [Start Date])))
Auto-populates = MIN(1, MAX(0, (TODAY() - [Start Date]) / [Auto-populates]))

## Phase Key - DO NOT DELETE
Dropdown Key - Do Not Delete
Current Phase
Planning
In Progress
Delayed
Complete

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.