## EXAMPLE Res Construction Sched
Residential Construction Schedule Template Example
Project Location |  |  |  |  | Project Manager |  |  | Start Date
Address |  |  |  |  | Name |  |  | 2028-01-05 | <--Enter date of Sunday of first week.
WBS | Task Name | Responsible Party | Planned Start Date | Planned End Date | Actual Start Date | Actual Finish Date | DURATION in days | Percentage Complete | Notes | 2028-01-05 | [6 empty] | 2028-01-12 | [6 empty] | 2028-01-19 | [6 empty] | 2028-01-26 | [6 empty] | 2028-02-02 | [6 empty] | 2028-02-09 | [6 empty] | 2028-02-16 | [6 empty] | 2028-02-23 | [6 empty] | 2028-03-01 | [6 empty] | 2028-03-08 | [6 empty] | 2028-03-15 | [6 empty] | 2028-03-22 | [6 empty] | 2028-03-29 | [6 empty] | 2028-04-05 | [6 empty] | 2028-04-12 | [6 empty] | 2028-04-19 | [6 empty] | 2028-04-26 | [6 empty] | 2028-05-03 | [6 empty] | 2028-05-10 | [6 empty] | 2028-05-17 | [6 empty] | 2028-05-24 | [6 empty] | 2028-05-31 | [6 empty] | 2028-06-07 | [6 empty] | 2028-06-14 | [6 empty] | 2028-06-21 | [6 empty] | 2028-06-28 | [6 empty] | 2028-07-05 | [6 empty] | 2028-07-12
[10 empty] | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa
1 | PRE-CONSTRUCTION |  |  |  | 2028-01-06 | 2028-01-14 | 9 | 92.5%
1.1 | Contracts |  |  |  | 2028-01-06 | 2028-01-14 | 9 | 100% | bar: 2028-01-05 M to 2028-01-12 Sa
1.2 | Financing |  |  |  | 2028-01-07 | 2028-01-10 | 4 | 85% | bar: 2028-01-05 T to 2028-01-05 F
2 | FOUNDATION |  |  |  | 2028-01-10 | 2028-01-20 | 11 | 75% | bar: 2028-01-05 F to 2028-01-19 M
2.1 | Layout, Pour, and Pin Footings |  |  |  | 2028-01-10 | 2028-01-13 | 4 | 90% | bar: 2028-01-05 F to 2028-01-12 Sa
2.2 | Block, Mortar, Sand Foundation |  |  |  | 2028-01-12 | 2028-01-20 | 9 | 75% | bar: 2028-01-12 Su to 2028-01-19 M
3 | DRAW #1
3.1 | Steel and Lumber Delivery
3.2 | Waterproofing and Drain Tile
4 | FRAMING
4.1 | Set Steel
4.2 | Deck Framing
4.3 | Specialty Rough-Ins (Alarm, Cable, etc.)
5 | ROOF
5.1 | Roof Trusses
5.2 | Roofing Paper and Shingles
6 | DRAW #2
6.1 | Wall Framing
6.2 | Windows and Doors
7 | EXTERIOR FINISHES
7.1 | Siding
7.2 | Trim and Brick Veneer
8 | PLUMBING/ELECTRICAL/HVAC
8.1 | Plumbing/Electrical/HVAC Rough-In
8.2 | Inspections
9 | DRAW #3
9.1 | Frame Basement
9.2 | Frame Bulkheads
10 | INSULATION/DRYWALL
10.1 | Caulk, Air Seal, Draft and Fire Stop, Insulation
10.2 | Hang, Tape, Finish, and Sand Drywall
11 | INTERIOR FINISHES
11.1 | Interior Walls and Trim
11.2 | Cabinetry and Countertops
12 | DRAW #4
12.1 | Paint Cabinets and Doors
12.2 | Switch and Plug Finishing
13 | FLOORING
13.1 | Tile and Hardwood Install, Sand, Stain, Seal
13.2 | Carpet Install
14 | FIXTURES AND APPLIANCES
14.1 | Remaining Lights/Fans
14.2 | Appliance Install
15 | DRAW #5
15.1 | Door Hardware
15.2 | Bath Hardware
16 | LANDSCAPING/DESIGN
16.1 | Patios, Porches, Decks, Drive and Walkways
16.2 | Yard, Plants, Groundskeeping
17 | FINAL DETAILS/CLOSEOUT
17.1 | Final Walk-Through
17.2 | Final Touch-Ups
18 | FINAL DRAW
18.1 | Cleaning
18.2 | Move-In
CLICK HERE TO CREATE IN SMARTSHEET | bar: 2028-01-05 Su to 2028-01-26 Sa
Formulas:
Project Manager = IF(MIN([Project Manager, row below]:G10) > 0, MIN([Project Manager, row below]:G10), "")
TODAY

## BLANK Res Construction Sched
Residential Construction Schedule Template
Project Location |  |  |  |  | Project Manager |  |  | Start Date
[8 empty] | 2028-01-05 | <--Enter date of Sunday of first week.
WBS | Task Name | Responsible Party | Planned Start Date | Planned End Date | Actual Start Date | Actual Finish Date | DURATION in days | Percentage Complete | Notes | 2028-01-05 | [6 empty] | 2028-01-12 | [6 empty] | 2028-01-19 | [6 empty] | 2028-01-26 | [6 empty] | 2028-02-02 | [6 empty] | 2028-02-09 | [6 empty] | 2028-02-16 | [6 empty] | 2028-02-23 | [6 empty] | 2028-03-01 | [6 empty] | 2028-03-08 | [6 empty] | 2028-03-15 | [6 empty] | 2028-03-22 | [6 empty] | 2028-03-29 | [6 empty] | 2028-04-05 | [6 empty] | 2028-04-12 | [6 empty] | 2028-04-19 | [6 empty] | 2028-04-26 | [6 empty] | 2028-05-03 | [6 empty] | 2028-05-10 | [6 empty] | 2028-05-17 | [6 empty] | 2028-05-24 | [6 empty] | 2028-05-31 | [6 empty] | 2028-06-07 | [6 empty] | 2028-06-14 | [6 empty] | 2028-06-21 | [6 empty] | 2028-06-28 | [6 empty] | 2028-07-05 | [6 empty] | 2028-07-12
[10 empty] | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa
1 | Pre-Construction |  |  |  | 2028-01-01 | 2028-01-02 | 2 | 100%
1.1 | [7 empty] | 0% | bar: 2028-01-05 M to 2028-01-12 T
1.2 | [7 empty] | 0% | bar: 2028-01-05 T to 2028-01-05 F
1.3 | [7 empty] | 0% | bar: 2028-01-12 M to 2028-01-12 W
1.4 | [7 empty] | 0% | bar: 2028-01-12 W to 2028-01-12 F
1.5
1.6
1.7
1.8
1.9
1.10.
2 | Foundation
2.1
2.2
2.3
2.4
2.5
2.6
2.7
2.8
2.9
2.10.
3 | Draw #1
3.1
3.2
3.3
3.4
3.5
3.6
3.7
3.8
3.9
3.10.
4 | Framing
4.1
4.2
4.3
4.4
4.5
4.6
4.7
4.8
4.9
4.10.
5 | Roof
5.1
5.2
5.3
5.4
5.5
5.6
5.7
5.8
5.9
5.10.
6 | Draw #2
6.1
6.2
6.3
6.4
6.5
6.6
6.7
6.8
6.9
6.10.
7 | Exterior Finishes
7.1
7.2
7.3
7.4
7.5
7.6
7.7
7.8
7.9
7.10.
8 | Plumbing/Electrical/HVAC
8.1
8.2
8.3
8.4
8.5
8.6
8.7
8.8
8.9
8.10.
9 | Draw #3
9.1
9.2
9.3
9.4
9.5
9.6
9.7
9.8
9.9
9.10.
10 | Insulation/Drywall
10.1
10.2
10.3
10.4
10.5
10.6
10.7
10.8
10.9
10.10.
11 | Interior Finishes
11.1
11.2
11.3
11.4
11.5
11.6
11.7
11.8
11.9
11.10.
12 | Draw #4
12.1
12.2
12.3
12.4
12.5
12.6
12.7
12.8
12.9
12.10.
13 | Flooring
13.1
13.2
13.3
13.4
13.5
13.6
13.7
13.8
13.9
13.10.
14 | Fixtures and Appliances
14.1
14.2
14.3
14.4
14.5
14.6
14.7
14.8
14.9
14.10.
15 | Draw #5
15.1
15.2
15.3
15.4
15.5
15.6
15.7
15.8
15.9
15.10.
16 | Landscaping/Design
16.1
16.2
16.3
16.4
16.5
16.6
16.7
16.8
16.9
16.10.
17 | Final Details/Closeout
17.1
17.2
17.3
17.4
17.5
17.6
17.7
17.8
17.9
17.10.
TODAY

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.