## EXAMPLE Construction Schedule
Simple Construction Schedule Template Example
Project Title | Start
Project Alpha | 2025-09-21
Project Manager | End
Lori Garcia | 2025-12-30 |  | Note: The estimated duration column auto-populates.
Task Name | Estimated Start Date | Estimated End Date | Estimated Duration in days | Comments
Plan and Design | 2035-09-21 | 2035-09-30 | 10
Site Prep | 2035-10-01 | 2035-10-06 | 6
Foundation Work | 2035-10-06 | 2035-10-24 | 19
Framing | 2035-10-25 | 2035-10-29 | 5
Plumbing | 2035-11-01 | 2035-11-13 | 13
Electrical | 2035-11-13 | 2035-11-15 | 3
HVAC | 2035-10-25 | 2035-12-05 | 42
Roofing | 2035-11-19 | 2035-12-10 | 22
Windows and Doors | 2035-10-29 | 2035-12-09 | 42
Exterior Finishing | 2035-11-22 | 2035-12-15 | 24
Interior Finishing | 2035-11-29 | 2035-12-20 | 22
Final Inspections | 2035-12-10 | 2035-12-22 | 13
Punch List | 2035-12-10 | 2035-12-15 | 6
Project Completion | 2035-12-27 | 2035-12-30 | 4
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Construction Schedule
Simple Construction Schedule Template
Project Title | Start
Name | MM/DD
Project Manager | End
Name | MM/DD |  | Note: The estimated duration column auto-populates.
Task Name | Estimated Start Date | Estimated End Date | Estimated Duration in days | Comments
Task 1 | 2035-09-21 | 2035-09-30 | 10
Task 2
Task 3
Task 4
Task 5
Task 6
Task 7
Task 8
Task 9
Task 10
Task 11
Task 12
Task 13
Task 14
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.