## EXAMPLE Proj. Mgmt. To-Do List
To-Do List for Project Management Template Example
Project Information
Task Name | Status | Priority | Start Date | Due Date | Project Phase / Category | Assigned to | Dependencies | Completion % | Notes
Design project wireframes | In Progress | High | 03/01/20XX | 03/15/20XX | Design Phase | Alexandra Mattson | None | 45% | Final review pending with UX team
Develop campaign landing page | Not Started | Medium | 03/05/20XX | 03/25/20XX | Development Phase | Aviv Perez | Wireframes approved | 0% | Waiting on creative assets
QA website functionality | Not Started | High | 03/10/20XX | 03/30/20XX | Testing Phase | Brian Gorman | Development complete | 0% | Create checklist before starting
Draft social media content | In Progress | Medium | 03/02/20XX | 03/12/20XX | Content Phase | Brooklyn Jansen | Campaign goals confirmed | 60% | Pending video assets
Prepare client presentation deck | Completed | Low | 03/08/20XX | 03/18/20XX | Client Deliverables | Carmen Robertson | Content drafts finalized | 100% | Submitted for client feedback
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Proj. mgmt. To-Do List
To-Do List for Project Management Template
Project Information
Task Name | Status | Priority | Start Date | Due Date | Project Phase / Category | Assigned to | Dependencies | Completion % | Notes
0%
0%
0%
0%
0%

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
Priority | Status
High | Completed
Medium | In Progress
Low | Blocked
Not Started

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.